## 000-H-MRQ-60001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ali Abbas | delete
2 | Text Box | 7 | Ebrahim | Not in the AVL and not in the additional subcontractor list also. TTSJV to clarify
3 | Text Box | 7 | Ebrahim | Remove electrical equipment as it is not in the scope of supply
4 | Text Box | 3 | Mahdi Ali | Remove spaces
5 | Text Box | 2 | Mahdi Ali | should read P&ID without spaces
6 | Call-out | 3 | Mahdi Ali | Should read PLATE SIZE. Remove spaces