## 000-K-ITP-80001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Saeed Taher | add c in all pages
2 | Callout | 2 | Saeed Taher | Add o in all pages
3 | Callout | 1 | Saeed Taher | Confirm criticality rating and inspection level
4 | Callout | 2 | Saeed Taher | Owner inspection requirements to be finalized during ITP finalization with vendor
5 | Callout | 3 | Saeed Taher | Painting Procedure
6 | Callout | 3 | Saeed Taher | PWHT & NDE Procedures
7 | Callout | 3 | Saeed Taher | WPS, WPQR, Weld map & NDE map