## 000-A-PRO-50009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | james.wright | to Add: 1. Include the "Reporting Requirements Matrix" as found in Vol. 2, Section 1.1 (Project Instructions), Para 9.20 - Regularity of Reporting & Modes of Issue. 2. For daily reporting, "to be developed with Construction Reporting mechanisms"
2 | Stamp |  | david.huggins
3 | Arrow |  | Jeung.Kim
4 | Text Box |  | Jeung.Kim | Is this basis applied for procurement and construction phases?
5 | Arrow |  | Jeung.Kim
6 | Arrow |  | Jeung.Kim
7 | Arrow |  | Jeung.Kim
8 | Arrow |  | Jeung.Kim
9 | Text Box |  | Jeung.Kim | How about to make to differentiate?
10 | Callout |  | james.wright | PM
11 | Callout |  | james.wright | Include "Actual vs planned S-curves and resource histograms" as found in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 2.1, item d. Weekly Status Report, General
12 | Text Box |  | Daniella.Botta | Include 'per area and discipline (as a percentage and in a narrative form) 'as found in Section 1.1 Project Instructions, Exhibit 1. Para 2.2 Item b. Weekly Report Status, Engineering Activities
13 | Arrow |  | Daniella.Botta
14 | Callout |  | james.wright | Add "f. Quantities installed Table (Plan vs Actual)"
15 | Line |  | james.wright
16 | Callout |  | james.wright | "5th Calendar Day" as defined in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 3. Monthly Status Report
17 | Callout |  | Daniella.Botta | Include Cost Status as defined in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 3. Monthly Status Report
18 | Arrow |  | Daniella.Botta
19 | Text Box |  | Daniella.Botta | Include details described in Vol. 2, Section 1.1 (Project Instructions) Para 7.11 Project Milestones Status Report
20 | Arrow |  | Daniella.Botta
21 | Text Box |  | Daniella.Botta | Include item d as found in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 3. Monthly Status Report, Engineering
22 | Arrow |  | Daniella.Botta
23 | Text Box |  | Daniella.Botta | Include CTN register
24 | Text Box |  | james.wright | a. Indexed Progress Photographs