## 000-E-GRD-70007-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 6 | Yousif Ahmadi | Add: "NDE procedures" to Fabrication procedures
2 | Callout | 4 | Adnan Alothman | As per the Contract, Annex1-Technical documents do not have any order of precedence. Please correct this to align with EPC Contract.
3 | Text Box | 21 | Yousif Ahmadi | Below to be considered basis lessons learned from BAPCO 77E7707 incident and fabrication of new banks: APPLICATION OF CHEVRON SPECIFICATIONS & STRINGENT QA/QC REQUIREMENTS. The requirement of following Chevron Specifications considered in procuring of new tube bundles. ØCPM-SU-5013-D, Rev. D: Alloy 825 for Heat Exchangers and Piping in Hydro-processing Reactor Effluent Service ØEXH-SU-1826, Rev. L: Air Cooled Heat Exchangers ØQAM-SU-6053, Rev.1:Quality Assurance Requirements for Equipment and Material Manufacturers ØAdd: Comply section 12 of API 661 (applicable when design pressure exceeds 2000 PSIg) Following stringent QA/QC requirements considered in procuring of new tube bundles. ØASME U Stamp and stage wise third party inspection Ø100% UT (Shear Wave or Phased Array) for all Corner Plate Weld Joints, Stiffener / Partition Plate Weld Joints and Inlet/Outlet nozzles including Drain and Vents weld joints including Butt Welds. Ø100% Radiography Ø100% PMI of all pressure part materials ØEN10204, 3.2 Certification UT Examination: ØUT examination as per Chevron recommendation for Incoloy 825 (coarse grain) materials for REAC, calls for prior demonstration of UT examination on the demonstration blocks with artificial defects fabricated with Incoloy 825 material with all the dimensions, tubesheet/plugsheet drilling, and having all weld configurations (corner welds, stiffener/partition plate welds, nozzle welds etc.) similar to the production header. Please refer below Chevron Requirements on UT examination, A qualification process with welded samples and simulated flaws is required to perform UT inspections on coarse grain materials (e.g. Incoloy 825). The ultrasonic method shall be qualified to ASME art. 4, T-50(d), mandatory appendix VII, VIII and IX as applicable. A demonstration blocks drawing shall be prepared by the REAC vendor and shall be submitted to owner/Chevron for approval. ØAll UT Technicians performing UT inspections on Incoloy material must have prior demonstrated experience on the inspection of Incoloy welds and materials. ØThe UT technicians must pass the Chevron Performance Qualification Demonstration Examination using the above demonstration blocks. ØA specific procedure or technique sheet must be prepared for each weld or material configuration where all essential variables, including scan plans, technique and specific acceptance criteria are included. This document must be reviewed and approved by the company UT Level III inspector. RT examination: ØVendor shall prepare RT techniques sheets for each weld (especially for corner welds) and get Level-III approval prior to carry out RT on production welds. This is required to verify the required sensitivity and density are achieved to avoid re-shoot of welding.
4 | Cloud+ | 5 | Ahmed Marhoon | Client preference is electropneumatic smart positioners with full diagnostics.
5 | Call-out | 7 | Ahmed Marhoon | Client preference is electropneumatic smart positioners with full diagnostics.
6 | Call-out | 6 | 986131 | Fan performance characteristic curves showing the operating point and shaft power Consumption; including fan critical speeds for use with variable-frequency drives. Louver characteristic performance curve.
7 | Callout | 13 | Yousif Ahmadi | For level 2 inspection this to be changed to 3.2
8 | Text Box | 1 | Adnan Alothman | General: - Equipment numbering need to be corrected. - TR to check whether Diesel Air Cooler (010E0023) is part of this MR and modify documents accordingly
9 | Callout | 2 | Mohamed Ayyash | INDEX PAGE 2/21 ITEM 2: Typo, should read "OBJECTIVE" and not OBJECT.
10 | Callout | 3 | Mohamed Ayyash | INDEX page 3/21 item 10.1 should read "Commissioning and Start-up" and not vise versa.
11 | Call-out | 8 | Ahmed Marhoon | Instruct the suppliers to source equipment (including instrumentations) only from project AVL.
12 | Callout | 20 | Mohamed Ayyash | Page 20/21 item 10.1 "Commissioning" to the sentence.
13 | Callout | 20 | Mohamed Ayyash | Page 20/21 item 10.1 should read "Commissioning and Start-up" and not vise versa.
14 | Callout | 4 | Mohamed Ayyash | PAGE 4/21 ITEM 2: Typo, should read "OBJECTIVE" and not OBJECT.
15 | Callout | 6 | Mohamed Ayyash | Page 6/21 under inclusions item 3.1 should read "Commissioning and Start-up" and not vise versa.
16 | Callout | 7 | Mohamed Ayyash | Page 7/21 item 3.1 under supply should read "Commissioning and Start-up" and not vise versa.
17 | Callout | 19 | Yousif Ahmadi | Paragraph starts with Site run test: Delete repeated words "to be"
18 | Text Box | 14 | Mahdi Ali | Remove D from the unit number
19 | Text Box | 14 | Mahdi Ali | Remove D from the unit number
20 | Call-out | 5 | Ahmed Marhoon | Scope of DCS has not been described in this document. Contractor to adequately include the design requirements of the control system. Details of the type of signals to be included according to the PID and BMPS-J1/J2/J6 specifications. Also applicable to ESD in case introduced based on Hazop/SIL studies.
21 | Callout | 6 | Yousif Ahmadi | Site assistance : Typo error DAYLY
22 | Text Box | 3 | Ahmed Marhoon | The following are comments related to instrumentation and control. Contractor is requested to update the other documents issued as part of this transmittal, in addition to the Data Sheets, based on the comments stated herein and ensure consistency prior to release of MR to suppliers. 1. Instruct the suppliers to source instrumentations from project AVL only. 2. Add a note to the suppliers with reference to the applicable BMPS to design and supply the system according to the final PID. Functional design specifications covered in this MR shall be firmed based on the approved PID. Vendors to be clearly notified on the necessity to include all the Hazop3/SIL recommendations and changes made Post-EPC-Development. 3. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting &etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 4. Supplier to be instructed to generate all instrument data sheets, hook ups ...etc. in project specs (according to Bapco standard formats) and to be developed in SPI format. Typical formats can be provided to the supplier at a later stage for compliance. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 5. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval. 6. The actuators are preferred to be fitted with smart positioners as per BMPS-J2 Specifications and not I/P transducer. I/P converters may be considered, with client prior-approval, in case the smart positioners cannot be fitted. 7. Add reference to all applicable BMPS J series such as J2, J6, J3 ...etc for the supplier to comply with. All instruments and control systems to be designed according to BMPS specifications. 8. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included.