## 000-E-ITP-70001-001
ID Nº | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ |  | bapco-user | Change Technip Italy to TTSJV | Updated | Y
2 | Cloud+ |  | bapco-user | Typo; to be changed from 019E0072 to 079E0074 | Updated | Y
3 | Cloud+ |  | bapco-user | Exchangers no to be combined as 019E0006 A/B | Referenced items have been stated separately because both items are different (materials, etc) as per stated in MDS. | N
4 | Stamp |  | Raj |  |  | -
5 | Call-out |  | Yousif | Add Impact test | Updated | Y
6 | Call-out |  | Yousif | Add a stage for Tubes test / inspection | 000-E-ITP-70001-001 follows the Std. Form Nº BMPS-E-50204 INSPECTION CHECKLIST FOR SHELL AND TUBE HEAT EXCHANGERS, where tubes test / inspection are included in "N.D.E. on raw materials" within the "BEFORE FABRICATION" stage in page nº3. | N
7 | Text Box |  | Hasan Asad | Add: Hydrostatic test after installation (Activity during pre-commisioning). | 000-E-ITP-70001-001 states the corresponding Inspection and Test Plan for vendors, so that, no hydrostatic test after installation shall be shown in the referenced document. | Y