## 000-F-SOW-80002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  | Nalini Mohan
2 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
3 | Callout |  | Nalini Mohan | Include all relevant Datasheets, Specifications, Standard Drawings, approved Vendor List if combustion air blowers is requested as OPTION
4 | Callout |  | Mohamed Ayyash | align
5 | Arrow |  | Mohamed Ayyash
6 | Callout |  | BD Mori | Reaction Furnace/Burner CFD report
7 | Callout |  | BD Mori | Burner test report
8 | Callout |  | Nalini Mohan | Calculation Notes should be for review
9 | Callout |  | Nalini Mohan | Add pipe stress report
10 | Callout |  | Mohamed Ayyash | align
11 | Arrow |  | Mohamed Ayyash
12 | Call-out |  | Ahmed Marhoon | List of Hardware, Software and services along with the format of each shall comply with the BMPS-J series specifications such as BMPS-J2, J3, J6 ...etc.