## 000-K-MRQ-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Yousif Ahmadi | Remove M so it should read 000-K-ITP-70001-001 | Noted. Modification will be included document revision | Y
2 | Callout | 1 | Yousif Ahmadi | Remove M so it should read 000-K-IDL-70001-001 | Noted. Modification will be included document revision | Y
3 | Callout | 1 | Isamu | Please attach compressors data sheet and resubmit | Noted.
4 | Callout | 1 | Mohamed Ayyash | What is 000M? should be 7CDU/2HCU | Not applicable. This is a generic designation of the document assigned by TTSJV DCC and cannot be modified. | N
5 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets | Not aplicable. This is not a typo mistake | N
6 | Text Box | 3 | Hasan Asad | BMPS-S12 | BMPS-12 superseed by Project Procedures Instructions to Vendor for Filling-up of “Spare Parts List for 2 year Operation and Interchangeability Record” and "Instructions to Vendors for Filling-Up of Spare Parts Interchangeability Record (SPIR)" already included in MRQ | N
7 | Text Box | 5 | A.Jabbar Mahmood | Ensure that any applicable Licensors specifications are included | Applicable licensor specification included on this requisition have been standardized by Directorate in accordance. If any, missing specifications will be included in next document revision | N