## 000-K-SOW-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
2 | Callout | 1 | Mohamed Ayyash | What is 000M? should be 7CDU/2HCU
3 | Call-out | 2 | Raj | This list to include all Capital Spares required for the equipment as per the Contract Annex 1
4 | Call-out | 2 | Mahdi Ali | Motor equipment code is 'M' and not 'KM'
5 | Call-out | 2 | Raj | Change the motor tags as per the agreed equipment numbering
6 | Call-out | 3 | Sameer Foujdar | Supplier shall provide startup procedure along with logic sequence and pre startup requisites.
7 | Callout | 4 | Mohamed Ayyash | Typo
8 | Call-out | 5 | Ahmed Marhoon | Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to relevant BMPS J series specifications.
9 | Callout | 5 | Mohamed Ayyash | better to write full words
10 | Callout | 6 | Mohamed Ayyash | Should read Commissioning and Start-up ( not vise versa)
11 | Text Box | 6 | Hasan Asad | Including troubleshooting guideline for complete unit and associated systems.
12 | Text Box | 8 | A.Jabbar Mahmood | Ensure that all performance curves requested in the equipment datasheets are included.