## 000-S-MST-60001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 |  |  | Adel
2 |  |  | Antony.Bentley | Water Collection Basin - FEED Geotch. Report recommends pumping tests be undertaken for design of dewatering system; please include. AMB 25/03/2018
3 |  |  | Antony.Bentley
4 |  |  | Antony.Bentley | FEED Geotechnical Report indicates additional SI is required to verify basic design assumptions in the Sulphur Handling & Buried Bullets Area - advise why this is now not required? AMB 25/03/18
5 |  |  | Antony.Bentley | FEED Geotechnical Report indicates additional SI is necessary to confirm design assumptions for the Transfer Lines in the Wet Gap; please confirm that this information is available/ why not now necessary AMB 25/03/2018