## 000-S-SOW-80003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Julio.Aguilar | Package tag number to be included.
2 | Text Box | 1 | Mahdi Ali | add title in the header
3 | Text Box | 2 | Mahdi Ali | Correct EPC equipment tags to be used.
| Cloud | 2 | Mahdi Ali
4 | Text Box | 3 | Hasan Asad | Add: Belt Splicing and Vulcanizing kit and machine - (optional)
5 | Callout | 4 | Julio.Aguilar | Confirm if the "Dust Suppression Study" mentioned in the SOW for WP3 will be part of the Scope of Supply documents to be provided in this MR
6 | Call-out | 6 | Ebrahim | and asset
7 | Callout | 6 | Nalini Mohan | Provide Asset Information Sheets for all equipment
8 | Text Box | 7 | Nalini Mohan | Performance curves for all machineries shall be provided. - Line list and isometric sketches shall be provided. - It is recommended that the Contractor internally check the document supply conditions of the Instrument and electric departments