## 005-A-PFD-00001-004-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | BD Mori | Add stream composition and other properties details for all the streams for C3, C4 and mixture of C3+C4 as per standard PFD H& M balance formate
2 | Callout | 1 | Abdul Rahim | C3 and C4 volumes from SGP to be confirmed
3 | Callout | 1 | Salman Jaffer | The ratio of C3 and C4 to existing Horton spheres via blending facilities, is preliminary prepared during FEED and shall be further developed and finalized by EPC Contractor, taking into consideration the design conditions of existing Horton spheres. For more detail please refer to Bid Query T1937.
4 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. PFD shall be modified to incorporate the updated streams data and H&M balance.