## 010-A-PFD-00001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Refer to the first sheet for the General Comments.
2 | Text Box | 1 | Ahmed Ali | C0002
3 | Text Box | 1 | Ahmed Ali | C0003
4 | Callout | 1 | Mohamed Ayyash | No need fot this line change. can go straight to the left all the way
5 | Text Box | 1 | Ahmed Ali | V0008
6 | Call-out | 1 | Sameer Foujdar | correct the typo error 7VDU instead of 7VOU
7 | Text Box | 1 | Ahmed Ali | also add "while 7CDU in Operation"
8 | Call-out | 1 | Ahmed Ali | E0019
9 | Text Box | 1 | Ahmed Ali | change the note to: 4- Atm. Residue to Vacuum Residue jump-over to be used during 7VDU shutdown while 7CDU in operation.
10 | Call-out | 1 | Ali Abbas | Arrow and SP location to be corrected
11 | Call-out | 1 | Ali Abbas | Firing Control or BMS with flame eyes and sequence purge etc. control to be developed with heater vendor?
12 | Text Box | 1 | alexis.martinez | GENERAL: Equipment TAG number shall be modified based on the list and PFDs Mark-up sent to Contractor.
13 | Text Box | 1 | alexis.martinez | GENERAL: All the utility stream and the correspondent Heat and Material Balance stream number shall be shown on a separate Utility Flow Diagram (UFD).
14 | Call-out | 1 | 986131 | Avoid the line bends by readjusting the equipments in the layout.
15 | Call-out | 1 | 986131 | Add: FUEL GAS and remove the line break symbol " 4 "
16 | Call-out | 1 | 986131 | Show stripping steam line with "NNF" and add note 7 on the line.
17 | Call-out | 1 | 986131 | Add stream data
18 | Call-out | 1 | 986131 | Place the equipment numbers directly above the equipments
19 | Callout | 1 | alexis.martinez | Add slash symbol i.e. Crude/Kero
20 | Callout | 1 | alexis.martinez | Delete the word "Heavy". Only one type of Kerosene is produce
21 | Callout | 1 | alexis.martinez | Correct: use "FLASHED CRUDE" instead of "FLASH CRUDE" in the heater inlet stream.
22 | Callout | 1 | alexis.martinez | Add slash symbol i.e. Crude/Kero
23 | Text Box | 1 | alexis.martinez | GENERAL COMMENT APPLICABLE TO ALL PFD'S: - As required in BMPS A8, 7.2.7 item 4 add the note stating: The data on equipment data blocks indicate the normal operating case for the unit and may not be the design case. - All tag numbers shown close to or inside the equipment to have the full equipment number including the unit number - this is based on the updated BMPS-A8 (issued on 09 April 2018)
24 | Text Box | 1 | alexis.martinez | GENERAL: locate the pumps data blocks aligned with the corresponding pump.
25 | Callout | 1 | alexis.martinez | The design temperature of Atmospheric Column does not match with FEED information. Review
26 | Callout | 1 | alexis.martinez | Add the location for design temperature of Atmospheric Column i.e. Top/ Bottom
27 | Callout | 1 | alexis.martinez | The design temperature of Diesel Stripper does not match with FEED information. Review
28 | Call-out | 1 | Ahmed Marhoon | Control scheme for the VDU bypass scenario to be carefully reviewed and designed. According to the FEED PID, level override signals are required. However, these signals have not been found on this PFD. Contractor to review the overall system and provide the necessary Hardware and Software systems (including sequence logic, blocks, flow chart ... etc) to allow the plant operator bypass the VDU safely and easily. This comment to be addressed in conjunction with the VDU PFD
29 | Call-out | 1 | Ahmed Marhoon | Add TV tag to signal description.
30 | Call-out | 1 | Ahmed Marhoon | Improve representation of the signal and equipment labels to avoid congestion.
31 | Call-out | 1 | A.Jabbar Mahmood | Slightly enlarge the heater drawing for better representation.