## 010-C-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
2 | Call-out | 1 | Tapas | Delete the word "Mechanical" from the name "MECHANICAL DATA SHEET"
3 | Call-out | 2 | Tapas | For clarity, express as - H2S: 5 ppmw maximum, NH3: 25 ppmw maximum, pH > 7
4 | Call-out | 2 | Tapas | ADD: Slop 3000 BPSD
5 | Call-out | 2 | Tapas | Refer to reference made to note 16 in row 15,16,25 & 26 of the data sheet - Contractor to confirm is additional data is required from Owner - If yes please request ASAP what is requried.
6 | Callout | 2 | Mohamed Ayyash | Service not written ?
7 | Callout | 2 | Mohamed Ayyash | 7CDU
8 | Call-out | 2 | Ahmed Ali | add "Phenolic"
9 | Call-out | 2 | Tapas | Based on existing refinery experience BFW conductivity observed is ≤ 30 microS/cm inside the units. Refinery specification ≤ 50 MicroS/cm for steam generators.
10 | Callout | 2 | alexis.martinez | There is an inconsistency with the FEED desalter design pressure. The increment of design pressure need to be justified.
11 | Call-out | 3 | Tapas | Correct typo.
12 | Call-out | 3 | Tapas | Add the expected pH and TDS to the effluent quality.
13 | Callout | 3 | alexis.martinez | In General Requirement, section b), add: "Static mixer (in case the desalter vendor consider necessary to include one)"
14 | Call-out | 3 | Tapas | ADD: Static mixture downstream of the mixing valve to be installed, if required.
15 | Cloud+ | 3 | Tapas | Rephrase as: make up water
16 | Text Box | 3 | Tapas | Refer to note 11 of FEED data sheet "Vendor to provide multiple indipendet high level alarms connected to electrode(s) shutdown for each Vessel" - This note is omitted in the current sheet. Contractor to explain why and if omitted inadvertently then the same needs to be added.
17 | Callout | 3 | alexis.martinez | Add in note 7, row 38: "(To be confirmed by desalter vendor)"
18 | Text Box | 3 | Mahdi Ali | Leave space
19 | Call-out | 3 | Tapas | Add: as a minimum Agar probe to be considered.
20 | Text Box | 3 | Tapas | Add note: Rag Layer detection and removal system shall be installed.
21 | Call-out | 3 | Tapas | Remove the brackets i.e. "(" and ")" . Similarly removed it row 5 and 6 of the data sheet.
22 | Text Box | 3 | Tapas | Add note: AB crude feeding the unit may not have residence time in the tank. Therefore there may be situation where desalter could see slug of water. first stage desalter type should be capable of handling such scenarios and should not cause and upset to the unit.
23 | Callout | 4 | alexis.martinez | In addition to EDD desalter type add: The contractor will evaluated all the existing technologies and select the technology that guarantee the desalted crude requirements. One of the evaluated technologies will be EDD.
24 | Text Box | 4 | Ahmed Marhoon | - Note 8: Add a note to the supplier to advise the recommended type of level transmitters and requirement of stilling wells. Final design of the Desalters (including nozzles) shall be based on the final approved PID (i.e. post detail engineering and Hazop
25 | Call-out | 4 | Ahmed Marhoon | List of Documentation and Inspection have not been attached to this transmittal and hence not reviewed. Contractor to ensure both items are detailed according to the BMPS specifications.
26 | Text Box | 4 | Tapas | Based on the discussion with various vendors at the existing refinery it is understood that such low outlet salt content can be achieved only by EDD (electro dynamic desalter). Therefore add a note stating that :- The 2nd stage desalter in each train to be of EDD type.
27 | Text Box | 4 | Tapas | Add Note: Desalter should have frequency and power modulation units with DCS interface.
28 | Call-out | 4 | Ahmed Marhoon | Control Valves shall comply with BMPS-J8 specifications and the supplier to be notified accordingly. Tag numbers to be updated based on the final PID. Requirement of mechanical stop to be highlighted as per PID. The mechanical stop is preferred to be external on the stem. If required by Hazop, in addition to the mechanical stop, a soft clamp may also be provided on DCS for extra assurance. Set point to be finalized at a later stage.