## 010-C-GAD-10003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 3
2 | Call-out | 2 | MAK | 3
3 | Call-out | 3 | MAK | 3
4 | Call-out | 2 | MAK | 2
5 | Text Box | 1 | MAK | 3
6 | Call-out | 3 | MAK | 3
7 | Text Box | 1 | MAK | 010 - 7CDU
8 | Text Box | 2 | MAK | 010 - 7CDU
9 | Text Box | 3 | MAK | 010 - 7CDU
10 | Cloud+ | 1 | Adnan Alothman | Add negative "-" to the Ext. Design Pressure values.
11 | Call-out | 3 | 986131 | Check and correct the equipment number in this document.
12 | Call-out | 1 | 986131 | Ensure compliance with Bid Query T1153
13 | Call-out | 3 | 986131 | HHL and level transmitter tapping at same level. consider moving the tapping higher than HHL.
14 | Callout | 2 | alexis.martinez | In Page 2, Note 18, add the column pressure drop and the liquid static head used to calculate the design pressure at Bottom Tangent Line (B.T.L.)
15 | Call-out | 3 | alexis.martinez | In Page 3, the nozzles N7A and N8A shall be at the same elevation.
16 | Call-out | 3 | alexis.martinez | In Page 3, the nozzles N7B and N8B shall be at the same elevation.
17 | Call-out | 3 | alexis.martinez | In Page 3, to be consistent with column 010C0001, the Manway nozzles shall be numbered from bottom to top.
18 | Call-out | 1 | 986131 | item 1 & 3 to be distinguished as top head and bottom head. based on note 18 it appears that the selected design pressure is not adequate. please correct as nessary.
19 | Callout | 1 | alexis.martinez | On page 1, the design pressure is not matching with the design pressure shown on FEED datasheet. Review and correct.
20 | Callout | 2 | alexis.martinez | On page 2, delete the note 29.
21 | Call-out | 3 | 986131 | provide detail drawing with support arrangement.
22 | Call-out | 3 | 986131 | Provide details of the stripping steam inlet pipe.
23 | Call-out | 3 | alexis.martinez | Provided the details of nozzle N6 with the Vortex Breaker
24 | Call-out | 1 | 986131 | Repeat the Name plate on each page.
25 | Text Box | 1 | MAK | Use the latest A3 Border
26 | Text Box | 2 | MAK | Use the latest A3 Border
27 | Text Box | 3 | MAK | Use the latest A3 Border