## 010-F-DAT-00001-001-RAP
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
| Stamp | Raj
1 | Call-out | Hasan Al Noaimi | which type of steam eg 110# Steam | Updated as follow60# Steam superheating | Y
| Call-out | Hasan Al Noaimi
2 | Cloud+ | Yousif Ahmedi | Notes pages to be changed basis total number of sheets | Noted and updated | Y
3 | Callout | alexis.martinez | Check the value, because the maximum consumption is 50018 lb/h when the steam is used for Kerosene stripper. | Noted and updated | Y
4 | Callout | alexis.martinez | Check the value, based on H&MB the pressure is 60 psig. | Operating pressure will be defined later according detailed hydraulic design | N
| Arrow | alexis.martinez
5 | Callout | alexis.martinez | Check the value, based on H&MB the outlet pressure is 60 psig. | Operating pressure will be defined later according detailed hydraulic design | N
6 | Callout | alexis.martinez | Check the value, based on H&MB it is 42.2 lb/ft3. | Indicated Data on H&M balance corresponds to conditions upstream heater pass control valves. This comment doesn't apply for this data. | N
7 | Call-out | 986131 | Clearly indicate if the data provided is for fouled or clean. Provide both the data. | Data provided is at fouled conditions (refer to note 7) is the more restrictive case, VENDOR to provide pressure drop for clean/fouled conditions calculated. | Y
8 | Call-out | 986131 | Maximum allowable Inside film temperature to be specified (in line with API 560) For crude heater suggest considering maximum of 850°F. | Max allow/calc inside film temperature shall be defined by Vendor according their knowhow. Please note that no max allowable film temperature is specified for this heater – refer to heater DS. Only max average radiant flux limit shall be respected by heater. | N
9 | Call-out | 986131 | Mention the Feed Composition - crude blend | Crude blend referenced. | Y
10 | Call-out | 986131 | Indicate if the pressure provided is for clean of fouled condition | Inlet pressure is independent from fouling in heater tubes. Not applicable | N
11 | Call-out | 986131 | Indicate if the pressure provided is for clean of fouled condition | Oulet pressure is referred to fouled conditions. Note 7 referenced | Y
12 | Call-out | Hasan Al Noaimi | which type 110# steam | Updated as follow60# Steam superheating | Y
13 | Callout | alexis.martinez | Check the value, based on H&MB it is 401.9 MMBtu/h | Current data corresponds to updated H&M Balance for Alternative Design Case (100% Arabian Light) provided by TPIT. Final H&MB is pending to be received by Licensor. Once available final data will be reflected on D.S. . Note 59 has been added to reflect the clarification pending: 59) Data to be confirmed by Technolgy Provider (TPIT) according to final H& M balance for alternative design case (100% Arabian light). Refer to MOC-JVD-TCQ-000104, “CDU/VDU Process simulation. | Y
14 | Callout | alexis.martinez | Check the value, based on H&MB it is 2703124 lb/h. | Refer to answer 13 above | Y
15 | Callout | alexis.martinez | Check the value, based on H&MB it is 690 °F. | Refer to answer 13 above | Y
16 | Callout | alexis.martinez | Check the value, based on H&MB it is 1329058 lb/h. | Refer to answer 13 above | Y
17 | Callout | alexis.martinez | Check the value, based on H&MB it is 1374066 lb/h. | Refer to answer 13 above | Y
18 | Callout | alexis.martinez | Check the value, based on H&MB it is 155.1 °F. | Refer to answer 13 above | Y
19 | Callout | alexis.martinez | Check the value, based on H&MB the pressure is 60 psig. | Operating pressure will be defined later according detailed hydraulic design | N
| Arrow | 986131
20 | Call-out | 986131 | Clearly indicate if the data provided is for fouled or clean. Provide both the data. | Data provided is at fouled conditions (refer to note 7) is the more restrictive case, VENDOR to provide pressure drop for clean/fouled conditions calculated. | Y
21 | Call-out | 986131 | Maximum allowable Inside film temperature to be specified (in line with API 560) For crude heater suggest considering maximum of 850°F. | Max allow/calc inside film temperature shall be defined by Vendor according their knowhow. Please note that no max allowable film temperature is specified for this heater – refer to heater DS. Only max average radiant flux limit shall be respected by heater. | N
22 | Call-out | 986131 | Mention the Feed Composition - crude blend | 100% Arabian Light inlcuded, references pending refer to answer to comment 13 | Y
23 | Call-out | 986131 | Revalidate based on detailed hydraulics. | Detailed information will be provided in the context of Note 11 in next revision. | N
24 | Call-out | 986131 | For note 7 - Note that BMPS F1 - item 3.86 - JV to confirm if this requirement supersedes that requirement. Or based on the vendor provided information provided the final coke buildup would be decided. To be clarify in the data sheet. | As per BMPS-F1 para 3,86 data sheet requirement prevails. Final coke buildup shall be provided by VENDOR accordingly. | N
25 | Callout | alexis.martinez | Write in brackets the meaning of "BQ" | Noted and updated | Y
26 | Callout | alexis.martinez | Change to 0.0004, as per Fuel Gas System Process Design Basis document (FEED number 2520-u058-CN-0007-01_D) | Noted and updated | Y
27 | Call-out | 986131 | Refer note (20) - the ID and FD fan design should cater to special operation when 7VDU is shutdown and 7CDU is on turndown condition | Note 20 updated as follows: 20) One APH and one Steam APH common with 011F0001 to be provided with one ID fan for flue gas extration and two FD fan (each one for 100% combined CDU/VDU capacity). ID fans and FD fan shall be design also for the special operation case: 7VDU is shutdown with 7CDU operating in turndown case. (Refer to Note 55) | Y
27 | Cloud+ | Yousif Ahmedi | Change asset numbers in note 55 See numbering | Noted and updated | Y
29 | Callout | alexis.martinez | Include the document title. This apply for all reference. | Noted and updated | Y
30 | Call-out | 986131 | Specify the Case name for all pages pertaining to this case. | Noted and updated | Y
31 | Text Box | 986131 | Add the alternate case Heating curves | Refer to answer 13 above | Y
32 | Callout | alexis.martinez | Correct to 7CDU/7VDU | Noted and updated | Y
33 | Callout | alexis.martinez | Use BLOWER instead of FORCED FAN, as per equipment description on P&ID | Noted and updated | Y
34 | Callout | Yousif Ahmedi | 7CDU/7VDU | Noted and updated | Y
| Arrow | Yousif Ahmedi
35 | Callout | alexis.martinez | Write the complete words instead of the initials F.D. | Noted and updated | Y
36 | Callout | alexis.martinez | Add "0". The unit is 010. | Noted and updated | Y
37 | Call-out | 986131 | The Fans to be designed to operate when 7VDU is shutdown and 7CDU is in turndown condition. | Note 15 included as follows: '(15) Fans shall be designed for normal, design case and additional operating case (7VDU shutdown and 7CDU at turndown case) | Y
38 | Callout | alexis.martinez | Correct to 7CDU/7VDU | Noted and updated | Y
39 | Callout | alexis.martinez | Add "0". The unit is 010. | Noted and updated | Y
40 | Callout | Yousif Ahmedi | 7CDU/7VDU | Noted and updated | Y
| Arrow | Yousif Ahmedi
41 | Call-out | 986131 | The Fans to be designed to operate when 7VDU is shutdown and 7CDU is in turndown condition. | Note 14 included as follows: '(15) Fans shall be designed for normal, design case and additional operating case (7VDU shutdown and 7CDU at turndown case) | Y
42 | Callout | alexis.martinez | Correct to 7CDU/7VDU | Noted and updated | Y
43 | Callout | alexis.martinez | Correct to 010E0036. To be confirmed based on the final equipment TAG number list. | Noted and updated | Y
44 | Callout | Yousif Ahmedi | 7CDU/7VDU | Noted and updated | Y
| Arrow | Yousif Ahmedi
45 | Cloud+ | Yousif Ahmedi | Heaters 010F0001 and 011F0001 | Noted and updated | Y
46 | Callout | alexis.martinez | Correct to 7CDU/7VDU | Noted and updated | Y
47 | Callout | alexis.martinez | Correct to 010E0037. To be confirmed based on the final equipment TAG number list. | Noted and updated | Y
48 | Callout | alexis.martinez | Add "/" | Noted and updated | Y
49 | Callout | Yousif Ahmedi | 7CDU/7VDU | Noted and updated | Y