## 011-H-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Mohamed Ayyash | No. (Typo) apply to all sheets
2 | Cloud+ | 2 | bapco-user | 011E0003 A-F or only A-C To be confirmed
3 | Cloud+ | 2 | 986131 | As per ITB P&ID six condensers - each ejector connected to two exchanger:one operating and one standby.
4 | Call-out | 2 | Raj | Add a para in this datasheet which existed on FEED datasheet 'Vendor to develop proposal on this base configuration; if deemed attractive in terms of CAPEX and/or Utilities consumption, Vendor may also propose alternative configurations such as - A hybrid arrangement with ejectors and liquid ring pumps; - a scheme with precondenser and use of chilling water'
5 | Callout | 3 | Mohamed Ayyash | psig (why put the g between brackets) ?
6 | Cloud+ | 3 | Adnan Alothman | MR code number is 000-H-MRQ-70001-001
7 | Callout | 3 | Adnan Alothman | As per FEED Data Sheet Abs Pressure is 41.7 inHg. To be verified and confirm
8 | Cloud+ | 3 | Adnan Alothman | Inlet and Min. Outlet pressures to be verified and check against FEED Data Sheet
9 | Call-out | 3 | 986131 | For ease please list all the note together.
10 | Call-out | 3 | 986131 | Mention (3) as "Note 3" consistent with the above.
11 | Callout | 3 | alexis.martinez | Estimated steam and water consumption values are not matching with the FEED estimated consumption.
12 | Call-out | 3 | 986131 | this to be updated based on Cooling tower vendor information and can be higher due to chemical addition
13 | Call-out | 3 | 986131 | inHg (a) as per BMPS A1. correct at other locations
14 | Callout | 3 | alexis.martinez | The minimum steam temperature does not match with FEED specification package. Review and confirm (Refer to BMPS-A1)
15 | Text Box | 5 | Mahdi Ali | include Unit number in the equipment tag
16 | Callout | 5 | Mohamed Ayyash | Add an arrow here
17 | Callout | 5 | Mohamed Ayyash | LINE IS TOO CLOSE TO THE CONDENSOR. CAN BE MOVED BACK A LITTLE TO LOOK BETTER
18 | Callout | 5 | Mohamed Ayyash | Re write (CW IN)
19 | Callout | 5 | Mohamed Ayyash | Re write (CW RETURN)
20 | Call-out | 5 | 986131 | A/B/C/D/E/F
21 | Call-out | 6 | 986131 | Correct to two
22 | Call-out | 6 | 986131 | Please submit the hydraulics of the down stream piping to verify this pressure.
23 | Callout | 6 | alexis.martinez | Shows the scenarios and the operating column overhead pressure for each one.
24 | Callout | 6 | alexis.martinez | Remove the note 8 which is shown as deleted and re-order the numbers on the rest of the notes
25 | Callout | 6 | alexis.martinez | The minimum steam pressure does not match with FEED specification package. Review and confirm (Refer to BMPS-A1)
26 | Callout | 6 | alexis.martinez | Equipment Numbers need to be updated as per the new numbering provided by owner.
27 | Call-out | 6 | Ahmed Marhoon | Scope of supply to be detailed to avoid misunderstandings. A comprehensive list/matrix to be developed and shared with the suppliers to create a firm list of inclusions/exclusions in their proposals. Also applicable to 019-H-DAT-00001-001-RAP.