## 019-A-MSD-00001-014-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | Move the equipment no. to the center (Typical)
2 | Cloud+ | 1 | A.Jabbar Mahmood | Locate the control valve in the correct place as per the P&IDs
3 | Cloud+ | 1 | A.Jabbar Mahmood | The two arrows need to be shown in the right place and direction.
4 | Cloud+ | 1 | A.Jabbar Mahmood | The desuperheaters shall be represented correctly and tagged as DXXXX as per the latest equipment list
5 | Cloud+ | 1 | A.Jabbar Mahmood | The title shall be renamed to "LP STEAM GENERATION SYSTEM" as there is MP steam generation within other parts of the unit.
6 | Callout | 1 | Yousif Ahmadi | This is same as 019D0001 which is repated in sheet 8. Check and confirm.
7 | Callout | 1 | Yousif Ahmadi | Demister to be SS316L