## 019-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | General: No need to show continuation arrow for utility lines (refer to BMPS A8)
2 | Call-out | 1 | A.Jabbar Mahmood | General: Avoid breaking signals with text as per BMPS A8
3 | Text Box | 1 | A.Jabbar Mahmood | General: All Equipment Numbers need to be updated as per the new numbering provided by owner.
4 | Text Box | 1 | A.Jabbar Mahmood | It is suggested that Notes are moved up to make space for the equipment data above
5 | Cloud+ | 1 | A.Jabbar Mahmood | General : Delete. This is covered by a note.
6 | Text Box | 1 | A.Jabbar Mahmood | General: As per our current practice in PFD drafting, the stream descriptors entering the sheet shall be "Left Justified" and the descriptors for stream leaving the sheet shall be right justified.
7 | Cloud+ | 1 | A.Jabbar Mahmood | Move TC location slightly up for better representation.
8 | Cloud+ | 1 | A.Jabbar Mahmood | Move to downstream of FV1049 i.e. for stream 1813
9 | Callout | 1 | Robert.Kawitzki | Show equipment numbers as per project standard - typical comment
10 | Callout | 1 | Robert.Kawitzki | Text height and width as per project standard - typical comment
11 | Cloud+ | 1 | A.Jabbar Mahmood | Refer to general comment
12 | Cloud+ | 1 | A.Jabbar Mahmood | General: Delete the Sheet no. below the connector arrow - the sheet no. shall be shown as part of the PFD drawing no shown inside the arrow e.g in this case the drawing no. shall be "019-A-PFD-0001-002"
13 | Text Box | 1 | Mahdi Ali | Refer to General comments made for Unit '010' in transmittal BMP-MOC-TRI-00033
14 | Callout | 1 | Mohamed Ayyash | General comment: All texts and arrows from top to bottom to be aligned from the left side for better representation.
15 | Callout | 1 | Mohamed Ayyash | General comment: All texts and arrows from top to bottom to be aligned from the right side for better representation.
16 | Callout | 1 | Mohamed Ayyash | Can be written on the 2nd line for better representation and make room for other equipment
17 | Text Box | 1 | A.Jabbar Mahmood | General: As much as possible, the equipment data blocks shall be arranged to be so that the equipment block is vertically above or below the respective equipment
18 | Cloud+ | 1 | A.Jabbar Mahmood | The desuperheater shall be shown as part of the UFD and need not be shown in the PFDs
19 | Text Box | 1 | A.Jabbar Mahmood | General: The design pressures of most of the HP vessels, including the reactors, have been increased significantly. TR will need to provide the explanation supported with the hydraulic calculations for the owner to verify this change. The operating pressures indicated in this PFDs are still the same as the FEED PFD. Also, CLG needs to be notified for the change in the HP vessels design pressures.
20 | Call-out | 1 | A.Jabbar Mahmood | Reduce the height by moving the notes to allow more space for the drawing and equipment data blocks
21 | Call-out | 1 | Ali Abbas | process variables to be connected to ASC per BMPS-J16
22 | Call-out | 1 | Ali Abbas | show signal arrow direction. General comment.
23 | Cloud+ | 1 | A.Jabbar Mahmood | Show a stream arrow to indicate the flow direction
24 | Call-out | 1 | A.Jabbar Mahmood | This comment needs to be carefully implemented by TR. Only those general comments provided by Owner PIMH team in the referenced transmittal and are applicable to 2HCU PFDs shall be implemented. Other General comments related to other disciplines are already covered in this transmittal.