## 019-C-GAD-10003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest A3 Border
2 | Text Box | 1 | MAK | 019 - 2HCU
3 | Call-out | 1 | MAK | 3
4 | Text Box | 1 | MAK | 4
5 | Call-out | 1 | Ahmed Marhoon | Add the typical HOLD note for the instrument nozzles. Type, size, number and location to be finalized post detail design development and Hazop3/SIL sessions.
6 | Text Box | 1 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified under section 7.6 of the BMPS-A3. This is a typical comment for all vessels/columns with level measurement (control and ESD).
7 | Text Box | 1 | Mahdi Ali | Add DRAWING
8 | Cloud+ | 1 | Yousif Ahmadi | Per FEED datasheet this is 8"
9 | Cloud+ | 1 | Yousif Ahmadi | Per FEED document this is SELF. Reinf.
10 | Callout | 1 | Yousif Ahmadi | Per FEED document design pressure is 2310 and temperature is 178. Check and confirm
11 | Text Box | 2 | MAK | Use the latest A3 Border
12 | Text Box | 2 | MAK | 019 - 2HCU
13 | Call-out | 2 | MAK | 3
14 | Call-out | 2 | MAK | 2
15 | Cloud+ | 3 | A.Jabbar Mahmood | The gap between the demister pad edge and the column wall is 200 mm as per the FEED D/S and hence the demister dia shall be 2494 mm instead. Check and confirm.
16 | Text Box | 3 | MAK | Use the latest A3 Border
17 | Text Box | 3 | MAK | 019 - 2HCU
18 | Call-out | 3 | MAK | 3
19 | Call-out | 3 | MAK | 3
20 | Cloud+ | 3 | Ahmed Marhoon | HLL elevation shall be within the level measurement span. Currently the upper level nozzle is located lower (+2920) than the HLL (+2970) which need to be corrected.
21 | Text Box | 3 | Mahdi Ali | Add equipment number in the drawing
22 | Cloud+ | 4 | A.Jabbar Mahmood | The MIN is applicable to for the distance between the pipe and the column wall. Correct the representation.
23 | Cloud+ | 4 | A.Jabbar Mahmood | Improve the representation of the distances between the lines inline with the drawing below this view e.g the downcomer width is shown here much narrower than in the drawing below.
24 | Text Box | 4 | MAK | Use the latest A3 Border
25 | Text Box | 4 | MAK | 019 - 2HCU
26 | Call-out | 4 | MAK | 3
27 | Call-out | 4 | MAK | 4
28 | Text Box | 4 | Mahdi Ali | Add equipment number in the drawing