## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Harshad.K.Patel | Please revise and re-submit PEP per comments shown on this document.
2 | Callout | A.Jabbar Mahmood | The design pressure of C0001R is 2575 psig per the FEED datasheet. Is the new value (2590 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit.TR to provide the calculations and obtain CLG's concurrence. | Waiting answer from Chevron to make them official, once receive them will be sent to you.
3 | Callout | A.Jabbar Mahmood | The inlet and outlet pressures of C0001R are 2462 and 2327 psig per the FEED datasheet. Are the new values (2467/2332 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit. TR to provide the calculations and obtain CLG's concurrence. | Waiting answer from Chevron to make them official, once receive them will be sent to you.
4 | Call-out | Ahmed Marhoon | Old Bapco logo to be replaced with the new logo. This is typical for all documents. | Agreed. This will be changed and updated in next emission. | Y
5 | Call-out | Ahmed Marhoon | According to the GAD, T39 - 41 are at different elevation than T42-44. If there is no technical reason for combining these two groups; split into two line items similar to the rest of Thermowell connections. | This omission will be corrected and updated for next emission of this document. | Y
6 | Stamp | Raj
7 | Callout | A.Jabbar Mahmood | This nozzle (N47) does not exist in the FEED drawings or Licensor drawings. The nozzle however is depicted in the EDP and FEED P&IDs. We believe that this is a graphical error in the P&IDs and this additional nozzle shall not exist . TR to seek confirmation from CLG and update the P&IDs. | This nozzle will be deleted and updated in next emission of the GAD, by other hand this it has been informed to Process to correct and update the P&ID. | Y
8 | Text Box | A.Jabbar Mahmood | The ID (overlay to overlay) of 5100mm shall be indicated in the drawing | Agreed. This will be included and updated in next emission. | Y
9 | Call-out | Ahmed Marhoon | Bapco logo to be added to the frame block. Typical for all documents. | Agreed. This will be changed and updated in next emission. | Y
10 | Call-out | Ahmed Marhoon | For the Thermowells points, add reference to the typical assembly drawing. Typical for all TW points on Reactors. | Thermowells points for this Reactor are very specials and specific, so the typical assembly drawing for TW points on Reactors does not apply. | Y
11 | Call-out | Ahmed Marhoon | Direction to North, is it applicable for this drawing? If applicable, is it shown at the right direction? Otherwise, delete from the drawing. Typical for similar drawing. | The direction to North is applicable for that drawing, and with it is indicated the way to see in the drawing the orientation of the nozzles once they are defined by Piping, in this case will be from upward to downward. This direction of North is relative and referential to the drawing, the true North and Plant North will be included once known. | Y