## 019-E-DAT-00001-001
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  | Raj |  |  | -
2 | Cloud+ |  | A.Jabbar Mahmood | The tubeside inlet pressure is 2595 psig in the FEED D/S i.e. 36 psi higher!. To be veridfied. | MOC Process:Tube side inlet pressure has been updated according to reaction loop updated pressure profile. CLG will be informed. | -
3 | Cloud |  | Hasan Asad |  |  | -
4 | Text Box |  | Hasan Asad | DEU / Modified DEU | Since the maximum differential pressure between sides is 430 psi (<650), "Modified DEU" TEMA Type will be followed according to Licensor doc. EXH-SU-4764-A.1, annex E. | Y
5 | Arrow |  | Hasan Asad |  |  | -
6 | Cloud+ |  | A.Jabbar Mahmood | The tubeside nozzles are 10" per FEED D/S and P&IDs. To be verified. | MOC HeatTransfer: Nozzles size had been updated in order to decrease the ρV2 value. | -
7 | Text Box |  | Hasan Asad |  |  | -
8 | Arrow |  | Hasan Asad |  |  | -
9 | Text Box |  | Hasan Asad | YES | Updated | Y
10 | Arrow |  | Hasan Asad |  |  | -
11 | Text Box |  | Hasan Asad | YES | Updated | Y
12 | Cloud+ |  | A.Jabbar Mahmood | The H2S conc. shall on weight basis i.e as ppm wt | MOC Process: 'wt' will be added to the reported values. | To be added
13 | Cloud+ |  | A.Jabbar Mahmood | Tube max H2 PP in the tubeside is 2447 psia as per Licensor MSD. Verify | MOC Process: Maximum H2 PP updated considering the updated inlet operating pressure. | -
14 | Text Box |  | A.Jabbar Mahmood | Consider adding note 11 of the licensors datasheet for information | Updated by D/S Note (31) "11. TUBE SUPPORT PLATES ARE CROPPED ON TOP AND BOTTOM FOR DRAINAGE PURPOSES ONLY." | Y