## 019-E-DAT-00007-001
ID Nº | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp | Raj |  |  | -
2 | Cloud+ | A.Jabbar Mahmood | The shellside nozzles are 16" (inlet) and 16" (outlet) per FEED D/S and P&IDs. Verify | Nozzles size had been updated in order to decrease the ρV2 value. | -
3 | Cloud+ | A.Jabbar Mahmood | Note 15: Specify design case - SOR or EOR | MOC Process: Note 15 is referring the heat exchanger design case, which, as per note 2, is 'Design Case SOR.' | -
4 | Callout | A.Jabbar Mahmood | Also report the tubeside composition | MOC Process: Composition is reported for the cases when condensation takes place. In tube side no condensation is expected. | N
5 | Cloud+ | A.Jabbar Mahmood | Note 27: The max shell/tube differential pressure is 430 psig per CLG D/S and as also reported in 000-E-GRD-70001-001 (section 5.6.11) | MOC Process: Maximum shell/tubes differential pressure has been increased from the value specified by CLG considering the updated design pressure for shell side (2406 psig) and tube side (2970 psig). CLG will be informed. | -
6 | Text Box | A.Jabbar Mahmood | Detail B1 in CLG´s D/S is not shown here. Check and confirm | N/A since the baffle layout had been updated to one more baffle. | N