## 019-E-DAT-00008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | A.Jabbar Mahmood | 2223 psig as per FEED D/S and PFD. TR to provide the basis for this change and update other documents.
2 | Call-out | 4 | Ahmed Marhoon | Contractor to add reference to the applicable BMPS specifications such as BMPS-P20/P21 and relevant BMPS-J specifications. Typical for all air coolers with Variable Speed Drives.
3 | Cloud+ | 4 | A.Jabbar Mahmood | Correct the equipment number to 019E0007A/B as per the new numbering
4 | Text Box | 4 | Mahdi Ali | Do not use FEED numbers
5 | Call-out | 2 | A.Jabbar Mahmood | Font is too small
6 | Callout | 1 | Mohamed Ayyash | General Comment: Fonts are too small throughout the data sheets and unreadable.
7 | Callout | 4 | Yousif Ahmadi | Note 10 of FEED data sheet to be added: "Two fans per bay shall be provided as minimum"
8 | Cloud+ | 1 | Mohamed Ayyash | On cover sheet correct unit number. Delete c, should read 019
9 | Call-out | 4 | Raj | Since the metallurgy of the aircoller has been changed to Incoloy 625 during Negotiations agreement, the fabrication spec for new metallurgy for the bundle to be specified
10 | Cloud+ | 4 | Yousif Ahmadi | Specify the grade of Plug
11 | Cloud+ | 4 | A.Jabbar Mahmood | The H2S and NH3 conc. numbers seem to be incorrect. Check and update
12 | Call-out | 4 | Ahmed Marhoon | The scope for instrumentation and control is not limited to the alarms in DCS. All the control functions will be done in the DCS with the necessary interconnections with the electrical MCC. The final design of the system shall be based on the BMPS specifications (including relevant J class) and the final PID post detail design and Hazop3/SIL analysis. Suppliers to be instructed accordingly. This is a typical comment for all fin fan air coolers.
13 | Callout | 1 | Mohamed Ayyash | Top of cover page: add Unit name 2HCU. Apply to all sheets.