## 019-H-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | This is not a mechanical data sheet! |  | Not applicable. This is a mechanical data shet.
2 | Text Box | 1 | A.Jabbar Mahmood | Use decimal points instead of commas as decimal separators to avoid confusions |  | Noted and corrected in next revision.
3 | Cloud+ | 2 | Adnan Alothman | MR code number is 000-H-MRQ-70001-001 |  | Noted and corrected in next revision.
4 | Callout | 2 | Adnan Alothman | FEED Data Sheet shows temperature of Vacuum side as 275 deg. F. To be verified |  | Agreed. It will be corrected to 275 ºF in the next revision.
5 | Cloud+ | 2 | Adnan Alothman | Inlet and Min. Outlet pressures to be verified and check against FEED Data Sheet |  | Not applicable. New values checked a confirmed by Process Dept. Reported values in feed data sheet corresponds to CW supply and return operating pressure at B2. Credit for this pressure lost has been considered.
6 | Cloud+ | 2 | A.Jabbar Mahmood | The estimated ejector inlet pressure during FEED was 1.8 inHg corresponding to a dryer inlet pressure of 2 inHg as specified by CLG. 1.97 inHg seems to be too tight leaving almost no margin for pressure drop across the dryer and pipes. TR to re-check |  | Not applicable. New values checked a confirmed by Process Dept. Value corresponds to the inlet pressure obtained in the hydraulic calculation developed by MOC.
7 | Cloud+ | 2 | A.Jabbar Mahmood | needs to be verified against the selected pump shut-off pressure |  | Noted. It will be done during technical evaluation stage.
8 | Text Box | 3 | Mahdi Ali | remove space between sequence number and suffix |  | Noted and corrected in next revision.
9 | Text Box | 3 | Mahdi Ali | 019C0012 |  | Noted and corrected in next revision.
10 | Text Box | 3 | Mahdi Ali | Include Unit number |  | Noted and corrected in next revision.
11 | Callout | 3 | Mohamed Ayyash | STREAM ARROW TO BE SHOWN LARGER AND DARK |  | It is not possible to modify the sketch. It will be updated when final confirguration is available after vendor awarding.
12 | Callout | 3 | Mohamed Ayyash | DISTANCE LINES ARROWS TO BE SHOWN SMALLER |  | It is not possible to modify the sketch. It will be updated when final confirguration is available after vendor awarding.
13 | Callout | 3 | Mohamed Ayyash | Add an arrow here |  | It is not possible to modify the sketch. It will be updated when final confirguration is available after vendor awarding.
14 | Call-out | 3 | Sameer Foujdar | As a general comment the new numbering system to be used for all the equipments shown in the drawing. |  | Noted.
15 | Call-out | 3 | A.Jabbar Mahmood | correct the equipment number to 019V0017 |  | Noted and corrected in next revision.
16 | Call-out | 3 | A.Jabbar Mahmood | correct the equipment no. to 019V0015 |  | Noted and corrected in next revision.
17 | Call-out | 3 | A.Jabbar Mahmood | 019P0015A/B |  | Noted and corrected in next revision.
18 | Call-out | 3 | A.Jabbar Mahmood | 019P0016A/B |  | Noted and corrected in next revision.
19 | Callout | 4 | Mohamed Ayyash | 019C0012 |  | Noted and corrected in next revision.
20 | Call-out | 4 | Sameer Foujdar | Vendor to provide Operating Guidelines. |  | Noted and implemented in next revision.
21 | Cloud+ | 4 | bapco-user | Destination of Spillback to be checked and confirmed |  | To be verified later by Process Dept. Information not relevant for vacuum package vendor.
22 | Call-out | 4 | Sameer Foujdar | As a general comment the new numbering system to be used for all the equipments in the table. |  | Noted.
23 | Call-out | 4 | Sameer Foujdar | As a general comment the new numbering system to be used for all the equipments shown in the table. |  | Noted.
24 | Call-out | 4 | A.Jabbar Mahmood | 1.9e+31 |  | Comment did not find in the PDF data sheet. Please, clarify,
25 | Call-out | 4 | A.Jabbar Mahmood | 1.9e+32 |  | Comment did not find in the PDF data sheet. Please, clarify,
26 | Cloud+ | 4 | A.Jabbar Mahmood | TR to verify the required elevation |  | To be verified later when information form vendors are available.
27 | Text Box | 5 | Sankara | Relevant Electrical Specifications shall be included if there area any electric motors / loads in the package |  | Not applicable. There is no motors in the package.
28 | Callout | 5 | Mohamed Ayyash | move to align in front |  | Noted and corrected in next revision.
29 | Callout | 5 | Adnan Alothman | Add " - " to be read -10 psig |  | Not applicable. As specified as external pressure (not internal), -10 psig is correct.
30 | Call-out | 5 | A.Jabbar Mahmood | Since the equipment can potentially be subjected to vacuum conditions, consideration shall be given for designing full vacuum (-14.7 psig). |  | Not applicable. Taking into account that this package is a vacuum package, design will cover mentioned condition.