## 019-K-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | A.Jabbar Mahmood | This datasheet shall also be reviewed and approved by the Licensor | Noted
2 | Text Box | 1 | Hasan Asad | As per Volume 2 Exhibit 6 - CDRL - Complete LCCA study shall provided and recommendations shall be considered during design. | It´s in CONTRACTOR deliverable. Vendor only supply the information to preapre the LCCA
3 | Callout | 1 | Mohamed Ayyash | Delete c | Noted, it will be removed and updated in following document revision
4 | Cloud+ | 1 | A.Jabbar Mahmood | This is a "Process" Data sheet not Mechnical! | This comment does not apply and will not be removed. It is a mechanical data sheet and it will be kept (this is not the process data sheet).
5 | Callout | 1 | Mohamed Ayyash | add 0 | Noted, it will be added and updated in following document revision
6 | Text Box | 1 | A.Jabbar Mahmood | Owner has not received the hydraulic calculations of the HP Circuit and hence cannot verify the revised compressor head and discharge design conditions. | Noted. To be submitted later by Process Department
7 | Callout | 2 | Mohamed Ayyash | No. (Typo) apply to all document | It will be standarized by Directorate
8 | Callout | 2 | Mohamed Ayyash | increase text font | Noted, it will be increased and updated in following document revision
9 | Callout | 2 | Mohamed Ayyash | add 0, apply to all document | Noted, it will be added and updated in following document revision
10 | Call-out | 5 | Sameer Foujdar | Rupture disc is not marked in FEED data sheet. Ensure the requirement of the same. | The requirement appiest and this is the reason why it is marked
11 | Text Box | 5 | Sankara | Synchronous Motor Not acceptable | Noted, it will be removed and updated in following document revision
12 | Call-out | 6 | Ahmed Marhoon | Instrumentation Data Sheets were not provided as part of the Transmittal and hence could not be reviewed. In any case, all documents shall be generated in the client's standard format. Also all pre-fabricated installations shall meet the BMPS specifications such as BMPS-J31. | Instrument data sheets are part of vendor's scope of supply and they will be developed and submitted during Engineering phase. They are not part of this mechanical data sheet part of MRQ. This note is part of data sheet template of API 618
13 | Callout | 6 | Mohamed Ayyash | write 58 on the 2nd line to ovoid overlaping with the line | Noted, it will updated in following document revision
14 | Call-out | 9 | Sameer Foujdar | To be confirmed by vendor cooling media water or oil. | Water cooled is the first option as per API and BMPS. Other options in case deviations or technical limitations will be evaluated during technical evalution phase.
15 | Callout | 9 | Yousif Ahmadi | <31 HRC note to be written against Piston Rods Hardness | Piston rod material and coating shall be as per API 618. The paragraph 6.10.4.1 of BMPS-K1 indicates "If specified" and it is not the case. So, this paragraph shall be updated accordingly as per API 618
16 | Callout | 9 | Yousif Ahmadi | add "as per BMPS-K1) point 6.10.4.1 to PISTON RODS(S): MATERIAL/YIELD, PSI | Piston rod material and coating shall be as per API 618. The paragraph 6.10.4.1 of BMPS-K1 indicates "If specified" and it is not the case. So, this paragraph shall be updated accordingly as per API 618
17 | Callout | 10 | Mohamed Ayyash | Delete line | This line cannot be removed. It means that arrangement I-1; I-3 do not apply. The applicable arrangement is I-2
18 | Text Box | 13 | Sankara | This is incorrect | This is the correct class.
19 | Call-out | 14 | Ahmed Ali | 48F per BMPS-A1 | Noted, it will updated in following document revision
20 | Callout | 20 | Mohamed Ayyash | Remove block | Noted, it will updated in following document revision
21 | Call-out | 21 | Ahmed Marhoon | All alarms and shutdown functions to be confirmed with/by the vendor and shall be reflected on final C&E diagram. | Noted, it will be carried out during Engineering phase
22 | Callout | 22 | Isamu | Delete. No room here | Noted, it will updated in following document revision
23 | Callout | 23 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001 | Noted, it will updated in following document revision
24 | Text Box | 23 | Mahdi Ali | Use Bapco number | The number shall be as per instruction of TTSJV as per project requirements.
25 | Cloud+ | 23 | A.Jabbar Mahmood | The operating pressure range to be confirmed based on the final hydrualic calculations on the H2 interconnecting network. | Operating pressure range indicated has been calculated considering the values of pressure reported in Battery Limit Interconnecting Table provided by FEED (2520-c019-NM-0051-01_B). These values of pressure shall be complied by 3&4 H2 Plant
26 | Cloud+ | 23 | A.Jabbar Mahmood | Correct the steam out pressure to 60 psig | According to BMPS A3 paragraph "7.1 Design Pressure", steam out conditions for piping and equipment (different than heat exchangers and vessels) are 50 psig (internal pressure) at 300°F. Therefore, this comment is not applicable
27 | Call-out | 23 | A.Jabbar Mahmood | The operating discharge pressure has been revised from that specified by CLG. CLG shall be informed. | Agreed. This modification is related to reaction loop hydraulic calculation. A technical Query will be sent to CLG in order to receive Licensor approval
28 | Call-out | 23 | Ahmed Marhoon | Smart positioner? | This comment does not apply. Hydrocom is not part of this package's scope of supply (step-less capacity control). Control capacity system is by steps
29 | Callout | 23 | Mohamed Ayyash | Align | Noted, it will updated in following document revision
30 | Call-out | 23 | A.Jabbar Mahmood | The compressor suction design pressure to be revised to 490 psig as per bidder query number T132 | Noted and agreed, it will be reviewed in following document revision
31 | Call-out | 23 | Ahmed Marhoon | manual or automatic? | Both as per BMPS-K1 and FEED data sheets
32 | Call-out | 23 | Ahmed Marhoon | Add the required configuration for the remote system. | Noted
33 | Call-out | 23 | Ahmed Marhoon | Scope of Supply to be confirmed by Contractor. | Noted
34 | Call-out | 24 | A.Jabbar Mahmood | Indicate the operating case on which the turndown value is based | Turndown case considers the possibility of compressor operation at 50% of the lower flowrate case reported in H&MB cases
35 | Callout | 24 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001 | Noted, it will updated in following document revision
36 | Callout | 24 | Mohamed Ayyash | Overlapping, continue on the next line | Noted, it will updated in following document revision
37 | Call-out | 24 | A.Jabbar Mahmood | As per BMPS A1, the CW supply pressure at unit B.L is 65 psig | Reported inlet pressure for CW considers pressure drops from BL
38 | Cloud+ | 24 | A.Jabbar Mahmood | Not consistent with the design pressure of 2902 psig reported in note 18. Check | Value idnicated in DS is correct: 2970 psig (current design pressure stated in Note 18)*.999 (H2mole %)=2967 psig <>2982 psia.
39 | Call-out | 24 | A.Jabbar Mahmood | What is the basis for the max CW flow? | CW consumption has been estimated considering the type of compressor
40 | Call-out | 24 | A.Jabbar Mahmood | As per BMPS A1, the minimum CW return pressure at unit B.L is 36 psig. | Reported outlet pressure for CW considers pressure drops from BL
41 | Callout | 24 | Mohamed Ayyash | Align | Noted, it will updated in following document revision
42 | Text Box | 25 | Hasan Asad | Drain KO Drum shall be provided with manual/automatic draining facility. | KO drum with final moisture separation is a separated equipment from pulsation dampener of reciprocating compressor package and shall be supplied by contractor in another separated requisition.
43 | Callout | 25 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001 | Noted, it will updated in following document revision
44 | Callout | 26 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001 | Noted, it will updated in following document revision
45 | Text Box | 26 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. All applicable BMPS-J series to be referenced (such as J2, J3, J18 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. Contractor to consider the pumps protection requirements and reflux rate per process design. 6. Supplier to be notified on consideration of the Auto-Start (linked to discharge pressure) and Permissive (linked to level and MOVs status) requirements per the PID. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. All the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. | 1. ALL BMPS are i12. ncluded in MRQ, JVD will check and include any additional specification as required. In this RFI there are not control systems. 2.-All applicable project specifications are listed in MRQ (Requisition for enquiry) for reciprocating compressor, also AVL. 3. Final P&ID will be submitted by Pump Vendor, including all its scope and approved by CONTRACTOR. CONTRACTOR will check that HAZOP actions shall be correctly implemented. All BMPS applicable are part of the Material Requisition and included in section named MRQ. 4.Data sheets are filled in completely aligned with reciprocating compressor MRQ taking into account international standards and applicable project specifciations. 5. Noted. 6. All requirements mentioned in BMPS A-3 reference section 8.5MCM will be included in MR and Mechanical Data Sheet. It will be checked during Technical Bid Evaluation stage 7. Noted.All applicable requirements related to MCM are already implemented in data sheet/MRQ. 8. It is under discussion with JV Directorate (instrumentation) Vendor will be informed with final decision to standardize which instruments require wireless. 9. Noted. It´s standard requirement. 10. Noted. Already included in VDDR. 11.CHAZOP is not applicable to this RFI. ( PLC or MMS is not VENDOR scope). Hazop is already included in the scope of supply of reciprocating compressor package (shown in MRQ) 12.-All requirements as per BMPs are already included in reciprocating compressor's scope of supply. 13.-All applicable project specifications and standards are already listed in MRQ 14.-All applicable project specifications related to instrumentation and standards are already listed in MRQ of reciprocating compressor. Also some of them are already mentioned in compressor data sheet. 15.-Noted, this is an standard procedure during Enginnering phase (technical vendor's offers evaluation)
46 | Call-out | 27 | Sameer Foujdar | 3 Motors required one for each compressor. | Noted, it will updated in following document revision
47 | Callout | 27 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001 | Noted, it will updated in following document revision
48 | Text Box | 27 | Sankara | Delete Ex-p | Noted. Modification will be included document revision. Nevertheless based on BMPS-P1 Ex-p will be offered as and option.
49 | Text Box | 27 | Mahdi Ali | Remove c from Unit number | Noted, it will updated in following document revision
50 | Callout | 27 | Mohamed Ayyash | Make space | Noted, it will updated in following document revision
51 | Callout | 27 | Mohamed Ayyash | Correct: This is make up Hydrogen Compressors data sheet | Noted, it will updated in following document revision
52 | Call-out | 27 | Ahmed Marhoon | Service for Unit description to be corrected. This DS is related to 2HCU compressors. | Noted, it will updated in following document revision
53 | Callout | 28 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001 | Noted, it will updated in following document revision
54 | Callout | 28 | Mohamed Ayyash | Correct: This is make up Hydrogen Compressors data sheet | Noted, it will updated in following document revision
Noted. Modification will be included document revision. Nevertheless based on BMPS-P1 Ex-p will be offered as and option.