## 019-S-DAT-00005-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 1 | A.Jabbar Mahmood | This cannot be called a "mechanical" datasheet. This appears to be a 'specification' sheet for the filter package. | Title is ok. This is a Mechanical Data Sheet. | N
2 | Text Box | Page 1 | Ahmed Marhoon | 1. The notes related to Instrumentation & Control provided on the last sheet are general in nature. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification (not yet issued) that will be sent out to suppliers. 2. For example, note 15 on page 3, briefly describe the scope of the package supplier for the instrumentation with no reference to the relevant BMPS-J class or PID and so on. 3. Also, vendors to be notified on the fact that the final design of the system shall include all the Hazop/SIL (where the vendor will be involved) recommendation and approved PID. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that will be part of the requisition, could not be verified and hence it is the contractor's responsibility to update the other documents impacted by any of the comments on this transmittal and vice versa. | 1. Contractor ensures consistency between data sheet and RFI and all requirements regarding Instrumentation & Control of the Project. 2. All mentioned Instrumentation & Control requirements are fully and properly covered in the RFI. 3. Hazop/Sil will be rquested in RFI/RFP if required. 4. Consistency are guaranteed by Contractor. RFI is already issued to Company | N
3 | Stamp | Page 1 | mark.langerhorst
4 | Cloud+ | Page 2 | A.Jabbar Mahmood | The design pressure may need to be revised based on the shutoff pressure of selected upstream pump. A note shall be added in this regards. | Pump 019P0001A/B shut-off pressure has been limited to 334 psig, with the following note 'Discharge system design pressure is 334 psig. Shut-off pressure (calculated as per BMPS-A3) shall not exceed this value including all tolerances. | N
5 | Cloud+ | Page 2 | A.Jabbar Mahmood | A note shall be added indicating that the mechanical design temp will be upgraded to 500F as the filters are classified as vessels. | Noted. To be updated in following revision. | Y
6 | Cloud+ | Page 2 | Yousif | What will be the joint Efficiency | Noted. Joint efficiency is 0.85. It will be included in next revision. | Y
7 | Call-out | Page 3 | Hasan Al Noaimi | bank | Noted. To be corrected in following revision. | Y
8 | Text Box | Page 3 | A.Jabbar Mahmood | Note 1 of the FEED datasheet shall be retained | Noted. To be updated in following revision. | Y
9 | Cloud+ | Page 3 | A.Jabbar Mahmood | The pressure as per the FEED D/S and PFD is 124 psig (inlet). Owner's understanding is that the outlet pressure if set by the Feed Surge drum pressure 70 psig and the inlet by the pressure drop across the filter. TR to check and confirm. | Reported inlet pressure takes into account operating pressure in 019V0002 plus line pressure drop plus static head plus filter max DP. Two values have been reported: - 141 psig, which corresponds to 019P0001 @ Qnormal - 113 psig, which corresponds to 019P0001 @ Qrated So comment will not be implemented. | N
10 | Callout | Page 3 | Mohamed Ayyash | be (spilling) | Noted. To be corrected in following revision. | Y
11 | Call-out | Page 3 | Ali Abbas | P&IDs, | Noted. To be requested in following revision. | Y
12 | Call-out | Page 3 | Ali Abbas | (including flow chart) | Noted. To be updated in following revision. | Y
13 | Call-out | Page 3 | Ahmed Marhoon | To avoid future misunderstandings and to be in line with PID; replace "PDT" with "PDIT" | Noted. To be updated in following revision. | Y
14 | Text Box | Page 3 | Hasan Asad | Maintenance strategy during T&I shall be provided together with spare part list and troubleshooting guideline. | Maintenance strategy will be requeted to vendor to be provided in the IOM (Installation,Operation and Maintenance Manual). This comment is not applicable to data sheet. | N