## 021-F-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Ali Kadhem | Please provide the basis for using ambient air temperature of 110F for stack design. For air coolers, BMPS A1 specifies 117F.
2 | Call-out | 3 | Rashed Almudahka | indicate the values as per UOP data sheet
3 | Call-out | 6 | Ahmed Bucheeri | Mention the basis of selecting SS304 anchors
4 | Call-out | 6 | Ali Kadhem | There is no "Note 37" in page 8 and 9. Please check/revise
5 | Call-out | 7 | Ahmed Bucheeri | Mention the basis of selecting SS304 anchors
6 | Call-out | 7 | Ali Kadhem | To be written as 1.6
7 | Call-out | 8 | Ali Hasan | ZI (position indication) shall be provided for the stack damper as per the P&ID. Revise Note 19: Provide position indication for the stack damper.
8 | Call-out | 8 | Mahdi Ali | Do not use FEED number. Use Bapco numbers
9 | Call-out | 8 | Ali Kadhem | Please add to note 5: "and based on SGPs design development during EPC"
10 | Call-out | 8 | Ali Kadhem | Add the below note: "The heater must be capable of smooth controlled operation over an operating range of 30 to 100% of design with all burners in service." This is required to operate the unit at the guaranteed turndown with uniform heat flux. This comment is consistent with CLG heater datasheets.
11 | Call-out | 8 | Ali Kadhem | Regarding the shop fabrication of coil, and as per the EDP Datasheet, add to note 9: "UOP Standard Specification 8-12"
12 | Call-out | 8 | Ali Kadhem | Regarding the instrumentation requirement, and as per the EDP Datasheet, add to note 9: "UOP Standard Specification 697"
13 | Call-out | 9 | Ali Kadhem | As per the EDP datasheet, add the data for the oher cases i.e. Design SOR and Operating EOR.
14 | Text Box | 9 | Ali Kadhem | As per the EDP datasheet note 3-29 and the FEED P&ID BRA-226850 Sh.37 note 3, please add the following note: "EPC contractor to install the fuel gas preparation system per UOP project specification 992381-965 if required by heater/burner vendor to meet the heater/burner guaranteed performance."
15 | Call-out | 9 | Mahdi Ali | Do not use FEED number. Use Bapco numbers
16 | Text Box | 9 | Ali Kadhem | As per the EDP datasheet note 3-13, please add the tables of the maximum calculated convection section flue gas temperatures, as information to the vendors.
17 | Call-out | 9 | Ali Kadhem | As per the EDP datasheet, add the following note: "Provide ASTM A 312 Gr. TP 310, open ended tail gas nozzle located inside the burner tile of the main gas burners. Burner vendor shall determine the nozzle size and number required to incinerate tail gases."
18 | Text Box | 10 | Ali Kadhem | Please refer to BMPS-A8 Section 4.5.1: do not indicate figures in european style (which uses commas for decimal points and periods for thousands separators), use UK/US style with periods for decimal places and commas for thousands separators. check and correct all figures.