## 041-A-PFD-00001-002-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | balagangadhar.k | 60# STEAM
2 | Callout | 1 | balagangadhar.k | Show Arrow, typical for all CV.
3 | Callout | 1 | balagangadhar.k | Secondary Lines
4 | Callout | 1 | balagangadhar.k | 44
5 | Text Box | 1 | balagangadhar.k | S
6 | Callout | 1 | balagangadhar.k | Move down the Line to avoid crossing or terminate to the right near exchanger
7 | Callout | 1 | balagangadhar.k | Show Air cooler symbol as per LEGEND, this line to be deleted
8 | Callout | 1 | balagangadhar.k | Move right to match with others
9 | Callout | 1 | balagangadhar.k | Secondary Line
10 | Text Box | 1 | balagangadhar.k | 60#
11 | Callout | 1 | balagangadhar.k | Rename to include converters & Sulphur Condensers
12 | Text Box | 1 | balagangadhar.k | 600#
13 | Callout | 1 | balagangadhar.k | Major line should not be break over minor
14 | Callout | 1 | balagangadhar.k | Phosphate Lines is to be connected to BFW lines, the representation shows phosphate lines are main (drafting correction)
15 | Callout | 1 | balagangadhar.k | This gap is not same as sheet 1
16 | Callout | 1 | balagangadhar.k | 44
17 | Callout | 1 | balagangadhar.k | Terminate these connections near exchanger
18 | Callout | 1 | BD Mori | replace "X" with "BU"
19 | Callout | 1 | BD Mori | To make consistent with BMP units, replace word "Phosphate" with "Scale Inhibitor"
20 | Callout | 1 | BD Mori | Provide reference to "Note 5"
21 | Callout | 1 | Julio.Aguilar | Temperature and pressure conditions to be indicated. Check this throughout the PFDs
22 | Call-out | 1 | MAK | Move/stretch the OPC to the right.
23 | Text Box | 1 | MAK | The equipment data shall be placed in alignment with the location of the equipment as possible. See the examples below.
24 | Text Box | 1 | MAK | Move
25 | Text Box | 1 | MAK | Refer to Sht. 001 for the General Comments.
26 | Text Box | 1 | MAK | Move
27 | Call-out | 1 | MAK | Move/stretch the OPC to the right.
28 | Callout | 1 | Salman Jaffer | HEATERS
29 | Text Box | 1 | Sang.Hwang | In psig, ID, ID hyphen, font size shall be corrected. It looks different from others.
30 | Callout | 1 | Syed Ahmed | General comment: arrange to keep all equipment numbers at the center like the feed drawings.
31 | Callout | 1 | Syed Ahmed | keep this valve black as per BMPS-A-50003 Normally close for PFD only.