## 047-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 2
2 | Callout | 1 | Saeed Taher | Add : Note 2
3 | Call-out | 1 | MAK | Delete
4 | Text Box | 1 | MAK | Don't publish coloured PDF, instead use Black/White or Monochrome setting.
5 | Text Box | 1 | Robert.Kawitzki | equipment numbering and text height and width as per BMPS-A8 typ comment
6 | Callout | 1 | Syed Ahmed | keep this valve black as NNF for PFD as per BMPS-A-50003 and add NC.
7 | Callout | 1 | Saeed Taher | Material to be confirmed
8 | Callout | 1 | Saeed Taher | Material to be specified
9 | Callout | 1 | Saeed Taher | Material to be specified
10 | Callout | 1 | Saeed Taher | Material to be specified
11 | Callout | 1 | Saeed Taher | Material to be specified US & DS valve
12 | Callout | 1 | Saeed Taher | Materila to be confirmed
13 | Callout | 1 | Syed Ahmed | NNF
14 | Callout | 1 | Salman Jaffer | NNF
15 | Callout | 1 | Salman Jaffer | NNF
16 | Text Box | 1 | Mahdi Ali | Scale: NTS Size: A1
17 | Callout | 1 | Salman Jaffer | Should be consistence with PFD. Show the destination.
18 | Text Box | 1 | balagangadhar.k | Update the process flow scheme as per latest PFD. All Equipment numbers to be updated as per latest equipment list.
19 | Text Box | 1 | MAK | Use the latest PFD border.