## 081-A-PFD-50001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Robert.Kawitzki | If box is not populated insert dash or NA - typical comment
2 | Text Box | 1 | Mahdi Ali | Refer to general comments made on 010-A-PFD-00001-001 in transmittal BMP-MOC-TRI-00033
3 | Call-out | 1 | Ali Hasan | Reference to Owner comments on LSDP Flare revamp design basis (CON-BMP-TRA-010012 -081-A-BOD-00001-001), the LSDP flare load shall be verified and updated considering 1&2 SGPs and 2&3 ARUs design development in EPC.
4 | Text Box | 1 | Syed Ahmed | please add additional note: At any time, only one of the SGP units (1SGP or 2SGP) and one of the ARU units (2ARU or 3ARU) can be lined up to LSDP Flare.
5 | Cloud+ | 1 | 986131 | The relief load summary document could not be found in ITB. In addition during Hazop 2 this was recoded as a missing document (refer 2520 p012 ML 212 -page 43/132). Contractor to critically review the loads and update the flows as required to avoid any last minute surprise.