## 085-A-EQL-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 3 | A.Jabbar Mahmood | MAIN
2 | Text Box | 3 | A.Jabbar Mahmood | SECONDARY
3 | Cloud+ | 3 | A.Jabbar Mahmood | The equipment names for BA0001/2 shall be changed as indicated for differentiation
4 | Text Box | 6 | A.Jabbar Mahmood | All equipment data forming part of the packages shall be updated based on vendor input
5 | Cloud+ | 6 | A.Jabbar Mahmood | The design pressure of the acid mixers shall be based on the shutoff pressures of the off-site make-up CW pumps
6 | Cloud+ | 6 | A.Jabbar Mahmood | The operating pressures are 80 psig per PFD
7 | Callout | 8 | Adnan Alothman | Change description of 085V0001A/B to "INSTRUMENT AIR FILTER - 2"
8 | Callout | 8 | Adnan Alothman | Change description of 085V0001A/B to "INSTRUMENT AIR FILTER - 1"
9 | Callout | 8 | Adnan Alothman | Change description of 085V0001A/B to "INSTRUMENT AIR FILTER - 1"
10 | Callout | 8 | Adnan Alothman | Change description of 085V0001A/B to "INSTRUMENT AIR FILTER - 2"
11 | Text Box | 1 | MAK | General Comment: Use the latest document template issued to TTSJV as part of the Homogenization Procedure. The cover page shall be orientated the same as the documents they apply to.
12 | Call-out | 8 | MAK | Change to 085OMG0001
13 | Call-out | 8 | MAK | Change to 085U0011
14 | Call-out | 8 | MAK | Change to CWT
15 | Call-out | 8 | MAK | Change to 085U0012
16 | Call-out | 1 | Raj | The Item Index has mainly been reviewed for the Equipment Numbering. Many design parameters cannot be checked as preceding engineering documents such as equipment datasheets, MSD etc has not been submitted/completed
17 | Text Box | 1 | Yousif Ahmadi | General comments for all Equipment index - Use the new template - Provide Technip Group Spec. 000 GOPS 2014. - Fill the missing cells with the available information. - For new equipment in Existing units use the numbers as were agreed with Bapco.