## 087-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Always show the border size A1
2 | Callout | 1 | Salman Jaffer | Enter the PFD number
3 | Cloud+ | 1 | Sameer.Ahmed | Equipment tag number to be updated as per BMPS A8
4 | Callout | 1 | Syed Ahmed | General comment : use BMPS-A-50003 process flow diagram to show both pressure and temperature.
5 | Call-out | 1 | Edgardo | Please indicate the document number of the connecting PFD
6 | Callout | 1 | Robert.Kawitzki | Show equipment numbers
7 | Callout | 1 | BD Mori | These stream numbers are not consistent with steam data provided in the tables. Check and correct.
8 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. TTSJV to advise when the first utilities balance will be submitted for review. PFD shall be modified to incorporate the updated utilities streams data and H&M balance.
9 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 003
10 | Text Box | 1 | Mahdi Ali | Unit 087 is an existing unit and JV shall officially request the native file to be sent for modifications. It is not acceptable to use the FEED PFDs as there might been some modifications to the existing PFDs. Modifications shall be clouded.
11 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.