## 094-S-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | add document title in the header
2 | Callout | 1 | BD Mori | General comment: Units of measurement shall be consistent with BMPS-A1
| Cloud | 1 | Mahdi Ali
3 | Cloud+ | 1 | Julio.Aguilar | To be revised if this apply here or remove
4 | Cloud+ | 1 | Julio.Aguilar | Tag number to be revised as per new numbering procedure. This apply for all equipment throughout all document.
5 | Text Box | 1 | Mahdi Ali | Correct EPC equipment tags to be used.
| Highlight | 3 | Mahdi Ali
6 | Text Box | 3 | Mahdi Ali | Correct EPC equipment tags to be used.
| Arrow | 3 | Mahdi Ali
| Arrow | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Arrow | 4 | Mahdi Ali
| Arrow | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Arrow | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
7 | Callout | 4 | balagangadhar.k | P&ID tag number for transfer tower 094T001, typical
| Highlight | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
| Arrow | 4 | Mahdi Ali
| Highlight | 4 | Mahdi Ali
8 | Text Box | 4 | Mahdi Ali | Correct EPC equipment tags to be used which is as per BMPS-A8
| Highlight | 5 | Mahdi Ali
| Highlight | 5 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
9 | Callout | 7 | Salman Jaffer | Attachment 4
| Highlight | 7 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
| Highlight | 7 | Mahdi Ali
10 | Text Box | 9 | Mahdi Ali | Correct EPC equipment tags to be used.
| Highlight | 9 | Mahdi Ali
| Text Box | 10 | Jeung.Kim
| Highlight | 16 | Mahdi Ali
11 | Text Box | 16 | Mahdi Ali | Correct EPC equipment tags to be used.
| Highlight | 17 | Mahdi Ali
| Highlight | 18 | Mahdi Ali
| Highlight | 19 | Mahdi Ali
| Ellipse | 19 | Mahdi Ali
12 | Text Box | 19 | Mahdi Ali | Correct EPC equipment tags to be used.
13 | Text Box | 19 | Mahdi Ali | resolve overlap
| Highlight | 20 | Mahdi Ali
14 | Text Box | 20 | Nalini Mohan | Contractor to confirm the storage time allowed in silos.
15 | Text Box | 20 | Nalini Mohan | The main material of silo is given as CS. Contractor to confirm if inside surface is coated or not.t
16 | Text Box | 21 | Mahdi Ali | resolve overlap
| Ellipse | 21 | Mahdi Ali
| Callout | 22 | balagangadhar.k | 2
| Rectangle | 23 | Ebrahim
| Arrow | 23 | Ahmed Bucheeri
| Arrow | 23 | Ebrahim
17 | Call-out | 23 | Ebrahim | Remove, Not in the approved vendor list.
| Rectangle | 23 | Ebrahim
| Arrow | 23 | Ebrahim
| Rectangle | 23 | Ebrahim
| Arrow | 23 | Ahmed Bucheeri
| Rectangle | 23 | Ahmed Bucheeri
18 | Text Box | 23 | Ahmed Bucheeri | Not included in the AVL
| Rectangle | 23 | Ahmed Bucheeri