## 341-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Sameer.Ahmed | "C3/C4" & "Refinery Tank Farm (New portion)" to be included in the Secondary header
2 | Callout | 1 | Julio.Aguilar | 3H2 plant to have a separated block with a dedicated connection from main header. Similar to 4H2 plant.
3 | Callout | 1 | Julio.Aguilar | Add P and T conditions
4 | Callout | 1 | Sameer.Ahmed | C3/C4 to be provided air from the secondary header as well
5 | Callout | 1 | Julio.Aguilar | Consistency of Note 3 with similar Note 5 on PFD Nro. 341-A-PFD-00001-004 to be revised and updated.
6 | Call-out | 1 | Hasan Al Noaimi | CWT
7 | Callout | 1 | Sameer.Ahmed | Does it include the "Refinery Tank Farm (new portion)? To be confirmed.
8 | Text Box | 1 | Julio.Aguilar | General comment: Remove unit prefix. e.g.; u, h, etc.
9 | Callout | 1 | Sameer.Ahmed | Nitrogen Plant to be shown as a separate block with a separate air connection from the main and secondary headers
10 | Call-out | 1 | Hasan Al Noaimi | Refinery South Flare RSF
11 | Callout | 1 | BD Mori | Revise the unit number to 083
12 | Callout | 1 | Sameer.Ahmed | Show plant number & name in the box as follow: 036-2BAGRU 037-3BAGRU 041-5SRU 042-6SRU 043-7SRU 044-3TGTU 045-4TGTU 046-5SWS 047-6SWS 048-2ARU 049-3ARU
13 | Call-out | 1 | Edgardo | The title of this document is not fully consistent with the content of the drawing, which is the IA distribution. Please revise the document title to be reflective of the content of the document
14 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. TTSJV to advise when the first utilities balance will be submitted for review. PFD shall be modified to incorporate the updated utilities streams data and H&M balance