## 356-S-DAT-80002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | Page 1 | BD Mori | This Long Lead Item (LLI) Material Requisition (MR) is being prepared by TTSJV based on the data available from FEED documents. As the detail engineering progresses, some of the information provided in this MR may change. TTSJV shall ensure that the changes arising from the detail engineering are fully incorporated in the MR before placing an order to the vendor.
2 | Callout | Page 1 | Mohamed Ayyash | No.
3 | Text Box | Page 1 | Nalini Mohan | Comments incorporated on this document are also applicable for other 2 Desal Plants
4 | Callout | Page 5 | Julio.Aguilar | Add space here
5 | Line | Page 8 | Julio.Aguilar
6 | Text Box | Page 8 | Julio.Aguilar | to consider
7 | Callout | Page 8 | Sameer.Ahmed | add "distillate"
8 | Typewritten Text | Page 10 | Julio.Aguilar
9 | Typewritten Text | Page 10 | Julio.Aguilar
10 | Cloud+ | Page 10 | Julio.Aguilar | Replace ppm by ppmw
11 | Cloud+ | Page 11 | Julio.Aguilar | Replace ppm by ppmw
12 | Callout | Page 11 | Sameer.Ahmed | add "distillate"
13 | Text Box | Page 16 | Julio.Aguilar | Add Note: (4) Feed to unit after Feed Strainer Package.
14 | Callout | Page 16 | Julio.Aguilar | Include (note 4)
15 | Callout | Page 17 | Saeed Taher | Trim material to be as per BMPS-L2
16 | Callout | Page 17 | Saeed Taher
17 | Cloud+ | Page 17 | Sameer.Ahmed | Drinking water