## 372-G-DAT-57001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Khalid | 372P3730 A/B/C
2 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets.
3 | Callout | 1 | Mohamed Ayyash | Add unit name BFWCD
4 | Cloud+ | 1 | Mohamed Ayyash | Typo, delete "u" from unit number, should read 372
5 | Call-out | 1 | Mahdi Ali | Incorrect sequence number
6 | Call-out | 1 | Mahdi Ali | Incorrect sequence number
7 | Text Box | 1 | A.Jabbar Mahmood | The pumps head and capacity are preliminary and will be finalized later during the detailed design when the FED requirement has been frozen. A note shall be added in this regard.
8 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate.
9 | Callout | 2 | Mohamed Ayyash | Should read 2/9. correct all pages
10 | Callout | 2 | alexis.martinez | GENERAL: For decimal separator use dot (.) instead of coma (,)
11 | Callout | 2 | alexis.martinez | Rated flow is not matching with FEED datasheet. Review and confirm.
12 | Callout | 2 | alexis.martinez | For process data in Row 19 to 24: Provide the detailed engineering work carried out to get the numbers.
13 | Callout | 2 | alexis.martinez | Completed the missing information for maximum, normal and minimum cases
14 | Callout | 2 | Yousif Ahmadi | Correct all: FED WATER PUMPS
15 | Cloud+ | 2 | A.Jabbar Mahmood | Ensure compliance with BMPS A1. Assumed pressure drop from/to unit B.L will need to be verified during detailed engineering
16 | Callout | 4 | Adnan Alothman | Mounting of Seal Support System on Baseplate to be checked against relative standard and confirm.
17 | Text Box | 7 | Sankara | HV motors in Zone 2 areas shall be Ex-d or Ex-e type only. Refer Query T107: Typical Comment
18 | Call-out | 7 | Sameer Foujdar | 372M0030 A/B/C each require an individual motor and hence the number of units required should read as 3.
19 | Callout | 7 | Yousif Ahmadi | CORRECT: FED WATER PUMPS
20 | Callout | 9 | Isamu | Delete. NPSHR test already specified as witness
21 | Call-out | 9 | Mahdi Ali | Use Bapco number. FEED number shall not be used.
22 | Call-out | 9 | A.Jabbar Mahmood | Minimum flow requirement shall be confirmed by the vendor. A note shall be added in this regard.
23 | Call-out | 9 | A.Jabbar Mahmood | Also add the basis for the having three pumps.