## Sheet1
Transmittal | Document Code | Doc. Client Code | Doc. Description | Rev. | Doc Date | Action | Recipient | Expected Date | Status/Transmittal | Response Date | Discipline
CON-BMP-EML-00112 | 076551C-000M-DL-4141-001 | 000-S-IDL-70009-001 | DEVIATION LIST FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-ITP-4141-001 | 000-S-ITP-70009-001 | INSPECTION AND TEST PLAN FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-MR-4141-001 | 000-S-MRQ-70009-001 | MATERIAL REQUISITION FOR DESALTER PACKAGER | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-SP-4141-001 | 000-S-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00112 | 076551C-000M-SR-4141-001 | 000-S-SOW-70009-001 | SCOPE OF SUPPLY FOR DESALTER PACKAGE | A | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00114 | 076551C-000R-DL-0511-001 | 000-C-IDL-60005-001 | DEVIATION LIST FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-000R-ITP-0511-001 | 000-C-ITP-60005-001 | INSPECTION AND TEST PLAN (ITP) FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-000R-MR-0511-001 | 000-C-MRQ-60005-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-000R-SP-0511-001 | 000-C-GRD-60005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-000R-SR-0511-001 | 000-C-SOW-60005-001 | SCOPE OF SUPPLY FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-001-001 | 018-C-GAD-00013-001 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-001-002 | 018-C-GAD-00013-002 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-001-003 | 018-C-GAD-00013-003 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-002-001 | 018-C-GAD-00011-001 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-002-002 | 018-C-GAD-00011-002 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-002-003 | 018-C-GAD-00011-003 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-004-001 | 018-C-GAD-00012-001 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-004-002 | 018-C-GAD-00012-002 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-004-003 | 018-C-GAD-00012-003 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-007-001 | 018-C-GAD-00014-001 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-007-002 | 018-C-GAD-00014-002 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00114 | 076551C-018-DW-0510-007-003 | 018-C-GAD-00014-003 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00115 | 076551C-000R-DL-0846-001 | 000-S-IDL-60002-001 | DEVIATION LIST FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-ITP-0846-001 | 000-S-ITP-60002-001 | INSPECTIONA AND TEST PLAN FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-MR-0846-001 | 000-S-MRQ-60002-001 | MATERIAL REQUISITION FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-SP-0846-001 | 000-S-GRD-60002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-000R-SR-0846-001 | 000-S-SOW-60002-001 | SCOPE OF SUPPLY FOR FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00115 | 076551C-021-SP-0841-001 | 021-S-DAT-00001-001 | DATA SHEET FOR 021U0001 FEED FILTERS | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-DL-0310-001 | 000-E-IDL-70006-001 | DEVIATION LIST FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-ITP-0310-001 | 000-E-ITP-70006-001 | INSPECTION AND TEST PLAN FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-MR-0310-001 | 000-E-MRQ-70006-001 | MATERIAL REQUISITION FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-SP-0310-001 | 000-E-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 076551C-000M-SR-0310-001 | 000-E-SOW-70006-001 | SCOPE OF SUPPLY FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 085-E-DAT-00001-001 | 085-E-DAT-00001-001 | MECHANICAL DATA SHEET BMP MAIN COOLING TOWER 085CWT0001 | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00122 | 085-E-DAT-00002-001 | 085-E-DAT-00002-001 | MECHANICAL DATA SHEET BMP SECONDARY COOLING TOWER 085CWT0002 | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00123 | 076551C-000R-DL-0570-001 | 000-C-IDL-60007-001 | DEVIATION LIST FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-ITP-0570-001 | 000-C-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-MR-0570-001 | 000-C-MRQ-60007-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-SP-0570-001 | 000-C-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-000R-SR-0570-001 | 000-C-SOW-60007-001 | SCOPE OF SUPPLY FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-001-001 | 018-C-GAD-00013-001 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-001-002 | 018-C-GAD-00013-002 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-001-003 | 018-C-GAD-00013-003 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-002-001 | 018-C-GAD-00011-001 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-002-002 | 018-C-GAD-00011-002 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-002-003 | 018-C-GAD-00011-003 | 018C0001 ATMOSPHERIC COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-004-001 | 018-C-GAD-00012-001 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-004-002 | 018-C-GAD-00012-002 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-004-003 | 018-C-GAD-00012-003 | 018C0003 VACUUM COLUMN COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-007-001 | 018-C-GAD-00014-001 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-007-002 | 018-C-GAD-00014-002 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00123 | 076551C-018-DW-0510-007-003 | 018-C-GAD-00014-003 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00124 | 019-S-DAT-00005-001 | 019-S-DAT-00005-001 | MECHANICAL DATA SHEET FEED FILTER 019U0001 | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00124 | 076551C-000M-DL-0846-001 | 000-S-IDL-70003-001 | DEVIATION LIST FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00124 | 076551C-000M-ITP-0846-001 | 000-S-ITP-70003-001 | INSPECTION AND TEST PLAN FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00124 | 076551C-000M-MR-0846-001 | 000-S-MRQ-70003-001 | MATERIAL REQUISITION FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00124 | 076551C-000M-SP-0846-001 | 000-S-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00124 | 076551C-000M-SR-0846-001 | 000-S-SOW-70003-001 | SCOPE OF SUPPLY FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-DL-0910-004 | 000-G-IDL-60001-001 | DEVIATION LIST FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-ITP-0910-004 | 000-G-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-MR-0910-004 | 000-G-MRQ-60001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-SP-0910-004 | 000-G-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-000R-SR-0910-004 | 000-G-SOW-60001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-0910-001 | 018-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN1 & TRAIN2 FEED PUMPS 018P1001A/B & 018P2001A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-0910-002 | 018-G-DAT-00003-001 | CENTRIFUGAL PUMPS DATA SHEET QUENCH OIL PUMPS 018P0001A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-0910-018 | 018-G-DAT-00004-001 | CENTRIFUGAL PUMPS DATA SHEET HP LEAN AMINE PUMPS 018P0019A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-1012-001 | 018-K-DAT-00003-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T1001A/018T2001A TRAIN 1 FEED PUMP TURBINE TRAIN 2 FEED PUMP TURBINE | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-018-SP-1012-002 | 018-K-DAT-00004-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T0001A QUECH OIL PUMP TURBINE | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00125 | 076551C-021-SP-0910-002 | 021-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET FOR FEED PUMPS 021P0001 A/B | A | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-DL-0960-001 | 000-G-IDL-60002-001 | DEVIATION LIST FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-ITP-0960-001 | 000-G-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-MR-0960-001 | 000-G-MRQ-60002-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-SP-0960-001 | 000-G-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-000R-SR-0960-001 | 000-G-SOW-60002-001 | SCOPE OF SUPPLY FOR EBULLATING PUMPS | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00126 | 076551C-018-SP-0960-001 | 018-G-DAT-00001-001 | 1ST 2ND REACTOR RECYCLE PUMPS PACKAGE | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-DL-1020-001 | 000-K-IDL-60001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-ITP-1020-001 | 000-K-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-MR-1020-001 | 000-K-MRQ-60001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-SP-1020-001 | 000-K-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-000R-SR-1020-001 | 000-K-SOW-60001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-018-SP-1020-001 | 018-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 018K1001/K1002/K00001/K2001/K2002 MAKE-UP HYDROGEN COMPRESSORS | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00128 | 076551C-023-SP-1020-001 | 023-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 023K0001A/B FEED GAS COMPRESSORS | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 010-K-DAT-00001-001 | 010-K-DAT-00001-001 | MECHANICAL DATA SHEET CDU OVERHEAD VAPOR COMPRESSOR 010K0001 A/B | A | 2018-05-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 019-K-DAT-00002-001 | 019-K-DAT-00002-001 | MECHANICAL DATA SHEET MAKE-UP HYDROGEN COMPRESSORS 19K0002 19K0003 19K0004 | A | 2018-05-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-DL-1020-001 | 000-K-IDL-70001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-ITP-1020-001 | 000-K-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-MR-1020-001 | 000-K-MRQ-70001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-SP-1020-001 | 000-K-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00132 | 076551C-000M-SR-1020-001 | 000-K-SOW-70001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00139 | 019-C-DAT-00004-001 | 019-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE COLD HIGH PRESSURE SEPARATOR 019V0004 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-DAT-00006-001 | 019-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECYCLE GAS KO DRUM 019V0006 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-DAT-00009-001 | 019-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAEG COLD HIGH PRESSURE SEPARATOR 019V0009 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-DAT-10003-001 | 019-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-00004-001 | 019-C-GAD-00004-001 | MECHANICAL DRAWING FOR 1ST STAGE COLD HIGH PRESSURE SEPARATOR DRRUM 019V0004 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-00006-001 | 019-C-GAD-00006-001 | MECHANICAL DRAWING FOR RECYCLE GAS K.O. DRUM 019V0006 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-00009-001 | 019-C-GAD-00009-001 | MECHANICAL DRAWING FOR 2ND STAGE COLD HIGH PRESSURE SEPARATOR DRUM 019V0009 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 019-C-GAD-10003-001 | 019-C-GAD-10003-001 | MECHANICAL DRAWING FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-DL-0811-002 | 000-C-IDL-70001-001 | DEVIATION LIST FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-ITP-0811-002 | 000-C-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-MR-0811-002 | 000-C-MRQ-70001-001 | MATERIAL REQUISITION FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-SP-0811-002 | 000-C-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00139 | 076551C-000M-SR-0811-002 | 000-C-SOW-70001-001 | SCOPE OF SUPPLY FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00140 | 076551C-000R-DL-0710-001 | 000-E-IDL-60007-001 | DEVIATION LIST FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-ITP-0710-001 | 000-E-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-MR-0710-001 | 000-E-MRQ-60007-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-SP-0710-001 | 000-E-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-000R-SR-0710-001 | 000-E-SOW-60007-001 | SCOPE OF SUPPLY FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-001 | 018-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E1005 TRAIN 1 - HP/MT FLASH GAS COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-002 | 018-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0006 - MP/MT VAPOR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-003 | 018-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0010 - ATM COLUMN REFLUX AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-007 | 018-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0007 - QUENCH OIL COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-008 | 018-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E2005 - TRAIN 2 - HP/MT FLASH GAS COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-018-SP-0710-011 | 018-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0030 - CIRCULATION OIL AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-021-SP-0710-001 | 021-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0010 HHPS VAPOR AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00140 | 076551C-021-SP-0710-002 | 021-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0011 HLPS VAPOR AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-DL-0710-002 | 000-E-IDL-60008-001 | DEVIATION LIST FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-ITP-0710-002 | 000-E-ITP-60008-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-MR-0710-002 | 000-E-MRQ-60008-001 | MATERIAL REQUISITION FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-SP-0710-002 | 000-E-GRD-60008-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-000R-SR-0710-002 | 000-E-SOW-60008-001 | SCOPE OF SUPPLY FOR AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-004 | 018-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0011 - ATM COLUMN OVHD PRODUCT AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-005 | 018-E-DAT-00009-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0015 - DIESEL PRODUCT AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-006 | 018-E-DAT-00008-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0012 A/B - SOUR GAS COMPRESSOR DISCHARGE COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-009 | 018-E-DAT-00010-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0019 - LVGO AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-010 | 018-E-DAT-00011-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0023 - MVGO AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-018-SP-0710-012 | 018-E-DAT-00012-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0035 -TEMPERED WATER COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-021-SP-0710-003 | 021-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0012 -STRIPPER OVERHEAD AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00141 | 076551C-021-SP-0710-004 | 021-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0016 -DIESEL PRODUCT COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-DL-0851-001 | 000-H-IDL-70001-001 | DEVIATION LIST FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-ITP-0851-001 | 000-H-ITP-70001-001 | INSPECTION AND TEST PLAN FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-MR-0851-001 | 000-H-MRQ-70001-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-SP-0851-001 | 000-H-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00153 | 076551C-000M-SR-0851-001 | 000-H-SOW-70001-001 | SCOPE OF SUPPLY FOR VACUUM UNIT PACKAGES | A | 2018-04-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 019-S-DAT-00005-001 | 019-S-DAT-00005-001 | MECHANICAL DATA SHEET FEED FILTER 019U0001 | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00155 | 076551C-000M-DL-0846-001 | 000-S-IDL-70003-001 | DEVIATION LIST FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-ITP-0846-001 | 000-S-ITP-70003-001 | INSPECTION AND TEST PLAN FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-MR-0846-001 | 000-S-MRQ-70003-001 | MATERIAL REQUISITION FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-SP-0846-001 | 000-S-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00155 | 076551C-000M-SR-0846-001 | 000-S-SOW-70003-001 | SCOPE OF SUPPLY FOR FEED FILTER | A | 2018-05-11 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00157 | 019-C-GAD-00003-001 | 019-C-GAD-00003-001 | GENERAL ARRANGEMENT 019V0003 1ST STAGE HOT HIGH PRESSURE SEPARATOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 019-C-GAD-00008-001 | 019-C-GAD-00008-001 | GENERAL ARRANGEMENT 019V0008 2ND STAGE HOT HIGH PRESSURE SEPARATOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 019-C-GAD-00010-001 | 019-C-GAD-00010-001 | GENERAL ARRANGEMENT 019V0010 HOT LOW PRESSURE SEPARATOR | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-DL-0411-002 | 000-C-IDL-70004-001 | DEVIATION LIST FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-ITP-0411-002 | 000-C-ITP-70004-001 | INSPECTION AND TEST PLAN FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-MR-0411-002 | 000-C-MRQ-70004-001 | MATERIAL REQUISITION FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-SP-0411-002 | 000-C-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00157 | 076551C-000M-SR-0411-002 | 000-C-SOW-70004-001 | SCOPE OF SUPPLY FOR SEPARATORS CR-MO | A | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | STABILIZER - ITEM 010C0004 EX 010C0005/010-C-GAD-10005-001 AS PER CLIENT COMMENTS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | NAPHTHA SPLITTER - ITEM 010C0005 EX 010C0005/010-C-GAD-10006-001 AS PER CLIENT COMMENTS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | KEROSENE STRIPPER - ITEM 019C0006 | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | NAPHTHA SPLITTER - ITEM 019C0010 | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-DL-0511-001 | 000-C-IDL-70008-001 | DEVIATION LIST FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-ITP-0511-001 | 000-C-ITP-70008-001 | INSPECTION AND TEST PLAN FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-MR-0511-001 | 000-C-MRQ-70008-001 | MATERIAL REQUISITION FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-SP-0511-001 | 000-C-GRD-70008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00159 | 076551C-000M-SR-0511-001 | 000-C-SOW-70008-001 | SCOPE OF SUPPLY FOR CS COLUMNS | A | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00162 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0007 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0009 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0010 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0044 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0047 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 019-E-DAT-00015-001 | 019-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0074 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-DL-0610-001 | 000-E-IDL-70001-001 | DEVIATION LIST FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-ITP-0610-001 | 000-E-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-MR-0610-001 | 000-E-MRQ-70001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-SP-0610-001 | 000-E-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00162 | 076551C-000M-SR-0610-001 | 000-E-SOW-70001-001 | SCOPE OF SUPPLY FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 019-E-DAT-00008-001 | 019-E-DAT-00008-001 | AIR COOLED HEX DATA SHEET FOR 1ST STAGE HHPS VAPOR 019E0008 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 019-E-DAT-00009-001 | 019-E-DAT-00009-001 | AIR COOLED HEX DATA SHEET FOR 2ND STAGE HHPS VAPOR AIR COOLER 019E0012 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 019-E-DAT-00010-001 | 019-E-DAT-00010-001 | AIR COOLED HEX DATA SHEET FOR HLPS VAPOR AIR COOLER 019E0013 | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-DL-0710-001 | 000-E-IDL-70007-001 | DEVIATION LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-ITP-0710-001 | 000-E-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-MR-0710-001 | 000-E-MRQ-70007-001 | MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-SP-0710-001 | 000-E-GRD-70007-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00165 | 076551C-000M-SR-0710-001 | 000-E-SOW-70007-001 | SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-DL-1011-001 | 000-K-IDL-60002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-ITP-1011-001 | 000-K-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-MR-1011-001 | 000-K-MRQ-60002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-SP-1011-001 | 000-K-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-000R-SR-1011-001 | 000-K-SOW-60002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-018-SP-1011-001 | 018-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 018K0002 A/B SOUR GAS COMPRESSORS | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-021-SP-1011-001 | 021-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 021K0001 RECYCLE GAS COMPRESSOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-021-SP-1012-001 | 021-K-DAT-00002-001 | DATA SHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 021T0001 RECYCLE GAS COMPRESSOR TURBINE | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-023-SP-1011-001 | 023-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 023K0002 A/B PURGE GAS COMPRESSORS | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00169 | 076551C-051-SP-1011-001 | 051-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 051K0001 A/B PROPANE COMPRESSORS | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 1
CON-BMP-EML-00170 | 010-C-DAT-10001-001 | 010-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ATMOSPHERIC COLUMN 010C0001 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-DAT-10002-001 | 010-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR KERO STRIPPER 010C0002 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-DAT-10003-001 | 010-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR DIESEL STRIPPER 010C0003 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-GAD-10001-001 | 010-C-GAD-10001-001 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-GAD-10002-001 | 010-C-GAD-10002-001 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 010-C-GAD-10003-001 | 010-C-GAD-10003-001 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-DAT-10001-001 | 011-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DEASIGN SPECIFICATION SHEET FOR VACUUM COLUMN 011C0001 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-DAT-10002-001 | 011-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DEASIGN SPECIFICATION SHEET FOR TAIL GAS ABSORBER 011C0002 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-GAD-10001-001 | 011-C-GAD-10001-001 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 011-C-GAD-10002-001 | 011-C-GAD-10002-001 | GENERAL ARRANGEMENT 011C0002 TAL GAS ABSORBER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10004-001 | 019-C-DAT-10004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT STRIPPER 019C0004 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10005-001 | 019-C-DAT-10005-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR PRODUCT FRACTIONATOR 019C0005 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10007-001 | 019-C-DAT-10007-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR LIGHT DIESEL STRIPPER 019C0007 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10008-001 | 019-C-DAT-10008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HEAVY DIESEL STRIPPER 019C0008 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-DAT-10009-001 | 019-C-DAT-10009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER 019C0009 | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10004-001 | 019-C-GAD-10004-001 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10005-001 | 019-C-GAD-10005-001 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10007-001 | 019-C-GAD-10007-001 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10008-001 | 019-C-GAD-10008-001 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 019-C-GAD-10009-001 | 019-C-GAD-10009-001 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-DL-0511-002 | 000-C-IDL-70009-001 | DEVIATION LIST FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-ITP-0511-002 | 000-C-ITP-70009-001 | INSPECTION AND TEST PLAN (ITP) FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-MR-0511-002 | 000-C-MRQ-70009-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-SP-0511-002 | 000-C-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-EML-00170 | 076551C-000M-SR-0511-002 | 000-C-SOW-70009-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS (LLI) | A | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 2
CON-BMP-TRA-000001 | 076551C-000D-PP-101 | 000-A-PRO-50001-001 | PROJECT EXECUTION PLAN | A | 2018-03-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000001 CS REPLIED ON 16/04/18 | 2018-03-28 | CLASS 1
CON-BMP-TRA-000001 | 076551C-000D-PP-102 | 000-A-PRO-50002-001 | COORDINATION PROCEDURE BETWEEN THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV | A | 2018-03-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 2-REVIEWED WITH COMMENTS BMP-BOC-TRE-000013 | 2018-04-03 | CLASS 1
CON-BMP-TRA-000001 | 076551C-000D-PP-124 | 000-A-PRO-50018-001 | TTSJV ENGINEERING MANAGEMENT PLAN | A | 2018-03-09 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3-REVIEWED WITH COMMENTS BMP-BOC-TRE-000010 | 2018-03-28 | CLASS 1
CON-BMP-TRA-000002 | 076551C-000D-PP-107 | 000-A-PRO-50005-001 | PROJECT DOCUMENT CODING | A | 2018-03-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3-REVIEWED WITH COMMENTS BMP-BOC-TRE-000009 | 2018-03-28 | CLASS 1
CON-BMP-TRA-000002 | 076551C-000D-PP-110 | 000-A-PRO-50008-001 | DOCUMENT ISSUE DISTRIBUTION TO AND APPROVAL BY BAPCO | A | 2018-03-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-03-26 | 3-REVIEWED WITH COMMENTS BMP-BOC-TRE-000004 | 2018-03-28 | CLASS 1
CON-BMP-TRA-000004 | 076551C-000D-SL-0811-001 | 000-A-INX-50001-001 | BIDDERS LIST FOR HP VESSELS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1-APPROVED BMP-DIR-TRE-000009 | 2018-04-17 | CLASS 3
CON-BMP-TRA-000004 | 076551C-000D-SL-0910-004 | 000-A-INX-50002-001 | BIDDERS LIST FOR BB5 CENTRIFUGAL PUMPS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1-APPROVED BMP-DIR-TRE-000009 | 2018-04-17 | CLASS 3
CON-BMP-TRA-000004 | 076551C-000D-SL-1011-001 | 000-A-INX-50003-001 | BIDDERS LIST FOR BB5 CENTRIFUGAL COMPRESSORS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1-APPROVED BMP-DIR-TRE-000009 | 2018-04-17 | CLASS 3
CON-BMP-TRA-000004 | 076551C-000D-SL-1020-001 | 000-A-INX-50004-001 | BIDDERS LIST FOR RECIPROCATING COMPRESSORS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  | 1-APPROVED BMP-DIR-TRE-000009 | 2018-04-17 | CLASS 3
CON-BMP-TRA-000005 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE | 0 | 2018-03-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-BOC-TRE-000011 CS REPLIED ON 11/04/18 | 2018-03-28 | CLASS 3
CON-BMP-TRA-000006 | 076551C-000D-PP-015 | 000-A-PRI-50011-001 | PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK (MDRB) | A | 2018-03-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3-REVIEWED WITH COMMENT BMP-DIR-TRE-000008 CS REPLIED ON 07/05/18 | 2018-04-16 | CLASS 2
CON-BMP-TRA-000007 | 076551C-000D-PP-601 | 000-A-PRO-50045-001 | PROCUREMENT EXECUTION PLAN | A | 2018-03-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000002 | 2018-04-12 | CLASS 2
CON-BMP-TRA-000007 | 076551C-000D-PP-605 | 000-A-PRI-50006-001 | QA QC/INSPECTION AND EXPEDITING REQUIREMENTS FOR VENDORS | A | 2018-03-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000002 CS REPLIED ON 07/05/18 | 2018-04-12 | CLASS 2
CON-BMP-TRA-000008 | 076551C-000D-PP-104 | 000-A-PRO-50003-001 | COORDINATION PROCEDURE AMONG THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV AND LICENSORS | A | 2018-03-19 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00009 CS REPLIED ON 19/04/18 | 2018-04-04 | CLASS 2
CON-BMP-TRA-000009 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | A | 2018-03-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-03 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000007 CS REPLIED ON 12/04/18 | 2018-03-30 | CLASS 1
CON-BMP-TRA-000010 | 076551C-000D-PLG-102 | 000-A-PMP-50001-001 | WORK BREAKDOWN STRUCTURE | A | 2018-03-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000006 CS REPLIED ON 03/05/18 | 2018-03-30 | CLASS 1
CON-BMP-TRA-000011 | 076551C-000D-PP-100 | 000-A-ORG-50001-001 | TTSJV PROJECT ORGANIZATION CHART | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000012 | 076551C-000D-RR-1001 | 000-A-RPT-50001-001 | WEEKLY PROGRESS REPORT N.01 AS OF MARCH 16TH, 2018 (WEEK 03) | 0 | 2018-03-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000013 | 076551C-000D-SL-0113-001 | 000-A-INX-50006-001 | BIDDERS LIST FOR HYDROGEN STEAM REFORMER | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000013 | 076551C-000D-SL-0470-001 | 000-A-INX-50008-001 | BIDDERS LIST FOR HCU REACTOR INTERNALS | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000013 | 076551C-000D-SL-4141-001 | 000-A-INX-50012-001 | BIDDERS LIST FOR DESALTER PACKAGE | 0 | 2018-03-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000014 | 076551C-000D-PP-551 | 000-A-PRO-50041-001 | PROJECT HSSE PLAN | A | 2018-03-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-07 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000017 | 2018-04-26 | CLASS 2
CON-BMP-TRA-000015 | 076551C-000D-PP-108 | 000-A-PRO-50006-001 | HOMOGENIZATION PROCEDURE | A | 2018-03-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-07 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00010 | 2018-04-04 | CLASS 2
CON-BMP-TRA-000016 | 076551C-000D-PP-500 | 000-A-PRO-50039-001 | OVERALL PROJECT QUALITY PLAN | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000016 CS REPLIED ON 13/04/18 | 2018-04-06 | CLASS 1
CON-BMP-TRA-000016 | 076551C-000D-PP-502 | 000-A-PRO-50040-001 | CONFIDENTIALITY PLAN | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000001 CS REPLIED ON 13/04/18 | 2018-04-09 | CLASS 1
CON-BMP-TRA-000017 | 076551C-000D-SL-0960-001 | 000-A-INX-50005-001 | BIDDERS LIST FOR EBULLATING PUMPS | 0 | 2018-03-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000018 | 076551C-000D-PP-111 | 000-A-PRO-50009-001 | REPORTING PROCEDURE | A | 2018-03-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000015 CS REPLIED ON 18/04/18 | 2018-04-06 | CLASS 2
CON-BMP-TRA-000019 | 076551C-000D-RR-1002 | 000-A-RPT-50002-001 | WEEKLY PROGRESS REPORT N.02 AS OF MARCH 23RD, 2018 (WEEK 04) | 0 | 2018-03-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000020 | 076551C-000D-PP-610 | 000-A-PRI-50002-001 | VENDOR PRE-QUALIFICATION PROCEDURE | A | 2018-03-28 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-18 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000015 REPLIED ON 11/05/18 | 2018-05-04 | CLASS 1
CON-BMP-TRA-000021 | 076551C-000D-SL-0110-001 | 000-A-INX-50013-001 | BIDDERS LIST FOR HCU HEATERS LICENSED FIRED HEATERS (RHCU) | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-0215-001 | 000-A-INX-50014-001 | BIDDERS LIST FOR MULTI EFFECT DESALINATION PACKAGE | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-0710-002 | 000-A-INX-50011-001 | BIDDERS LIST FOR AIR COOLERS | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-4010-001 | 000-A-INX-50015-001 | BIDDERS LIST FOR BMP SOLID SULPHUR HANDLING PACKAGE | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000021 | 076551C-000D-SL-4352-001 | 000-A-INX-50016-001 | BIDDERS LIST FOR BMP SOLIDIFICATION PACKAGE | 0 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000022 | 076551C-000D-PP-261 | 000-A-PRI-50012-001 | REQUIREMENTS FOR EQUIPMENT SUPPLIER 3D MODEL | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000003 | 2018-04-16 | CLASS 2
CON-BMP-TRA-000023 | 076551C-000D-RR-1002 | 000-A-RPT-50002-001 | WEEKLY PROGRESS REPORT N.02 AS OF MARCH 23RD, 2018 (WEEK 04) | 1 | 2018-03-30 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000024 | 076551C-000D-PP-128 | 000-A-PRO-50019-001 | PROJECT INTERFACE MANAGEMENT PLAN | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000006 | 2018-04-16 | CLASS 2
CON-BMP-TRA-000025 | 076551C-000D-RR-1003 | 000-A-RPT-50003-001 | WEEKLY PROGRESS REPORT N.03 AS OF MARCH 30TH, 2018 (WEEK 005) | 0 | 2018-04-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000026 | 076551C-000D-PP-121 | 000-A-PRO-50015-001 | DEVIATION WAIVER AND TECHNICAL QUERY REQUEST PROCEDURE | A | 2018-04-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-19 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000012 CS REPLIED ON 07/05/18 | 2018-04-19 | CLASS 2
CON-BMP-TRA-000027 | 076551C-000D-PP-101 | 000-A-PRO-50001-001 | PROJECT EXECUTION PLAN | B | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 4-NOT APPROVED BMP-DIR-TRE-000021 | 2018-05-03 | CLASS 1
CON-BMP-TRA-000028 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | B | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-30 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000014 CS REPLIED ON 27/04/18 | 2018-04-24 | CLASS 1
CON-BMP-TRA-000029 | 076551C-000D-PP-307 | 000-A-PRO-50036-001 | VARIATION PROCEDURE | A | 2018-04-05 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-20 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000018 CS REPLIED ON 07/05/18 | 2018-04-26 | CLASS 2
CON-BMP-TRA-000030 | 076551C-000D-PP-301 | 000-A-PRO-50031-001 | PLANNING AND SCHEDULING PROCEDURE | A | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000010 | 2018-04-17 | CLASS 1
CON-BMP-TRA-000031 | 076551C-000D-SL-0570-001 | 000-A-INX-50010-001 | BIDDERS LIST FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | 0 | 2018-04-06 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000032 | 076551C-000D-NM-0000-001 | 000-A-PLD-50001-001 | ENGINEERING DELIVERABLE LIST | A | 2018-04-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-23 |  |  | CLASS 2
CON-BMP-TRA-000032-REV.1 | 076551C-000D-NM-0000-001 | 000-A-PLD-50001-001 | ENGINEERING DELIVERABLE LIST | A | 2018-05-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000034 | 2018-05-18 | CLASS 2
CON-BMP-TRA-000033 | 076551C-000D-SL-0411-001 | 000-A-INX-50020-001 | BIDDERS LIST FOR 2.25CR-1MO-V REACTORS AND INTERNALS | 0 | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000033 | 076551C-000D-SL-0610-001 | 000-A-INX-50018-001 | BIDDERS LIST FOR HP S&T HEAT EXCHANGERS | 0 | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000033 | 076551C-000D-SL-0710-002 | 000-A-INX-50011-001 | BIDDERS LIST FOR AIR COOLERS | 0A | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000033 | 076551C-000D-SL-1013-001 | 000-A-INX-50019-001 | BIDDERS LIST FOR INTEGRALLY GEARED AIR COMPRESSOR | 0 | 2018-04-09 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000034 | 076551C-000D-PP-564 | 000-A-PRI-50004-001 | HSSE REQUIREMENTS FOR VENDORS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000016 | 2018-04-26 | CLASS 2
CON-BMP-TRA-000035 | 076551C-000D-PLG-303 | 000-A-SCH-50002-001 | LEVEL 1 PROJECT CONTRACT SCHEDULE AS OF 30-MARCH-2018 | 0 | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000023 | 2018-05-07 | CLASS 2
CON-BMP-TRA-000036 | 076551C-000D-PP-312 | 000-A-PRO-50073-001 | PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | A | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000011 REPLIED ON 11/05/2018 | 2018-04-18 | CLASS 2
CON-BMP-TRA-000037 | 076551C-000D-RR-1004 | 000-A-RPT-50004-001 | WEEKLY PROGRESS REPORT N.04 AS OF APRIL 6TH, 2018 (WEEK 006) | 0 | 2018-04-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000038 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE | 0A | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 |  |  | CLASS 3
CON-BMP-TRA-000039 | 076551C-000D-RR-101 | 000-A-MRS-50001-001 | MONTHLY PROGRESS REPORT N.01 AS OF MARCH 30TH, 2018 (MONTH 01) | 0 | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 |  |  | CLASS 2
CON-BMP-TRA-000040 | 076551C-000D-SL-0110-002 | 000-A-INX-50017-001 | BIDDERS LIST FOR FIRED HEATERS CDU/VDU | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0119-004 | 000-A-INX-50021-001 | BIDDERS LIST FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0140-001 | 000-A-INX-50022-001 | BIDDERS LIST FOR INCINERATOR PACKAGE | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0150-001 | 000-A-INX-50023-001 | BIDDERS LIST FOR AUXILIARY STEAM BOILERS | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000040 | 076551C-000D-SL-0411-001 | 000-A-INX-50020-001 | BIDDERS LIST FOR 2.25CR-1MO-V REACTORS AND INTERNALS | 0A | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000041 | 076551C-000D-SL-0310-001 | 000-A-INX-50025-001 | BIDDERS LIST FOR INDUCED DRAFT COOLING TOWER | 0 | 2018-04-12 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000042 | 076551C-000D-PP-500 | 000-A-PRO-50039-001 | OVERALL PROJECT QUALITY PLAN | B | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000013 CS REPLIED ON 03/05/18 | 2018-04-20 | CLASS 1
CON-BMP-TRA-000043 | 076551C-000D-PP-502 | 000-A-PRO-50040-001 | CONFIDENTIALITY PLAN | 0 | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000005 / CS REPLIED ON 22/05/2018 | 2018-05-02 | CLASS 1
CON-BMP-TRA-000044 | 076551C-000D-PP-256 | 000-A-PRO-50027-001 | 3D MODELLING CIVIL PROCEDURE | A | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 4-NOT APPROVED BMP-DIR-TRE-000020 | 2018-05-03 | CLASS 2
CON-BMP-TRA-000045 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF APRIL 13TH - WEEK 007 | 0B | 2018-04-17 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000046 | 076551C-000D-RR-1005 | 000-A-RPT-50005-001 | WEEKLY PROGRESS REPORT N.05 AS OF APRIL 13TH, 2018 (WEEK 007) | 0 | 2018-04-17 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000047 | 076551C-000D-PP-111 | 000-A-PRO-50009-001 | REPORTING PROCEDURE | 0 | 2018-04-18 | FOR BAPCO INFORMATION | BMP Project Director | 2018-05-07 |  |  | CLASS 2
CON-BMP-TRA-000048 | 076551C-000D-SL-0846-001 | 000-A-INX-50033-001 | BIDDERS LIST FOR FEED FILTERS | 0 | 2018-03-13 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000049 | 076551C-000D-SL-1410-001 | 000-A-INX-50024-001 | BIDDERS LIST FOR ADDITIONL SOIL INVESTIGATION | 0 | 2018-04-20 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000050 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF APRIL 20TH - WEEK 008 | 0C | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 |  |  | CLASS 3
CON-BMP-TRA-000051 | 076551C-000D-PP-104 | 000-A-PRO-50003-001 | COORDINATION PROCEDURE AMONG THE BAHRAIN PETROLEUM COMPANY B.S.C. (CLOSED) BAPCO AND TTSJV AND LICENSORS | B | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000019 | 2018-04-29 | CLASS 2
CON-BMP-TRA-000052 | 076551C-000D-SL-0511-001 | 000-A-INX-50035-001 | BIDDERS LIST FOR CS COLUMNS | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-0511-002 | 000-A-INX-50009-001 | BIDDERS LIST FOR CLADDED COLUMNS (LLI) | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-0848-002 | 000-A-INX-50030-001 | BIDDERS LIST FOR CALCITE BED PACKAGE | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-0910-005 | 000-A-INX-50031-001 | BIDDERS LIST FOR API 610 HIGH SPEED PUMPS | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-4112-001 | 000-A-INX-50029-001 | BIDDERS LIST FOR NITROGEN GENERATION STORAGE AND VAPORIZATION | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000052 | 076551C-000D-SL-4171-001 | 000-A-INX-50036-001 | BIDDERS LIST FOR AIR DRYERS PACKAGE | 0 | 2018-04-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000053 | 076551C-000D-RR-1006 | 000-A-RPT-50006-001 | WEEKLY PROGRESS REPORT N.06 AS OF APRIL 20TH, 2018 (WEEK 008) | 0 | 2018-04-24 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000054 | 076551C-000D-JSS-1300-001 | 000-L-TSP-50001-001 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000022 / CS REPLIED ON 21/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1310-001 | 000-L-TSP-50004-001 | JOB SUPPLY SPECIFICATION FOR VALVES (GATE - GLOBE - CHECK) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000022 / CS REPLIED ON 22/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1320-001 | 000-L-TSP-50008-001 | JOB SUPPLY SPECIFICATION FOR PIPES | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000022 / CS REPLIED ON 21/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1330-001 | 000-L-TSP-50010-001 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000022 / CS REPLIED ON 21/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-000054 | 076551C-000D-JSS-1350-001 | 000-L-TSP-50012-001 | JOB SUPPLY SPECIFICATION FOR FLANGES | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000022 / CS REPLIED ON 21/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-000055 | CON-BMP-MOM-000013 | 000-A-MOM-50001-001 | SPPID REVIEW MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000014 | 000-A-MOM-50002-001 | S3D REVIEW MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000015 | 000-A-MOM-50003-001 | WEEKLY PROGRESS MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000016 | 000-A-MOM-50004-001 | WEEKLY PROGRESS MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000017 | 000-A-MOM-50005-001 | 1ST PROCUREMENT WEEKLY MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000018 | 000-A-MOM-50006-001 | SPEL CAP ANALYSIS REVIEW | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000019 | 000-A-MOM-50007-001 | WEEKLY PROGRESS MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000020 | 000-A-MOM-50008-001 | PROJECT CONTROL MEETING N 1 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000022 | 000-A-MOM-50009-001 | ESAP ITEMS REVIEW MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000023 | 000-A-MOM-50010-001 | PROCUREMENT WEEKLY MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000024 | 000-A-MOM-50011-001 | ESIA FOLLOW UP KOM | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000025 | 000-A-MOM-50012-001 | 3RD PROCUREMENT WEEKLY MEETING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000026 | 000-A-MOM-50013-001 | WEEKLY PROGRESS MEETING N 4 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000028 | 000-A-MOM-50014-001 | PROJECT CONTROL MEETING N 2 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000029 | 000-A-MOM-50015-001 | PROJECT CONTROL MEETING N 3 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000030 | 000-A-MOM-50016-001 | INSTRUMENTATION TAGGING | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000055 | CON-BMP-MOM-000031 | 000-A-MOM-50017-001 | MONTHLY MEETING N 1 | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000056 | 076551C-000D-PP-264 | 000-A-PRO-50077-001 | PIPING MATERIAL MANAGEMENT PROCEDURE | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000037 | 2018-05-22 | CLASS 2
CON-BMP-TRA-000057 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | C | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH COMMENTS WITH MINOR COMMENT BMP-DIR-TRE-000024 CS REPLIED ON 10/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-000058 | 076551C-000D-SL-0710-001 | 000-A-INX-50027-001 | BIDDERS LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | 0 | 2018-05-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000058 | 076551C-000D-SL-0840-002 | 000-A-INX-50037-001 | BIDDERS LIST FOR SIDE STREAM FILTERS | 0 | 2018-05-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000058 | 076551C-000D-SL-0910-003 | 000-A-INX-50034-001 | BIDDERS LIST FOR BB1 BB2 AND BB3 PUMPS | 0 | 2018-05-02 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000059 | 076551C-000D-PP-109 | 000-A-PRO-50007-001 | COMMENT MANAGEMENT PROCEDURE | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000033 | 2018-05-16 | CLASS 2
CON-BMP-TRA-000060 | 076551C-000D-PP-853 | 000-A-PRI-50009-001 | HSSE REQUIREMENTS FOR SUBCONTRACTORS | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000025 | 2018-05-10 | CLASS 2
CON-BMP-TRA-000061 | 076551C-000D-PP-804 | 000-A-PRO-50052-001 | CONSTRUCTION EXECUTION PLAN | A | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-17 | 4-NOT APPROVED BMP-DIR-TRE-000031 | 2018-05-16 | CLASS 1
CON-BMP-TRA-000062 | 076551C-000D-SL-1430-005 | 000-A-INX-50040-001 | BIDDERS LIST FOR OVERALL PILING WARKS | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000035 | 2018-05-22 | CLASS 3
CON-BMP-TRA-000062 | 076551C-000D-SL-8200-015 | 000-A-INX-50039-001 | BIDDERS LIST FOR TEMPORARY CONTRUCTION FACILITIES | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000035 | 2018-05-22 | CLASS 3
CON-BMP-TRA-000063 | 076551C-000D-PLG-102 | 000-A-PMP-50001-001 | WORK BREAKDOWN STRUCTURE | B | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000028 | 2018-05-15 | CLASS 1
CON-BMP-TRA-000064 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF APRIL 27TH - WEEK 009 | 0D | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000065 | 076551C-000D-PP-500 | 000-A-PRO-50039-001 | OVERALL PROJECT QUALITY PLAN | 0 | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-18 |  |  | CLASS 1
CON-BMP-TRA-000066 | 076551C-000D-PP-505 | 000-A-PRO-50078-001 | PROJECT AUDIT PROCEDURE | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000032 | 2018-05-16 | CLASS 2
CON-BMP-TRA-000066 | 076551C-000D-PP-506 | 000-A-PRO-50079-001 | NON CONFORMANCE CONTROL PROCEDURE | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000032 | 2018-05-16 | CLASS 2
CON-BMP-TRA-000067 | 076551C-000D-SL-0411-002 | 000-A-INX-50026-001 | BIDDERS LIST FOR SEPARATOR CR-MB | 0 | 2018-05-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000067 | 076551C-000D-SL-0851-001 | 000-A-INX-50032-001 | BIDDERS LIST FOR VACUUM UNIT PACKAGE | 0 | 2018-05-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000067 | 076551C-000D-SL-0910-007 | 000-A-INX-50038-001 | BIDDERS LIST FOR SULPHUR TRANSFER PUMPS | 0 | 2018-05-04 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000068 | 076551C-000D-RR-1007 | 000-A-RPT-50007-001 | WEEKLY PROGRESS REPORT N.07 AS OF APRIL 27TH, 2018 (WEEK 009) | 0 | 2018-05-04 | FOR INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000069 | 076551C-000D-PP-609 | 000-A-PRO-50013-001 | INSPECTION PROCEDURE | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000040 | 2018-05-22 | CLASS 2
CON-BMP-TRA-000070 | 076551C-000D-PP-611 | 000-A-PRO-50074-001 | PROJECT EXPEDITING PROCEDURE | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 |  |  | CLASS 1
CON-BMP-TRA-000071 | 076551C-000D-PP-605 | 000-A-PRI-50006-001 | QA QC/INSPECTION AND EXPEDITING REQUIREMENTS FOR VENDORS | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 1-APPROVED BMP-DIR-TRE-000027 / CS REPLIED ON 22/05/2018 | 2018-05-15 | CLASS 2
CON-BMP-TRA-000072 | 076551C-000D-PP-014 | 000-A-PRI-50001-001 | REQUIREMENTS FOR VENDOR DOCUMENTATION AND EXCHANGE OF CORRESPONDENCE | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-DIR-TRE-000038 | 2018-05-22 | CLASS 2
CON-BMP-TRA-000073 | 076551C-000D-PP-015 | 000-A-PRI-50011-001 | PRESCRIPTIONS FOR PREPARATION OF QUALITY CONTROL MANUFACTURING DOSSIER (QCMD) | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 |  |  | CLASS 2
CON-BMP-TRA-000074 | 076551C-000D-PP-856 | 000-A-PRO-50075-001 | HSSE TRAINING PLAN | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 |  |  | CLASS 2
CON-BMP-TRA-000075 | CON-BMP-MOM-000027 | 000-A-MOM-50018-001 | SPF GAP ANALISYS REVIEW | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000032 | 000-A-MOM-50019-001 | EXTERNAL INTERFACES WITH EWA | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000033 | 000-A-MOM-50020-001 | INTERFACE MEETING WITH BAPCO CLIENT N.1 | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000035 | 000-A-MOM-50021-001 | PROJECT CONTROL MEETING N¿04 | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000038 | 000-A-MOM-50022-001 | 4TH PROCUREMENT WEEKLY MEETING | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000075 | CON-BMP-MOM-000039 | 000-A-MOM-50023-001 | 5TH PROCUREMENT WEEKLY MEETING | 0 | 2018-05-07 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000076 | 076551C-000D-PP-304 | 000-A-PRO-50034-001 | TREND PROCEDURE | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 1-APPROVED BMP-DIR-TRE-000029 | 2018-05-15 | CLASS 2
CON-BMP-TRA-000076 | 076551C-000D-PP-307 | 000-A-PRO-50036-001 | VARIATION PROCEDURE | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 1-APPROVED BMP-DIR-TRE-000029 | 2018-05-15 | CLASS 2
CON-BMP-TRA-000077 | 076551C-000D-PP-121 | 000-A-PRO-50015-001 | DEVIATION WAIVER AND TECHNICAL QUERY REQUEST PROCEDURE | B | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 |  |  | CLASS 2
CON-BMP-TRA-000078 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 4TH - WEEK 010 | 0E | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000079 | 076551C-000D-SL-0610-002 | 000-A-INX-50028-001 | BIDDERS LIST FOR CLAD & ALLOY SHELL AND TUBES HEAT EXCHANGERS | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000079 | 076551C-000D-SL-4111-002 | 000-A-INX-50043-001 | BIDDERS LIST FOR PSA | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000080 | 076551C-000D-RR-1008 | 000-A-RPT-50008-001 | WEEKLY PROGRESS REPORT N.08 AS OF MAY 4TH, 2018 (WEEK 0010) | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000081 | 076551C-000D-RR-102 | 000-A-MRS-50002-001 | MONTHLY PROGRESS REPORT N.02 ASOF APRIL 27TH 2018 (MONTH 02) | 0 | 2018-05-09 | FOR BAPCO REVIEW | TTSJV Project Director | 2018-05-24 |  |  | CLASS 2
CON-BMP-TRA-000082 | 076551C-000D-NM-601 | 000-A-PSR-50001-001 | MATERIAL REQUISITION STATUS REPORT | 0 | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-24 |  |  | CLASS 2
CON-BMP-TRA-000083 | 076551C-000D-SL-0110-003 | 000-A-INX-50041-001 | BIDDERS LIST FOR UOP LICENSED FIRED HEATERS | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000083 | 076551C-000D-SL-0411-003 | 000-A-INX-50042-001 | BIDDERS LIST FOR REACTORS | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000084 | CON-BMP-MOM-000041 | 000-A-MOM-50025-001 | LEVEL 3 SCHEDULE AND ASSOCIATED DELIVERABLES DEVELOPMENT STATUS WORKSHOP | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000084 | CON-BMP-MOM-000043 | 000-A-MOM-50026-001 | 6TH PROCUREMENT WEEKLY MEETING | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000084 | CON-BMP-MOM-000044 | 000-A-MOM-50027-001 | WEEKLY PROGRESS MEETING N 6 | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000085 | 000-C-TCQ-00001-001 | 000-C-TCQ-00001-001 | TECHNICAL QUERY FOR GASKET MATERIAL FOR PV&HE | 0 | 2018-05-10 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000086 | 076551C-000D-PP-401 | 000-A-PRO-50037-001 | INVOICING PROCEDURE | D | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 1-APPROVED BMP-DIR-TRE-000026 | 2018-05-11 | CLASS 1
CON-BMP-TRA-000087 | 076551C-000D-PP-814 | 000-A-PRI-50014-001 | CONSTRUCTION SUBCONTRACTORS PRE-QUALIFICATION PROCEDURE | A | 2018-05-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 |  |  | CLASS 2
CON-BMP-TRA-000088 | 076551C-000D-PP-312 | 000-A-PRO-50073-001 | PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | B | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-27 |  |  | CLASS 2
CON-BMP-TRA-000089 | 076551C-000D-PP-610 | 000-A-PRI-50002-001 | VENDOR PRE-QUALIFICATION PROCEDURE | B | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 |  |  | CLASS 1
CON-BMP-TRA-000090 | 076551C-000D-PP-106 | 000-A-PRO-50004-001 | PROJECT TAGGING SYSTEM | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 |  |  | CLASS 2
CON-BMP-TRA-000091 | 076551C-000D-PP-857 | 000-A-PRO-50076-001 | SITE HSSE PROCEDURE FOR GEOTECHNICAL WORKS | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000039 | 2018-05-22 | CLASS 2
CON-BMP-TRA-000092 | 076551C-000D-SL-0950-001 | 000-A-INX-50047-001 | BIDDERS LIST FOR MECHANICAL SEAL | 0 | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000093 | CON-BMP-MOM-000040 | 000-A-MOM-50028-001 | PROJECT CONTROL MEETING N. 5 | 0 | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000094 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 11TH - WEEK 011 | 0F | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000095 | 076551C-000D-RR-1009 | 000-A-RPT-50009-001 | WEEKLY PROGRESS REPORT N 09 AS OF MAY 11TH 2018 (WEEK 011) | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000096 | 076551C-000D-MTO-1311-004 | 000-L-MTO-50001-001 | PIPING MATERIAL TAKE OFF SPECIFICATION | A | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000037 | 000-A-MOM-50029-001 | BMP UNITS' ASSIGNMENT TO ESD SYSTEM | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000045 | 000-A-MOM-50031-001 | WEEKLY CONSTRUCTION MEETING N.1 | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000046 | 000-A-MOM-50032-001 | PROCUREMENT WEEKLY MEETING N.7 | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000097 | CON-BMP-MOM-000048 | 000-A-MOM-50030-001 | MONTHLY MEETING NO.2 | 0 | 2018-05-16 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000098 | 076551C-000D-PP-815 | 000-A-PRO-50081-001 | CONSTRUCTION SUBCONTRACTING PLAN | A | 2018-05-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-000099 | 076551C-000D-PP-507 | 000-A-PRO-50082-001 | PROJECT AUDIT PLAN AND SCHEDULE | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-000099 | 076551C-000D-PP-508 | 000-A-PRO-50083-001 | CORRECTIVE ACTION PROCEDURE | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-000100 | 076551C-000D-JSD-1300-030 | 000-L-TSP-50016-001 | JOB DESIGN SPECIFICATION FOR ALLOWABLE NOZZLE LOADS FOR EQUIPMENT | A | 2018-05-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-01 |  |  | CLASS 1
CON-BMP-TRA-000101 | 000-L-TCQ-00006-001 | 000-L-TCQ-00006-001 | TECHNICAL QUERY FOR PWHT REQUIREMENT OF PIPING CLASS D3H | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000101 | 000-L-TCQ-00007-001 | 000-L-TCQ-00007-001 | TECHNICAL QUERY FOR BODY TO BONNET CONNECTION OF SMALL BORE VALVES IN HYDROGEN SERVICE #900 AND #1500 | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000101 | 000-L-TCQ-00010-001 | 000-L-TCQ-00010-001 | TECHNICAL QUERY FOR LINE-MOUNTED BY PASS FOR GATE VALVES IN STEAM SERVICE 8 AND ABOVE | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000102 | 076551C-000D-SL-1750-280 | 000-A-INX-50045-001 | BIDDERS LIST FOR MARINE WORKS | 0 | 2018-05-18 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000103 | 076551C-000D-SL-1410-002 | 000-A-INX-50044-001 | BIDDERS LIST FOR TOPOGRAPHIC SURVEY | 0 | 2018-05-14 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000104 | 076551C-000D-PP-123 | 000-A-PRO-50017-001 | EQUIPMENT AND MATERIAL CRITICALITY RATING | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-000105 | 076551C-000D-SL-0910-003 | 000-A-INX-50034-001 | BIDDERS LIST FOR BB1 BB2 AND BB3 PUMPS | 0A | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000106 | 076551C-000D-SL-4046-001 | 000-A-INX-50048-001 | BIDDERS LIST FOR DOSING SYSTEM | 0 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000107 | 076551C-000D-JSS-1300-001 | 000-L-TSP-50001-001 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-000107 | 076551C-000D-JSS-1320-001 | 000-L-TSP-50008-001 | JOB SUPPLY SPECIFICATION FOR PIPES | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-000107 | 076551C-000D-JSS-1330-001 | 000-L-TSP-50010-001 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-000107 | 076551C-000D-JSS-1350-001 | 000-L-TSP-50012-001 | JOB SUPPLY SPECIFICATION FOR FLANGES | 0 | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-000108 | CON-BMP-MOM-000021 | 000-A-MOM-50033-001 | SPI GAP ANALISYS REVIEW | 0 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000108 | CON-BMP-MOM-000047 | 000-A-MOM-50034-001 | PROJECT CONTROL MEETING N.6 | 0 | 2018-05-21 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000109 | 076551C-000D-PLG-302 | 000-A-SCH-50001-001 | BMP PROJECT 90 DAYS STARTER SCHEDULE AS OF MAY 18TH - WEEK 012 | 0G | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000110 | 076551C-000D-PP-502 | 000-A-PRO-50040-001 | CONFIDENTIALITY PLAN | 0A | 2018-05-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-06 |  |  | CLASS 1
CON-BMP-TRA-000111 | 076551C-000D-JSS-1310-001 | 000-L-TSP-50004-001 | JOB SUPPLY SPECIFICATION FOR VALVES (GATE - GLOBE - CHECK) | 0 | 2018-05-22 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-06 |  |  | CLASS 1
CON-BMP-TRA-000112 | 076551C-000D-PP-605 | 000-A-PRI-50006-001 | QA QC/INSPECTION AND EXPEDITING REQUIREMENTS FOR VENDORS | 0 | 2018-05-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-06 |  |  | CLASS 2
CON-BMP-TRA-000113 | 076551C-000D-RR-1010 | 000-A-RPT-50010-001 | WEEKLY PROGRESS REPORT N 10 AS OF MAY 18TH 2018 (WEEK 012) | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000114 | 076551C-000D-PP-810 | 000-A-PRO-50056-001 | SITE INSPECTION COORDINATION PROCEDURE (CONSTRUCTION AND PRECOMMISSIONING) | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-07 |  |  | CLASS 2
CON-BMP-TRA-000115 | 000-L-TCQ-00004-001 | 000-L-TCQ-00004-001 | TECHNICAL QUERY FOR BOLT TENSIONING REQUIREMENT FOR HYDROGEN SERVICE 600 AND GREATER | 0 | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000116 | CON-BMP-MOM-000050 | 000-A-MOM-50035-001 | WEEKLY PROGRESS MEETING N 7 | 0 | 2018-05-23 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000117 | 076551C-000D-PP-557 | 000-A-PRO-50084-001 | EQUIPMENT INSPECTION GUIDELINE | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-000118 | 000-P-TCQ-00001-001 | 000-P-TCQ-00001-001 | TECHNICAL QUERY FOR POWER SUPPLY TO SALVAGE YARD | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-000118 | 000-P-TCQ-00002-001 | 000-P-TCQ-00002-001 | TECHNICAL QUERY FOR POWER SUPPLY TO U378 AREA | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010001 | 076551C-000R-MS-1410-001 | 000-S-MST-60001-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION REFINERY AREA | A | 2018-03-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3-REVIEWED WITH MINOR COMMENTS BMPC-BOC-TRE-000012 | 2018-04-03 | CLASS 2
CON-BMP-TRA-010001 | 076551C-000R-PS-1410-001 | 000-S-BOM-60001-001 | PRICE LIST FOR SOIL INVESTIGATION REFINERY AREA | A | 2018-03-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-03-30 | 3-REVIEWED WITH MINOR COMMENTS BMPC-BOC-TRE-000012 | 2018-04-03 | CLASS 2
CON-BMP-TRA-010002 | 076551C-079-CN-0007-001 | 079-A-BOD-00001-001 | PROCESS DESIGN BASIS SPENT CAUSTIC TREATING PLANT | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000012 | 2018-04-06 | CLASS 1
CON-BMP-TRA-010003 | 076551C-082-CN-0007-001 | 082-A-BOD-00001-001 | PROCESS DESIGN BASIS 1 FLARE SYSTEM | A | 2018-03-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000011 | 2018-04-05 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0051-001-001 | 000-A-PPN-60000-001 | GENERAL PLOT PLAN REFINERY NORTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000021 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0051-002-001 | 000-A-PPN-60001-001 | GENERAL PLOT PLAN REFINERY SOUTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000021 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-005-001 | 000-A-PPN-60002-001 | OPERATING CENTRAL KEY PLAN NORTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000021 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-006-001 | 000-A-PPN-60003-001 | OPERATING CENTRAL KEY PLAN SOUTH SIDE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000021 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-009-001 | 000-A-PPN-60005-001 | OVERALL KEY PLAN BMP | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000021 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010004 | 076551C-000R-DW-0053-011-001 | 000-A-PPN-60004-001 | OVERALL OPERATING CENTER KEY PLAN | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000021 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-001-001 | 018-A-PFD-00001-001 | PROCESS FLOW DIAGRAM FIRST TRAIN REACTION AND SEPARATIONSECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-002-001 | 018-A-PFD-00001-002 | PROCESS FLOW DIAGRAM FIRST TRAIN H2 RECOVERY SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-003-001 | 018-A-PFD-00001-003 | PROCESS FLOW DIAGRAM FIRST TRAIN COMPRESSION SECTION SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-004-001 | 018-A-PFD-00001-004 | PROCESS FLOW DIAGRAM SECOND TRAIN REACTION AND SEPARATION SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-005-001 | 018-A-PFD-00001-005 | PROCESS FLOW DIAGRAM SECOND TRAIN H2 RECOVERY SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-006-001 | 018-A-PFD-00001-006 | PROCESS FLOW DIAGRAM SECOND TRAIN H2 COMPRESSION SECTION SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-007-001 | 018-A-PFD-00001-007 | PROCESS FLOW DIAGRAM SEPARATION & AMINE ABSORBER COMMON SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-008-001 | 018-A-PFD-00001-008 | PROCESS FLOW DIAGRAM ATMOSPHERIC COLUMN SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-009-001 | 018-A-PFD-00001-009 | PROCESS FLOW DIAGRAM VACUUM COLUMN SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-010-001 | 018-A-PFD-00001-010 | PROCESS FLOW DIAGRAM VACUUM TOWER SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-011-001 | 018-A-PFD-00001-011 | PROCESS FLOW DIAGRAM WASH WATER/LEAN AND RICH AMINE/SOUR WATER SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-012-001 | 018-A-PFD-00001-012 | PROCESS FLOW DIAGRAM WASH CATALYST HANDLING SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-013-001 | 018-A-PFD-00001-013 | PROCESS FLOW DIAGRAM CATALYST HANDLING SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-014-001 | 018-A-PFD-00001-014 | PROCESS FLOW DIAGRAM CATALYST HANDLING SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-015-001 | 018-A-PFD-00001-015 | PROCESS FLOW DIAGRAM SHORT CIRCULATION LOOP SECTION | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-016-001 | 018-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-017-001 | 018-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-018-001 | 018-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-019-001 | 018-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-020-001 | 018-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-021-001 | 018-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-022-001 | 018-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-023-001 | 018-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-024-001 | 018-A-PFD-00001-024 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-025-001 | 018-A-PFD-00001-025 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-026-001 | 018-A-PFD-00001-026 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-027-001 | 018-A-PFD-00001-027 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-028-001 | 018-A-PFD-00001-028 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-029-001 | 018-A-PFD-00001-029 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-030-001 | 018-A-PFD-00001-030 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-031-001 | 018-A-PFD-00001-031 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-032-001 | 018-A-PFD-00001-032 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-033-001 | 018-A-PFD-00001-033 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-034-001 | 018-A-PFD-00001-034 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-035-001 | 018-A-PFD-00001-035 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-036-001 | 018-A-PFD-00001-036 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-037-001 | 018-A-PFD-00001-037 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-038-001 | 018-A-PFD-00001-038 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-039-001 | 018-A-PFD-00001-039 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-040-001 | 018-A-PFD-00001-040 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-041-001 | 018-A-PFD-00001-041 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-042-001 | 018-A-PFD-00001-042 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-043-001 | 018-A-PFD-00001-043 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-044-001 | 018-A-PFD-00001-044 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-045-001 | 018-A-PFD-00001-045 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-046-001 | 018-A-PFD-00001-046 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-047-001 | 018-A-PFD-00001-047 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-048-001 | 018-A-PFD-00001-048 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010005 | 076551C-018-PFD-0010-049-001 | 018-A-PFD-00001-049 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000020 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-001-001 | 021-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HIGH PRESSURE LOOP | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-002-001 | 021-A-PFD-00001-002 | PROCESS FLOW DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-003-001 | 021-A-PFD-00001-003 | PROCESS FLOW DIAGRAM AMINE AND SOUR WATER | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-004-001 | 021-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-005-001 | 021-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-006-001 | 021-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-007-001 | 021-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-008-001 | 021-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-009-001 | 021-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-010-001 | 021-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-011-001 | 021-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-012-001 | 021-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-013-001 | 021-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-014-001 | 021-A-PFD-00001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-015-001 | 021-A-PFD-00001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-016-001 | 021-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-017-001 | 021-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-018-001 | 021-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-019-001 | 021-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-020-001 | 021-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-021-001 | 021-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-022-001 | 021-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010006 | 076551C-021-PFD-0010-023-001 | 021-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000025 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010007 | 076551C-023-CN-0007-001 | 023-A-BOD-00001-001 | BASIS OF DESIGN 1HRU (UNIT 023) HYDROGEN RECOVERY UNIT | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 |  |  | CLASS 1
CON-BMP-TRA-010008 | 076551C-051-CN-0007-001 | 051-A-BOD-00001-001 | PROCESS DESIGN BASIS REFRIGERATED LPG STORAGE (AT SITRA MARINE TERMINAL) | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000022 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010009 | 076551C-056-CN-0007-001 | 056-A-BOD-00001-001 | PROCESS DESIGN BASIS SITRA TANK FARM | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000023 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010010 | 076551C-061-CN-0007-001 | 061-A-BOD-00001-001 | PROCESS DESIGN BASIS SITRA WHARF AND ASSOCIATED MARINE FACILITIES | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000019 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010011 | 076551C-073-CN-0007-001 | 073-A-BOD-00001-001 | PROCESS DESIGN BASIS LSFO FLARE SYSTEM MODIFICATIONS | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000018 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010012 | 076551C-081-CN-0007-001 | 081-A-BOD-00001-001 | PROCESS DESIGN BASIS LSDP FLARE SYSTEM REVAMPING | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000017 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010013 | 076551C-907-CN-0007-001 | 907-A-BOD-00001-001 | PROCESS DESIGN BASIS REFINERY TO SITRA TRANSFE LINES | A | 2018-03-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000024 | 2018-04-09 | CLASS 1
CON-BMP-TRA-010014 | 076551C-000R-PP-100 | 000-A-ORG-60001-001 | ROC PROJECT ORGANIZATION CHART | 0 | 2018-03-27 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-001 | 930-L-GAD-00001-001 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 1 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00027 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-002 | 930-L-GAD-00001-002 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 2 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00027 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-003 | 930-L-GAD-00001-003 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 3 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00027 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010015 | 076551C-930-DW-1442-002-004 | 930-L-GAD-00001-004 | GENERAL LAYOUT INTERFACE POINT LOCATION AREA 4 | A | 2018-03-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00027 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010016 | 076551C-000R-DL-0811-001 | 000-C-IDL-60001-001 | DEVIATION LIST FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-ITP-0811-001 | 000-C-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-MR-0811-001 | 000-C-MRQ-60001-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-SP-0811-001 | 000-C-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-000R-SR-0811-001 | 000-C-SOW-60001-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V H.P. VESSELS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-002 | 018-C-GAD-00005-001 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-003 | 018-C-GAD-00006-001 | 018V1003 TRAIN 1 HP/HT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-005 | 018-C-GAD-00007-001 | 018V1005 TRAIN 1 HP/MT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-022 | 018-C-GAD-00008-001 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-023 | 018-C-GAD-00009-001 | 018V2003 TRAIN 2 HP/HT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010016 | 076551C-018-DW-0810-025 | 018-C-GAD-00010-001 | 018V2005 TRAIN 2 HP/MT SEPARATOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000014 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-DL-0411-001 | 000-C-IDL-60004-001 | DEVIATION LIST FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-ITP-0411-001 | 000-C-ITP-60004-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-MR-0411-001 | 000-C-MRQ-60004-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-SP-0411-001 | 000-C-GRD-60004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-000R-SR-0411-001 | 000-C-SOW-60004-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V REACTORS AND INTRNALS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-001 | 018-C-GAD-00001-001 | 018C1001R TRAIN 1 1ST REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-002 | 018-C-GAD-00002-001 | 018C1002R TRAIN 1 2ND REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-003 | 018-C-GAD-00003-001 | 018C2001R TRAIN 2 1ST REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-018-DW-0410-004 | 018-C-GAD-00004-001 | 018C2002R TRAIN 2 2ND REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010017 | 076551C-021-DW-0410-001 | 021-C-GAD-00001-001 | 021C0001R REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000013 | 2018-04-06 | CLASS 2
CON-BMP-TRA-010018 | 076551C-000R-MS-1410-003 | 000-S-MST-60002-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION TRANSFER LINE SITRA TANK FARAM AND SHARF AREA | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000004 | 2018-04-16 | CLASS 2
CON-BMP-TRA-010018 | 076551C-000R-PS-1410-003 | 000-S-BOM-60002-001 | PRICE LIST FOR SOIL INVESTIGATION TRANSFER LINE SITRA TANK FARM AND WHARF AREAS | A | 2018-03-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-17 | 3-REVIEWED WITH COMMENTS BMP-DIR-TRE-000004 | 2018-04-16 | CLASS 2
CON-BMP-TRA-010019 | 076551C-023-PFD-0010-001-001 | 023-A-PFD-00001-001 | PROCESS FLOW DIAGRAM 1HRU HYDROGEN RECOVERY UNIT | A | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000028 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010019 | 076551C-023-PFD-0010-001-002 | 023-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000028 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010019 | 076551C-023-PFD-0010-001-003 | 023-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000028 | 2018-04-16 | CLASS 1
CON-BMP-TRA-010020 | 076551C-000R-MS-1410-004 | 000-S-MST-60003-001 | TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY TANK FARM TRANSFER LINE SITRA TANK FARM & WHARF AREAS | A | 2018-04-06 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-20 | 2-REVIEWED WITH MINOR COMMENTS | 2018-04-18 | CLASS 2
CON-BMP-TRA-010021 | 076551C-000R-DL-0960-001 | 000-G-IDL-60002-001 | DEVIATION LIST FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 1-APPROVED BMP-ROC-TRE-000031 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-ITP-0960-001 | 000-G-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000031 CS REPLIED ON 17/05/2018 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-MR-0960-001 | 000-G-MRQ-60002-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000031 CS REPLIED ON 17/05/2018 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-SP-0960-001 | 000-G-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000031 CS REPLIED ON 17/05/2018 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-000R-SR-0960-001 | 000-G-SOW-60002-001 | SCOPE OF SUPPLY FOR EBULLATING PUMPS | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000031 CS REPLIED ON 17/05/2018 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010021 | 076551C-018-SP-0960-001 | 018-G-DAT-00001-001 | 1ST 2ND REACTOR RECYCLE PUMPS PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000031 CS REPLIED ON 17/05/2018 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010022 | 076551C-000R-PP-102 | 000-A-PRO-60001-001 | COORDINATION PROCEDURE BETWEEN BAPCO IPMT AND ROC | A | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000040 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010023 | 076551C-000R-DL-0411-001 | 000-C-IDL-60004-001 | DEVIATION LIST FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-ITP-0411-001 | 000-C-ITP-60004-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-MR-0411-001 | 000-C-MRQ-60004-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-SP-0411-001 | 000-C-GRD-60004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-000R-SR-0411-001 | 000-C-SOW-60004-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V REACTORS AND INTRNALS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-001 | 018-C-GAD-00001-001 | 018C1001R TRAIN 1 1ST REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-002 | 018-C-GAD-00002-001 | 018C1002R TRAIN 1 2ND REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-003 | 018-C-GAD-00003-001 | 018C2001R TRAIN 2 1ST REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-018-DW-0410-004 | 018-C-GAD-00004-001 | 018C2002R TRAIN 2 2ND REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010023 | 076551C-021-DW-0410-001 | 021-C-GAD-00001-001 | 021C0001R REACTOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-DL-0811-001 | 000-C-IDL-60001-001 | DEVIATION LIST FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-ITP-0811-001 | 000-C-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-MR-0811-001 | 000-C-MRQ-60001-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-SP-0811-001 | 000-C-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-000R-SR-0811-001 | 000-C-SOW-60001-001 | SCOPE OF SUPPLY FOR 2.25CR-1MO-V H.P. VESSELS | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-002 | 018-C-GAD-00005-001 | 018V1002 TRAIN 1 INTERSTAGE SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-003 | 018-C-GAD-00006-001 | 018V1003 TRAIN 1 HP/HT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-005 | 018-C-GAD-00007-001 | 018V1005 TRAIN 1 HP/MT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-022 | 018-C-GAD-00008-001 | 018V2002 TRAIN 2 INTERSTAGE SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-023 | 018-C-GAD-00009-001 | 018V2003 TRAIN 2 HP/HT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010024 | 076551C-018-DW-0810-025 | 018-C-GAD-00010-001 | 018V2005 TRAIN 2 HP/MT SEPARATOR | A | 2018-04-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 |  |  | CLASS 2
CON-BMP-TRA-010025 | 076551C-058-CN-0007-001 | 058-A-BOD-50001-001 | PROCESS DESIGN BASIS FUEL GAS SYSTEM | A | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000036 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-DL-0110-001 | 000-F-IDL-60001-001 | DEVIATION LIST 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-ITP-0110-001 | 000-F-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-MR-0110-001 | 000-F-MRQ-60001-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-000R-SP-0110-001 | 000-F-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 1 RHCU FIRED HEATERS 18F1001/18-F1002/18F2001/18F2002/18F0001/18F0002 | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-001 | 018-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1001 /F 018F2001 TRAIN 1&2 - REACTOR FEED FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-002 | 018-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0001 ATM COLUMN FEED FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-003 | 018-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0002 VACUUM COLUMN FEED FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-23 | CLASS 1
CON-BMP-TRA-010026 | 076551C-018-SP-0110-004 | 018-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1002 / 018F2002 TRAIN 1&2 - RECYCLE HYDROGEN FURNACE | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS CON-ROC-TRE-000030 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010028 | 076551C-050-CN-0007-001 | 050-A-BOD-50001-001 | PROCESS DESIGN BASIS REFINERY TANK FARM | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000037 | 2018-04-26 | CLASS 1
CON-BMP-TRA-010029 | 076551C-000R-MS-1410-002 | 000-S-MST-60004-001 | TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY AREA | A | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000033 | 2018-04-24 | CLASS 2
CON-BMP-TRA-010029 | 076551C-000R-PS-1410-002 | 000-S-BOM-60004-001 | PRICE LIST FOR TOPOGRAPHIC SURVEY FOR REFINERY AREA | A | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000033 | 2018-04-24 | CLASS 2
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-001-001 | 058-A-PFD-00002-001 | PROCESS FLOW DIAGRAM REFINERY GAS SYSTEM | 11A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000043 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-002-001 | 058-A-PFD-50001-001 | PROCESS FLOW DIAGRAM HP KHUFF GAS TO 2&3 BAGRU | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000043 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-003-001 | 058-A-PFD-50001-002 | PROCESS FLOW DIAGRAM FUEL GAS DISTRIBUTION TO NEW UNIT | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000043 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-004-001 | 058-A-PFD-50001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000043 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010030 | 076551C-058-PFD-0010-005-001 | 058-A-PFD-50001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000043 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010031 | 076551C-081-PFD-0010-001-001 | 081-A-PFD-50001-001 | PROCESS FLOW DIAGRAM FLARE SYSTEM LSDP HIGH LEVEL FLARE SERIAL | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000032 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010031 | 076551C-081-PFD-0010-002-001 | 081-A-PFD-50001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000032 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010032 | 076551C-082-PFD-0010-001-001 | 082-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REFINERY SOUTH FLARE SYSTEM FLARE KO DRUM AND RECOVERY | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000038 | 2018-04-26 | CLASS 1
CON-BMP-TRA-010032 | 076551C-082-PFD-0010-002-001 | 082-A-PFD-00001-002 | PROCESS FLOW DIAGRAM REFINERY SOUTH FLARE SYSTEM SEAL DRUM AND FLARE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000038 | 2018-04-26 | CLASS 1
CON-BMP-TRA-010032 | 076551C-082-PFD-0010-003-001 | 082-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000038 | 2018-04-26 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-DL-1011-001 | 000-K-IDL-60002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-ITP-1011-001 | 000-K-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-MR-1011-001 | 000-K-MRQ-60002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-SP-1011-001 | 000-K-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-000R-SR-1011-001 | 000-K-SOW-60002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-018-SP-1011-001 | 018-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 018K0002 A/B SOUR GAS COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-021-SP-1011-001 | 021-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 021K0001 RECYCLE GAS COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-021-SP-1012-001 | 021-K-DAT-00002-001 | DATA SHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 021T0001 RECYCLE GAS COMPRESSOR TURBINE | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-023-SP-1011-001 | 023-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 023K0002 A/B PURGE GAS COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010033 | 076551C-051-SP-1011-001 | 051-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 051K0001 A/B PROPANE COMPRESSOR | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000008 CS REPLIED ON 23/05/2018 | 2018-05-08 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-DL-0710-002 | 000-E-IDL-60008-001 | DEVIATION LIST FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-ITP-0710-002 | 000-E-ITP-60008-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-MR-0710-002 | 000-E-MRQ-60008-001 | MATERIAL REQUISITION FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-SP-0710-002 | 000-E-GRD-60008-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-000R-SR-0710-002 | 000-E-SOW-60008-001 | SCOPE OF SUPPLY FOR AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-004 | 018-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0011 - ATM COLUMN OVHD PRODUCT AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-005 | 018-E-DAT-00009-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0015 - DIESEL PRODUCT AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-006 | 018-E-DAT-00008-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0012 A/B - SOUR GAS COMPRESSOR DISCHARGE COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-009 | 018-E-DAT-00010-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0019 - LVGO AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-010 | 018-E-DAT-00011-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0023 - MVGO AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-018-SP-0710-012 | 018-E-DAT-00012-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0035 -TEMPERED WATER COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-021-SP-0710-003 | 021-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0012 -STRIPPER OVERHEAD AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010034 | 076551C-021-SP-0710-004 | 021-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0016 -DIESEL PRODUCT COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000049 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-DL-1020-001 | 000-K-IDL-60001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 1-APPROVED BMP-ROC-TRE-000039 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-ITP-1020-001 | 000-K-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 1-APPROVED BMP-ROC-TRE-000039 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-MR-1020-001 | 000-K-MRQ-60001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000039 CS REPLIED ON 17/05/2018 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-SP-1020-001 | 000-K-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000039 CS REPLIED ON 17/05/2018 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-000R-SR-1020-001 | 000-K-SOW-60001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000039 CS REPLIED ON 17/05/2018 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-018-SP-1020-001 | 018-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 018K1001/K1002/K00001/K2001/K2002 MAKE-UP HYDROGEN COMPRESSORS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000039 CS REPLIED ON 17/05/2018 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010035 | 076551C-023-SP-1020-001 | 023-K-DAT-00001-001 | DATA SHEET FOR RECIPROCATING COMPRESSOR FOR 023K0001A/B FEED GAS COMPRESSORS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000039 CS REPLIED ON 17/05/2018 | 2018-04-27 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-DL-0910-004 | 000-G-IDL-60001-001 | DEVIATION LIST FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 1-APPROVED BMP-ROC-TRE-000041 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-ITP-0910-004 | 000-G-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-MR-0910-004 | 000-G-MRQ-60001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-SP-0910-004 | 000-G-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-000R-SR-0910-004 | 000-G-SOW-60001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-0910-001 | 018-G-DAT-00002-001 | CENTRIFUGAL PUMPS DATA SHEET TRAIN1 & TRAIN2 FEED PUMPS 018P1001A/B & 018P2001A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-0910-002 | 018-G-DAT-00003-001 | CENTRIFUGAL PUMPS DATA SHEET QUENCH OIL PUMPS 018P0001A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-0910-018 | 018-G-DAT-00004-001 | CENTRIFUGAL PUMPS DATA SHEET HP LEAN AMINE PUMPS 018P0019A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-1012-001 | 018-K-DAT-00003-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T1001A/018T2001A TRAIN 1 FEED PUMP TURBINE TRAIN 2 FEED PUMP TURBINE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-018-SP-1012-002 | 018-K-DAT-00004-001 | DATASHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 018T0001A QUECH OIL PUMP TURBINE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010036 | 076551C-021-SP-0910-002 | 021-G-DAT-00001-001 | CENTRIFUGAL PUMP DATA SHEET FOR FEED PUMPS 021P0001 A/B | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000041 CS REPLIED ON 17/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010037 | 076551C-907-PFD-0010-001-001 | 907-A-PFD-50001-001 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000035 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010037 | 076551C-907-PFD-0010-002-001 | 907-A-PFD-50001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000035 | 2018-04-24 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-DL-0846-001 | 000-S-IDL-60002-001 | DEVIATION LIST FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000044 | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-ITP-0846-001 | 000-S-ITP-60002-001 | INSPECTIONA AND TEST PLAN FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000044 CS REPLIED ON 15/05/2018 | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-MR-0846-001 | 000-S-MRQ-60002-001 | MATERIAL REQUISITION FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000044 CS REPLIED ON 15/05/2018 | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-SP-0846-001 | 000-S-GRD-60002-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000044 CS REPLIED ON 15/05/2018 | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-000R-SR-0846-001 | 000-S-SOW-60002-001 | SCOPE OF SUPPLY FOR FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000044 CS REPLIED ON 15/05/2018 | 2018-05-03 | CLASS 1
CON-BMP-TRA-010038 | 076551C-021-SP-0841-001 | 021-S-DAT-00001-001 | DATA SHEET FOR 021U0001 FEED FILTERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000044 CS REPLIED ON 15/05/2018 | 2018-05-03 | CLASS 1
CON-BMP-TRA-010039 | 076551C-000R-DL-0511-001 | 000-C-IDL-60005-001 | DEVIATION LIST FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-ITP-0511-001 | 000-C-ITP-60005-001 | INSPECTION AND TEST PLAN (ITP) FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-MR-0511-001 | 000-C-MRQ-60005-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-SP-0511-001 | 000-C-GRD-60005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-000R-SR-0511-001 | 000-C-SOW-60005-001 | SCOPE OF SUPPLY FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-001-001 | 018-C-GAD-00013-001 | 018C0003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-002-001 | 018-C-GAD-00011-001 | 018C0001 ATMOSPHERIC COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-004-001 | 018-C-GAD-00012-001 | 018C0003 VACUUM COLUMN COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010039 | 076551C-018-DW-0510-007-001 | 018-C-GAD-00014-001 | 018C0003 TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | AP | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000047 CS REPLIED ON 15/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-DL-0570-001 | 000-C-IDL-60007-001 | DEVIATION LIST FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000046 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-ITP-0570-001 | 000-C-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000046 CS REPLIED ON 16/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-MR-0570-001 | 000-C-MRQ-60007-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000046 CS REPLIED ON 16/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-SP-0570-001 | 000-C-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000046 CS REPLIED ON 16/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010040 | 076551C-000R-SR-0570-001 | 000-C-SOW-60007-001 | SCOPE OF SUPPLY FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000046 CS REPLIED ON 16/05/2018 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-001-001 | 051-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE SHIPPING PUMPS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-002-001 | 051-A-PFD-00001-002 | PROCESS FLOW DIAGRAM REFRIGERATION SYSTEM (TRAIN A) | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-003-001 | 051-A-PFD-00001-003 | PROCESS FLOW DIAGRAM REFRIGERATION SYSTEM (TRAIN B) | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-004-001 | 051-A-PFD-00001-004 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE PACKAGE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-005-001 | 051-A-PFD-00001-005 | PROCESS FLOW DIAGRAM RECYCLE VAPORIZERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-006-001 | 051-A-PFD-00001-006 | PROCESS FLOW DIAGRAM NITROGEN PACKAGE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-007-001 | 051-A-PFD-00001-007 | PROCESS FLOW DIAGRAM INSTRUMENT AIR SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-008-001 | 051-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-009-001 | 051-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-010-001 | 051-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-011-001 | 051-A-PFD-00002-001 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE FIRE WATER SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-012-001 | 051-A-PFD-00002-002 | PROCESS FLOW DIAGRAM REFRIGERATED LPG STORAGE FIRE WATER SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010041 | 076551C-051-PFD-0010-013-001 | 051-A-PFD-00002-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE FIRE WATER SYSTEM | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000045 | 2018-05-06 | CLASS 1
CON-BMP-TRA-010042 | 076551C-000R-RT-6200-002 | 000-A-RPT-60001-001 | FEED ESIA IMPLEMENTATION REPORT | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000034 | 2018-05-10 | CLASS 2
CON-BMP-TRA-010042 | 076551C-000R-RT-6200-003 | 000-A-RPT-60002-001 | FEED ESAP IMPLEMENTATION REPORT | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000034 | 2018-05-10 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-001-001 | 018-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM FIRST TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-002-001 | 018-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM FIRST TRAIN H2 RECOVERY SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-003-001 | 018-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM FIRST TRAIN COMPRESSION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-004-001 | 018-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM SECOND TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-005-001 | 018-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM SECOND TRAIN H2 RECOVERY SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-006-001 | 018-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM SECOND TRAIN H2 COMPRESSION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-007-001 | 018-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM SEPARATION & AMINE ABSORBER COMMON SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-008-001 | 018-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM ATMOSPHERIC COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-009-001 | 018-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM VACUUM COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-010-001 | 018-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM VACUUM TOWER SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-011-001 | 018-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM WASH WATER / LEAN AND RICH AMINE / SOUR WATER SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-012-001 | 018-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM CATALYST HANDLING SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-013-001 | 018-A-MSD-00001-013 | MATERIAL SELECTION DIAGRAM CATALYST HANDLING SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-014-001 | 018-A-MSD-00001-014 | MATERIAL SELECTION DIAGRAM CATALYST HANDLING SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-015-001 | 018-A-MSD-00001-015 | MATERIAL SELECTION DIAGRAM SHORT CIRCULATION LOOP SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-016-001 | 018-A-MSD-00001-016 | MATERIAL SELECTION DIAGRAM FIRST TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-017-001 | 018-A-MSD-00001-017 | MATERIAL SELECTION DIAGRAM SECOND TRAIN REACTION AND SEPARATION SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-018-001 | 018-A-MSD-00001-018 | MATERIAL SELECTION DIAGRAM SEPARATION & AMINE ABSORBER COMMON SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-019-001 | 018-A-MSD-00001-019 | MATERIAL SELECTION DIAGRAM ATMOSPHERIC COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-020-001 | 018-A-MSD-00001-020 | MATERIAL SELECTION DIAGRAM VACUUM COLUMN SECTION | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010043 | 076551C-018-MSD-0011-021-001 | 018-A-MSD-00001-021 | MATERIAL SELECTION DIAGRAM GENERAL NOTES | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-RE-000048 | 2018-05-07 | CLASS 2
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-001-001 | 061-A-PFD-50001-001 | PROCESS FLOW DIAGRAM WHITE PRODUCTS TO WHARF | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-002-001 | 061-A-PFD-50001-002 | PROCESS FLOW DIAGRAM BLACK PORDUCTS TO WHARF / SLOP TO SITRA | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-003-001 | 061-A-PFD-50001-003 | PROCESS FLOW DIAGRAM BERTH NO. 1 - PRODUCTS MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-004-001 | 061-A-PFD-50001-004 | PROCESS FLOW DIAGRAM BERTH NO. 1 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-005-001 | 061-A-PFD-50001-005 | PROCESS FLOW DIAGRAM BERTH NO. 2 - PRODUCTS MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-006-001 | 061-A-PFD-50001-006 | PROCESS FLOW DIAGRAM BERTH NO. 2 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-007-001 | 061-A-PFD-50001-007 | PROCESS FLOW DIAGRAM BERTH NO. 3 - PRODUCT MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-008-001 | 061-A-PFD-50001-008 | PROCESS FLOW DIAGRAM BERTH NO. 3 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-009-001 | 061-A-PFD-50001-009 | PROCESS FLOW DIAGRAM BERTH NO. 5 - PRODUCTS MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-010-001 | 061-A-PFD-50001-010 | PROCESS FLOW DIAGRAM BERTH NO. 5 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-011-001 | 061-A-PFD-50001-011 | PROCESS FLOW DIAGRAM BERTH NO. 6 - PRODUCT MANIFOLDS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-012-001 | 061-A-PFD-50001-012 | PROCESS FLOW DIAGRAM BERTH NO. 6 - LOADING ARMS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010044 | 076551C-061-PFD-0010-013-001 | 061-A-PFD-50001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000042 | 2018-04-29 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-DL-0710-001 | 000-E-IDL-60007-001 | DEVIATION LIST FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-ITP-0710-001 | 000-E-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-MR-0710-001 | 000-E-MRQ-60007-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-SP-0710-001 | 000-E-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-000R-SR-0710-001 | 000-E-SOW-60007-001 | SCOPE OF SUPPLY FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-001 | 018-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E1005 TRAIN 1 - HP/MT FLASH GAS COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-002 | 018-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0006 - HP/MT VAPOR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-003 | 018-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0010 - ATM COLUMN REFLUX AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-007 | 018-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0007 - QUENCH OIL COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-008 | 018-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E2005 - TRAIN 2 - HP/MT FLASH GAS COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-018-SP-0710-011 | 018-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0030 - CIRCULATION OIL AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-021-SP-0710-001 | 021-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0010 -HHPS VAPOR AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010045 | 076551C-021-SP-0710-002 | 021-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0011 -HLPS VAPOR AIR COOLER | AP | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000050 CS REPLIED ON 18/05/2018 | 2018-05-11 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-DL-0851-001 | 000-H-IDL-60001-001 | DEVIATION LIST FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-ITP-0851-001 | 000-H-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-MR-0851-001 | 000-H-MRQ-60001-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-SP-0851-001 | 000-H-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-000R-SR-0851-001 | 000-H-SOW-60001-001 | SCOPE OF SUPPLY FOR VACUUM UNIT PACAKGE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-018-SP-0851-001 | 018-H-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 018U0001 VACUUM COLUMN EJECTOR SYSTEM | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010046 | 076551C-021-SP-0851-001 | 021-H-DAT-00001-001 | VACUUM UNIT (MULTISTAGE EJECTOR) DATA SHEET FOR 021U0002 VACUUM PRODUCING EQUIPMENT | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000052 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010047 | 076551C-023-SP-4111-001 | 023-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 023U0001 PRESSURE SWING ADSORPTION PACKAGE (PSA) | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 |  |  | CLASS 1
CON-BMP-TRA-010047-REV.1 | 076551C-023-SP-4111-001 | 023-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 023U0001 PRESSURE SWING ADSORPTION PACKAGE (PSA) | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 |  |  | CLASS 1
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-001-001 | 021-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000051 | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-002-001 | 021-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000051 | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-003-001 | 021-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM AMINE AND SOUR WATER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000051 | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-004-001 | 021-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000051 | 2018-05-11 | CLASS 2
CON-BMP-TRA-010048 | 076551C-021-MSD-0011-005-001 | 021-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000051 | 2018-05-11 | CLASS 2
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-001-001 | 056-A-PFD-50001-001 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-002-001 | 056-A-PFD-50001-002 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-003-001 | 056-A-PFD-50001-003 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-004-001 | 056-A-PFD-50001-004 | PROCESS FLOW DIAGRAM (EXISTING SITRA TANK FARM) KERO TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-005-001 | 056-A-PFD-50001-005 | PROCESS FLOW DIAGRAM GASOLINE/MTBE TANK AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-006-001 | 056-A-PFD-50001-006 | PROCESS FLOW DIAGRAM CRUDE OIL IMPORT EXPORT AND FUEL OIL TANKS AND SHIPPING PUMPS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-007-001 | 056-A-PFD-50001-007 | PROCESS FLOW DIAGRAM NAPHTHA CRUDE OIL SITRA TANKS | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-008-001 | 056-A-PFD-50001-008 | PROCESS FLOW DIAGRAM (EXISTING SITRA TANK FARM) SITRA SLOP TANKS AND PUMP | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-009-001 | 056-A-PFD-50001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010049 | 076551C-056-PFD-0010-010-001 | 056-A-PFD-50001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-00053 | 2018-05-13 | CLASS 1
CON-BMP-TRA-010050 | 076551C-000R-RT-1990-001 | 000-A-RSK-60001-001 | JOB SPECIFICATION FOR QUANTITATIVE RISK ASSESSMENT (INCLUDING BUILDING RISK ASSESSMENT) | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000056 |  | CLASS 2
CON-BMP-TRA-010051 | ROC-BMR-MOM-000001 | 000-A-MOM-60001-001 | ROC WEEKLY PROGRESS MEETING NO.1 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000002 | 000-A-MOM-60002-001 | ROC WEEKLY PROGRESS MEETING NO.2 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000004 | 000-A-MOM-60003-001 | 050 REFINERY TANK FARM P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000005 | 000-A-MOM-60004-001 | UNIT 056 SITRA TANK FARM P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000006 | 000-A-MOM-60005-001 | UNIT 061 SITRA WHARF P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000007 | 000-A-MOM-60006-001 | ROC BAPCO WEEKLY MEETING INT. U&O 4 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000008 | 000-A-MOM-60007-001 | ROC BAPCO WEEKLY MEETING INT. U&O 5 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000012 | 000-A-MOM-60008-001 | TTSJVROC BAPCO WEEKLY MEETING INT. U&O 6 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010051 | ROC-BMR-MOM-000013 | 000-A-MOM-60009-001 | ROC WEEKLY PROGRESS MEETING NO. 3 | 0 | 2018-05-03 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010052 | 076551C-023-MSD-0011-001-001 | 023-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM 1HRU HYDROGEN RECOVERY UNIT | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000054 | 2018-05-15 | CLASS 2
CON-BMP-TRA-010052 | 076551C-023-MSD-0011-002-001 | 023-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM 1HRU HYDROGEN RECOVERY UNIT | A | 2018-05-04 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000054 | 2018-05-15 | CLASS 2
CON-BMP-TRA-010053 | 076551C-000R-DL-0110-003 | 000-F-IDL-60002-001 | DEVIATION LIST 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000055 | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-ITP-0110-003 | 000-F-ITP-60002-001 | INSPECTION AND TEST PLAN 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000055 | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-MR-0110-003 | 000-F-MRQ-60002-001 | MATERIAL REQUISITION 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000055 | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-SP-0110-003 | 000-F-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 3HDU FIRED HEATER 021F0001 COMBINED FEED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000055 | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-000R-SR-0110-003 | 000-F-SOW-60002-001 | SCOPE OF SUPPLY 3HDU FIRED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000055 | 2018-05-15 | CLASS 1
CON-BMP-TRA-010053 | 076551C-021-SP-0110-001 | 021-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 021F0001 COMBINED FEED HEATER | A | 2018-05-04 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000055 | 2018-05-15 | CLASS 1
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-001-001 | 000-R-GAD-60002-001 | TEMPORARY CONSTRUCTION FACILITIES GENERAL LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-001-002 | 000-R-GAD-60002-002 | TEMPORARY CONSTRUCTION FACILITIES GENERAL LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-003-001 | 000-R-GAD-60006-001 | TEMPORARY CONSTRUCTION SATELLITE OFFICE BUILDING | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-003-002 | 000-R-GAD-60006-002 | TEMPORARY CONSTRUCTION SATELLITE OFFICE BUILDING | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-004-001 | 000-R-GAD-60007-001 | TEMPORARY CONSTRUCTION SATELLITE CONTRACTOR MESS HALL LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-005-001 | 000-R-GAD-60008-001 | TEMPORARY CONSTRUCTION SATELLITE GUARD HOUSE LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-006-001 | 000-R-GAD-60009-001 | TEMPORARY CONSTRUCTION FACILITIES FIRST AND LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-007-001 | 000-R-GAD-60010-001 | TEMPORARY CONSTRUCTION FACILITIES SIMPLE MEDICAL FACILITY SMF LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-008-001 | 000-R-GAD-60011-001 | TEMPORARY CONSTRUCTION FACILITIES TRAINING CENTER LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-009-001 | 000-R-GAD-60012-001 | TEMPORARY CONSTRUCTION FACILITIES CF - TWO FLOOR CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-009-002 | 000-R-GAD-60012-002 | TEMPORARY CONSTRUCTION FACILITIES CONTRACTOR OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-010-001 | 000-R-GAD-60013-001 | TEMPORARY CONSTRUCTION FACILITIES CONTRACTOR OFFICE BUILDING LAYOUT AT SITRA | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-011-001 | 000-R-GAD-60014-001 | TEMPORARY CONSTRUCTION FACILITIES TWO FLOOR IPTM OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-011-002 | 000-R-GAD-60014-002 | TEMPORARY CONSTRUCTION FACILITIES TWO FLOOR IPTM OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8210-012-001 | 000-R-GAD-60015-001 | TEMPORARY CONSTRUCTION FACILITIES OWNER OFFICE BUILDING LAYOUT | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-001-001 | 000-R-GAD-60004-001 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 9.00 SQM-2.000 SQM OF COVERED SHELTER (WITH COLD ROOM & SHELVES LAY.) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-002-001 | 000-R-GAD-60005-001 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3.000 SQM-1.000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-002-002 | 000-R-GAD-60005-002 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3.000 SQM-1.000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010054 | 076551C-000R-DW-8240-002-003 | 000-R-GAD-60005-003 | TEMPORARY CONSTRUCTION FACILITIES CLOSED WAREHOUSE 3.000 SQM-1.000 SQM OF COVERED SHELTER (SHELVES LAYOUT) | A | 2018-05-07 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-22 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000057 | 2018-05-22 | CLASS 2
CON-BMP-TRA-010055 | ROC-BMR-MOM-000015 | 000-A-MOM-60010-001 | P&ID'S REDLINE REVIEW MEETING UNIT 371,372,373,375,381,386,930 | 0 | 2018-05-08 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-001-001 | 050-A-PFD-50001-001 | PROCESS FLOW DIAGRAM NAPHTA TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-002-001 | 050-A-PFD-50001-002 | PROCESS FLOW DIAGRAM KEROSENE TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-003-001 | 050-A-PFD-50001-003 | PROCESS FLOW DIAGRAM 10 PPM DIESEL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-004-001 | 050-A-PFD-50001-004 | PROCESS FLOW DIAGRAM LVGO TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-005-001 | 050-A-PFD-50001-005 | PROCESS FLOW DIAGRAM HSR NAPHTA SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-006-001 | 050-A-PFD-50001-006 | PROCESS FLOW DIAGRAM DIESEL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-007-001 | 050-A-PFD-50001-007 | PROCESS FLOW DIAGRAM NEW 1RHCU FEED TANKS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-008-001 | 050-A-PFD-50001-008 | PROCESS FLOW DIAGRAM A/B CRUDE OIL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-009-001 | 050-A-PFD-50001-009 | PROCESS FLOW DIAGRAM A/B CRUDE OIL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-010-001 | 050-A-PFD-50001-010 | PROCESS FLOW DIAGRAM FUEL OIL/CRUDE OIL TRANSFER SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-011-001 | 050-A-PFD-50001-011 | PROCESS FLOW DIAGRAM UNCONVERTED OIL (UCO)/DIESEL TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-012-001 | 050-A-PFD-50001-012 | PROCESS FLOW DIAGRAM 2HDU AND 3HDU FEED TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-013-001 | 050-A-PFD-50001-013 | PROCESS FLOW DIAGRAM 1HCU AND 2HCU GASOIL FEED TANKS AND PUMPS | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-014-001 | 050-A-PFD-50001-014 | PROCESS FLOW DIAGRAM KMU FEED TANKS AND KERO INJECTION TANKS (FO BLENDING) | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-015-001 | 050-A-PFD-50001-015 | PROCESS FLOW DIAGRAM LIGHT NAPHTA TANKS AND PUMPS FOR GASOLINE BLENDING | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-016-001 | 050-A-PFD-50001-016 | PROCESS FLOW DIAGRAM PLATFORMATE TANKS AND PUMPS FOR GASOLINE BLENDING | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-017-001 | 050-A-PFD-50001-017 | PROCESS FLOW DIAGRAM EXISTING DIESEL BLENDING SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-018-001 | 050-A-PFD-50001-018 | PROCESS FLOW DIAGRAM EXISTING FUEL OIL BLENDING SYSTEM | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-019-001 | 050-A-PFD-50001-019 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-020-001 | 050-A-PFD-50001-020 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-021-001 | 050-A-PFD-50001-021 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-022-001 | 050-A-PFD-50001-022 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010056 | 076551C-050-PFD-0010-023-001 | 050-A-PFD-50001-023 | PROCESS FLOW DIAGRAM HEAT & MATERIAL BALANCE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000058 | 2018-05-22 | CLASS 1
CON-BMP-TRA-010057 | 076551C-000R-PP-557 | 000-A-PRO-60003-001 | HSSE REQUIREMENTS FOR WORKING IN THE WHARF AREA | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-TRE-000059 | 2018-05-23 | CLASS 2
CON-BMP-TRA-010059 | 076551C-000R-MS-8200-001 | 000-R-MST-60001-001 | TECHNICAL SPECIFICATION FOR TEMPORARY CONSTRUCTIN FACITLITIES (PREFABRICATED OR MODULARIZED BUILDING) INCLUDING UTILITIE | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-24 |  |  | CLASS 2
CON-BMP-TRA-010059 | 076551C-000R-PS-8200-001 | 000-R-BOM-60001-001 | PRICE LIST FOR TEMPORARY CONSTRUCTIN FACITLITIES (PREFABRICATED OR MODULARIZED BUILDING) INCLUDING UTILITIES | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-24 |  |  | CLASS 2
CON-BMP-TRA-010060 | 076551C-018-SP-4111-001 | 018-S-DAT-00001-001 | DESIGN SPECIFICATION SHEET FOR 018U1001/2001 TRAIN 1 & TRAIN 2 MEMBRANE UNITS | A | 2018-05-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-010061 | 076551C-058-MSD-0011-001-001 | 058-A-MSD-00002-001 | MATERIAL SELECTION DIAGRAM REFINERY GAS SYSTEM | 11A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-010061 | 076551C-058-MSD-0011-002-001 | 058-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM HP KHUFF GAS TO 2&3 BAGRU | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-010061 | 076551C-058-MSD-0011-003-001 | 058-A-MSD-50001-002 | MATERIAL SELECTION DIAGRAM FUEL GAS DISTRIBUTION TO NEW UNITS | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-010062 | ROC-BMR-MOM-000016 | 000-A-MOM-60012-001 | ROC WEEKLY PROGRESS MEETING | 0 | 2018-05-15 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010063 | 076551C-079-PFD-0010-001-001 | 079-A-PFD-00001-001 | PROCESS FLOW DIAGRAM SPEND CAUSTIC TREATING PLANT | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010063 | 076551C-079-PFD-0010-002-001 | 079-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010063 | 076551C-079-PFD-0010-003-001 | 079-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010064 | 076551C-907-MSD-0011-001-001 | 907-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM REFINERY TO SITRA TRANSFER LINES | A | 2018-05-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-010065 | 076551C-023-PID-0021-001-001 | 023-A-PID-00001-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FEED GAS COMPRESSOR KO DRUM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-002-001 | 023-A-PID-00002-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FEED GAS COMPRESSOR A | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-003-001 | 023-A-PID-00003-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FEED GAS COMPRESSOR B | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-004-001 | 023-A-PID-00005-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU OFF GAS AMINE ABSORBER AND LP AMINE PUMPS | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-005-001 | 023-A-PID-00007-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU PSA UNIT | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-006-001 | 023-A-PID-00004-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU LEAN AMINE SURGE DRUM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-007-001 | 023-A-PID-00006-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU RICH AMINE ACCUMULATOR | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-008-001 | 023-A-PID-00008-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU PSA PURGE GAS COMPRESSOR A | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-009-001 | 023-A-PID-00009-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU PSA PURGE GAS COMPRESSOR B | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-401-001 | 023-A-PID-00012-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT PROCESS HYDROCARBON | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-402-001 | 023-A-PID-00013-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT PROCESS AUXILIARY | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-403-001 | 023-A-PID-00014-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT UTILITIES | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0021-404-001 | 023-A-PID-00015-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU BATTERY LIMIT UTILITIES | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-501-001 | 023-A-PID-00010-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU FLARE SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-502-001 | 023-A-PID-00011-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU COOLING WATER SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-504-001 | 023-A-PID-00016-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU NITROGEN SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-505-001 | 023-A-PID-00017-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU INSTRUMENT AIR SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010065 | 076551C-023-PID-0031-506-001 | 023-A-PID-00018-001 | PIPING AND INSTRUMENT DIAGRAM - 1HRU 60 STEAM SYSTEM | A | 2018-05-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-31 |  |  | CLASS 1
CON-BMP-TRA-010066 | 076551C-000R-MS-1410-001 | 000-S-MST-60001-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION REFINERY AREA | 0 | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-010066 | 076551C-000R-MS-1410-003 | 000-S-MST-60002-001 | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION TRANSFER LINE SITRA TANK FARM AND WHARF AREA | 0 | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-010067 | 076551C-081-MSD-0011-001-001 | 081-A-MSD-50001-001 | MATERIAL SELECTION DIAGRAM FLARE SYSTEM LSDP HIGH LEVEL FLARE SERIAL | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-010067 | 076551C-082-MSD-0011-001-001 | 082-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REFINERY SOUTH FLARE SYSTEM FLARE K.O. DRUM AND RECOVERY | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-010067 | 076551C-082-MSD-0011-002-001 | 082-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REFINERY SOUTH FLARE SYSTEM SEAL DRUM AND FLARE | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-010068 | 076551C-000R-DW-1421-001-001 | 000-S-LSD-60001-001 | SITE PREPARATION ARRANGEMENT (PHASE 1 & 2) WITH F.G.L. DETAILS ROC, SOC, MOC - AREAS | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-010069 | 076551C-180-RT-2000-001 | 180-A-RPT-00001-001 | REFINERY SOUTH CONTROL BUILDINGS (RSCB) CONTROL ROOM STUDY REPORT | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-010070 | 076551C-000R-MR-0610-001 | 000-E-MRQ-60001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-04 |  |  | CLASS 1
CON-BMP-TRA-010071 | 076551C-000R-DW-1410-001-001 | 000-A-PPN-60006-001 | PLANT DATUM & COORDINATE SYSTEM GENERAL PLOT PLAN | A | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-04 |  |  | CLASS 1
CON-BMP-TRA-010072 | 076551C-000R-MS-3800-001 | 000-A-SOW-60001-001 | SCOPE OF WORKS FOR BMP MARINE FACILITIES INCLUDING UTILITIE | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-010073 | 076551C-930-DW-1452-007-001 | 930-L-GAD-00002-001 | DESALINATION DISCHARGE TO EXISTING OUT-FALL DITCH GENERAL LAYOUT & HYDRAULIC PROFILE | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-010074 | 076551C-930-DW-1454-001-001 | 930-Q-GAD-00001-001 | DESALINATION DISCHARGE TO EXISTING OUT-FALL DITCH CONCRETE DITCH SETIONS & DETAILS | A | 2018-05-22 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-06 |  |  | CLASS 2
CON-BMP-TRA-010075 | 076551C-058-CN-0008-002 | 058-A-BOD-50002-001 | MATERIAL SELECTION BASIS FUEL GAS SYSTEM | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-010076 | 076551C-081-CN-0008-002 | 081-A-BOD-50002-001 | MATERIAL SELECTION BASIS LSDP FLARE SYSTEM REVAMPING | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-010077 | 076551C-082-CN-0008-002 | 082-A-BOD-00002-001 | MATERIAL SELECTION BASIS REFINERY SOUTH FLARE SYSTEM | A | 2018-05-21 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-05 |  |  | CLASS 1
CON-BMP-TRA-010078 | ROC-BMR-MOM-000010 | 000-A-MOM-60013-001 | F000 INTERCONNETING P&ID'S REDLINE REVIEW MEETING | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010078 | ROC-BMR-MOM-000017 | 000-A-MOM-60015-001 | ROC WEEKLY PROGRESS MEETING | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010078 | ROC-BMR-MOM-000018 | 000-A-MOM-60016-001 | TTSJVROC/BAPCO WEEKLY MEETING INT.U&0 #8 | 0 | 2018-05-22 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010079 | ROC-BMR-MOM-000011 | 000-A-MOM-60018-001 | DESIGN BASIS LSFO FLARE SYSTEM MODIFICATIONS | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010079 | ROC-BMR-MOM-000014 | 000-A-MOM-60017-001 | SPENT CAUSTIC TRATMENT COD OUTLET BASIS | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-010079 | ROC-BMR-MOM-000022 | 000-A-MOM-60014-001 | TTSJVROC/BAPCO WEEKLY MEETING INT.U&0 #7 | 0 | 2018-05-24 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040001 | 019-C-GAD-10001-001 | 019-C-GAD-10001-001 | 019C0001R 1ST STAGE REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 019-C-GAD-10002-001 | 019-C-GAD-10002-001 | 019C0002R 2ND STAGE REACTOR | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-DL-0470-001 | 000-C-IDL-70007-001 | DEVIATION LIST FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-ITP-0470-001 | 000-C-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-MR-0470-001 | 000-C-MRQ-70007-001 | MATERIAL REQUISITION FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-SP-0470-001 | 000-C-GRD-70007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040001 | 076551C-000M-SR-0470-001 | 000-C-SOW-70007-001 | SCOPE OF SUPPLY FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00001 | 2018-04-09 | CLASS 2
CON-BMP-TRA-040002 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | STABILIZER - ITEM 010C0004 EX 010C0005/010-C-GAD-10005-001 AS PER CLIENT COMMENTS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | NAPHTHA SPLITTER - ITEM 010C0005 EX 010C0006/010-C-GAD-10006-001 AS PER CLIENT COMMENTS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | KEROSENE STRIPPER - ITEM 019C0006 | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | NAPHTHA SPLITTER - ITEM 019C0010 | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-DL-0511-001 | 000-C-IDL-70008-001 | DEVIATION LIST FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 1-APPROVED BMP-MOC-TRE-000003 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-ITP-0511-001 | 000-C-ITP-70008-001 | INSPECTION AND TEST PLAN FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-MR-0511-001 | 000-C-MRQ-70008-001 | MATERIAL REQUISITION FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-SP-0511-001 | 000-C-GRD-70008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000003 CS REPLIED ON 22/05/2018 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040002 | 076551C-000M-SR-0511-001 | 000-C-SOW-70008-001 | SCOPE OF SUPPLY FOR CS COLUMNS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 1-APPROVED BMP-MOC-TRE-000003 | 2018-04-11 | CLASS 2
CON-BMP-TRA-040003 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0003 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0008 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0012 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0062 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0072 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 019-E-DAT-00015-001 | 019-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0074 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-DL-0610-001 | 000-E-IDL-70001-001 | DEVIATION LIST FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-ITP-0610-001 | 000-E-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-MR-0610-001 | 000-E-MRQ-70001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-SP-0610-001 | 000-E-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040003 | 076551C-000M-SR-0610-001 | 000-E-SOW-70001-001 | SCOPE OF SUPPLY FOR HP SHELL AND TUBE HEAT EXCHANGES | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000002 CS REPLIED ON 22/05/2018 | 2018-04-06 | CLASS 1
CON-BMP-TRA-040004 | 010-F-DAT-00001-001 | 010-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 010F0001 ATMOSPHERIC COLUMN HEATER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 011-F-DAT-00001-001 | 011-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 011F0001 VACUUM COLUMN HEATER | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-DL-0110-002 | 000-F-IDL-70002-001 | DEVIATION LIST FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-ITP-0110-002 | 000-F-ITP-70002-001 | INSPECTION AND TEST PLAN FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-MR-0110-002 | 000-F-MRQ-70002-001 | MATERIAL REQUISITION FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-SP-0110-002 | 000-F-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040004 | 076551C-000M-SR-0110-002 | 000-F-SOW-70002-001 | SCOPE OF SUPPLY FOR CDU/VCU FIRED HEATERS | AP | 2018-03-29 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-13 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000004 | 2018-04-10 | CLASS 1
CON-BMP-TRA-040005 | 019-S-DAT-00005-001 | 019-S-DAT-00005-001 | MECHANICAL DATA SHEET FEED FILTER 019U0001 | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-24 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000005 CS REPLIED ON 22/05/2018 | 2018-04-19 | CLASS 2
CON-BMP-TRA-040006 | 085-E-DAT-00001-001 | 085-E-DAT-00001-001 | MECHANICAL DATA SHEET BMP MAIN COOLING TOWER 085CWT0001 | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000007 CS REPLIED ON 16/05/2018 | 2018-04-20 | CLASS 2
CON-BMP-TRA-040006 | 085-E-DAT-00002-001 | 085-E-DAT-00002-001 | MECHANICAL DATA SHEET BMP SECONDARY COOLING TOWER 085CWT0002 | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000007 CS REPLIED ON 16/05/2018 | 2018-04-20 | CLASS 2
CON-BMP-TRA-040007 | 019-E-GAD-00026-001 | 019-E-GAD-00026-001 | SETTING PLAN 019E0061 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000006 | 2018-04-19 | CLASS 2
CON-BMP-TRA-040007 | 019-E-GAD-00027-001 | 019-E-GAD-00027-001 | SETTING PLAN 019E0071 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000006 | 2018-04-19 | CLASS 2
CON-BMP-TRA-040007 | 019-E-GAD-00028-001 | 019-E-GAD-00028-001 | SETTING PLAN 019E0073 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | AP | 2018-04-10 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-26 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000006 | 2018-04-19 | CLASS 2
CON-BMP-TRA-040008 | 010-E-DAT-00030-001 | 010-E-DAT-00030-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0030 KERO AIR COOLER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000009 | 2018-04-20 | CLASS 2
CON-BMP-TRA-040008 | 010-E-DAT-00032-001 | 010-E-DAT-00032-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0033 NAPHTA SPLITTER OVERHEAD AIR COOLER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000009 | 2018-04-20 | CLASS 2
CON-BMP-TRA-040009 | 011-G-DAT-00001-001 | 011-G-DAT-00001-001 | MECHANICAL DATA SHEET - HVGO PUMPS 011P0003AB | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000008 | 2018-04-20 | CLASS 2
CON-BMP-TRA-040010 | 010-A-PFD-00001-001 | 010-A-PFD-00001-001 | PROCESS FLOW DIAGRAM CRUDE PREHEAT 1 DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-002 | 010-A-PFD-00001-002 | PROCESS FLOW DIAGRAM CRUDE PREHEAT 2 DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-003 | 010-A-PFD-00001-003 | PROCESS FLOW DIAGRAM CRUDE DISTILLATION DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-004 | 010-A-PFD-00001-004 | PROCESS FLOW DIAGRAM GAS COMPRESSION SECTION DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-005 | 010-A-PFD-00001-005 | PROCESS FLOW DIAGRAM NAPHTHA STABILIZER / SPLITTER DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-006 | 010-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-007 | 010-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-008 | 010-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-009 | 010-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-010 | 010-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040010 | 010-A-PFD-00001-011 | 010-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-001 | 011-A-PFD-00001-001 | PROCESS FLOW DIAGRAM VACUUM DISTILLATION DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000010 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-002 | 011-A-PFD-00001-002 | PROCESS FLOW DIAGRAM STEAM GENERATION & PRODUCTS COOLING DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000010 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-003 | 011-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000010 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-004 | 011-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000010 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040011 | 011-A-PFD-00001-005 | 011-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE | A | 2018-04-12 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-27 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000010 | 2018-04-24 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-001 | 085-A-PFD-00001-001 | PROCESS FLOW DIAGRAM CALCITE BEDS PACKAGE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-002 | 085-A-PFD-00001-002 | PROCESS FLOW DIAGRAM CALCITE BEDS PACKAGE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-003 | 085-A-PFD-00001-003 | PROCESS FLOW DIAGRAM BMP MAIN COOLING WATER SYSTEM | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-004 | 085-A-PFD-00001-004 | PROCESS FLOW DIAGRAM BMP SECONDARY COOLING WATER SYSTEM | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-005 | 085-A-PFD-00001-005 | PROCESS FLOW DIAGRAM SIDE STREAM FILTER PACKAGES | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-006 | 085-A-PFD-00001-006 | PROCESS FLOW DIAGRAM CW CHEMICAL TREATMENT | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-007 | 085-A-PFD-00001-007 | PROCESS FLOW DIAGRAM BMP MAIN COOLING WATER DISTRIBUTION | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-008 | 085-A-PFD-00001-008 | PROCESS FLOW DIAGRAM BMP SECONDARY COOLING WATER DISTRIBUTION | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-009 | 085-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-010 | 085-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-011 | 085-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-012 | 085-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040012 | 085-A-PFD-00001-013 | 085-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000017 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040013 | 019-G-DAT-00001-001 | 019-G-DAT-00001-001 | MECHANICAL DATA SHEET 1ST STAGE REACTOR FEED PUMP 019P0002A/B | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 019-G-DAT-00002-001 | 019-G-DAT-00002-001 | MECHANICAL DATA SHEET 2ND STAGE REACTOR FEED PUMP 019P0003A/B | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 019-G-DAT-00003-001 | 019-G-DAT-00003-001 | MECHANICAL DATA SHEET HIGH PRESSURE LEAN AMINE PUMP 019P0021A/B | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-DL-0910-004 | 000-G-IDL-70001-001 | DEVIATION LIST FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-ITP-0910-004 | 000-G-ITP-70001-001 | INSPECTION AND TEST PLAN FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-MR-0910-004 | 000-G-MRQ-70001-001 | MATERIAL REQUISITION FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-SP-0910-004 | 000-G-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040013 | 076551C-000M-SR-0910-004 | 000-G-SOW-70001-001 | SCOPE OF SUPPLY FOR BB5 PUMPS | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040014 | 019-C-GAD-30001-001 | 019-C-GAD-30001-001 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 019-C-GAD-30002-001 | 019-C-GAD-30002-001 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-DL-0411-001 | 000-C-IDL-70006-001 | DEVIATION LIST FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-ITP-0411-001 | 000-C-ITP-70006-001 | INSPECTION AND TEST PLAN FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-MR-0411-001 | 000-C-MRQ-70006-001 | MATERIAL REQUISITION FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-SP-0411-001 | 000-C-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040014 | 076551C-000M-SR-0411-001 | 000-C-SOW-70006-001 | SCOPE OF SUPPLY FOR REACTORS HCU | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000014 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 019-C-GAD-00003-001 | 019-C-GAD-00003-001 | GENERAL ARRANGEMENT 019V0003 1ST STAGE HOT HIGH PRESSURE SEPARATOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 019-C-GAD-00008-001 | 019-C-GAD-00008-001 | GENERAL ARRANGEMENT 019V0008 2ND STAGE HOT HIGH PRESSURE SEPARATOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 019-C-GAD-00010-001 | 019-C-GAD-00010-001 | GENERAL ARRANGEMENT 019V0010 HOT LOW PRESSURE SEPARATOR | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-DL-0411-002 | 000-C-IDL-70004-001 | DEVIATION LIST FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-ITP-0411-002 | 000-C-ITP-70004-001 | INSPECTION AND TEST PLAN FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-MR-0411-002 | 000-C-MRQ-70004-001 | MATERIAL REQUISITION FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-SP-0411-002 | 000-C-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040015 | 076551C-000M-SR-0411-002 | 000-C-SOW-70004-001 | SCOPE OF SUPPLY FOR SEPARATORS CR-MO | AP | 2018-04-13 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000013 CS REPLIED ON 22/05/2018 | 2018-04-25 | CLASS 2
CON-BMP-TRA-040016 | 011-H-DAT-00001-001 | 011-H-DAT-00001-001 | MECHANICAL DATA SHEET FOR VACUUM PACKAGE 011U0001 | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000016 CS REPLIED ON 21/05/2018 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 019-H-DAT-00001-001 | 019-H-DAT-00001-001 | MECHANICAL DATA SHEET FOR VACUUM DRYER EJECTOR SYSTEM 019U0002 | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000016 CS REPLIED ON 21/05/2018 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-DL-0851-001 | 000-H-IDL-70001-001 | DEVIATION LIST FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 1-APPROVED BMP-MOC-TRE-000016 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-ITP-0851-001 | 000-H-ITP-70001-001 | INSPECTION AND TEST PLAN FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000016 CS REPLIED ON 21/05/2018 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-MR-0851-001 | 000-H-MRQ-70001-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000016 CS REPLIED ON 21/05/2018 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-SP-0851-001 | 000-H-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000016 CS REPLIED ON 21/05/2018 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040016 | 076551C-000M-SR-0851-001 | 000-H-SOW-70001-001 | SCOPE OF SUPPLY FOR VACUUM UNIT PACKAGES | AP | 2018-04-13 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000016 CS REPLIED ON 21/05/2018 | 2018-04-26 | CLASS 1
CON-BMP-TRA-040017 | 010-K-DAT-00001-001 | 010-K-DAT-00001-001 | MECHANICAL DATA SHEET CDU OVERHEAD VAPOR COMPRESSOR 010K0001 A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000018 CS REPLIED ON 18/05/2018 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040017 | 019-K-DAT-00002-001 | 019-K-DAT-00002-001 | MECHANICAL DATA SHEET MAKE-UP HYDROGEN COMPRESSORS 19K0002 19K0003 19K0004 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000018 CS REPLIED ON 18/05/2018 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00001-001 | 010-G-DAT-00001-001 | MECHANICAL DATA SHEET CRUDE FEED PUMPS 010-P0001A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00002-001 | 010-G-DAT-00002-001 | MECHANICAL DATA SHEET DESALTED CRUDE PUMPS 010P0002 A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00003-001 | 010-G-DAT-00003-001 | MECHANICAL DATA SHEET PREFLASHED DRUM BOTTOM PUMPS 010P0029A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00004-001 | 010-G-DAT-00004-001 | MECHANICAL DATA SHEET KERO PA PUMPS 010P0007A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00005-001 | 010-G-DAT-00005-001 | MECHANICAL DATA SHEET DIESEL PA PUMPS 010P0010A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00006-001 | 010-G-DAT-00006-001 | MECHANICAL DATA SHEET UNSTABILIZED NAPHTA PUMPS 010P0019A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040018 | 010-G-DAT-00008-001 | 010-G-DAT-00008-001 | MECHANICAL DATA SHEET DIESEL PRODUCT PUMPS 010P0012A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000021 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040019 | 019-G-DAT-00005-001 | 019-G-DAT-00005-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER BOTTOM PUMPS 019P0005A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000020 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040019 | 019-G-DAT-00006-001 | 019-G-DAT-00006-001 | MECHANICAL DATA SHEET FRACTIONATOR BOTTOM PUMPS 019P0017A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000020 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040020 | 085-G-DAT-00001-001 | 085-G-DAT-00001-001 | MECHANICAL DATA SHEET MAIN COOLING WATER CIRCULATING PUMPS 085P0001 A/B/C/D/E | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000036 | 2018-05-03 | CLASS 2
CON-BMP-TRA-040020 | 085-G-DAT-00002-001 | 085-G-DAT-00002-001 | MECHANICAL DATA SHEET SECONDARY COOLING WATER CIRCULATING PUMPS 085P0002A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000036 | 2018-05-03 | CLASS 2
CON-BMP-TRA-040021 | 010-E-GAD-00004-001 | 010-E-GAD-00004-001 | SETTING PLAN 010E0010 A/B FLASHED CRUDE DIESEL PA EXCHANGER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000022 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00011-001 | 019-C-GAD-00011-001 | GENERAL ARRANGEMENT 019V0011 COLD LOW PRESSURE SEPARATOR | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000022 CS REPLIED ON 09/05/2018 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00014-001 | 019-C-GAD-00014-001 | GENERAL ARRANGEMENT 019V0014 NAPHTHA STABILIZER REFLUX DRUM | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000022 CS REPLIED ON 09/05/2018 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00028-001 | 019-C-GAD-00028-001 | GENERAL ARRANGEMENT 019V0028 RICH AMINE FLASH DRUM | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000022 CS REPLIED ON 09/05/2018 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040021 | 019-C-GAD-00029-001 | 019-C-GAD-00029-001 | GENERAL ARRANGEMENT 019V0029 SOUR WATER FLASH DRUM | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000022 CS REPLIED ON 09/05/2018 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040022 | 010-E-DAT-00004-001 | 010-E-DAT-00004-001 | SHEEL AND TUBE HEAT EXCHANGER DATA SHEET FOR 010E0010 A/B FLASHED CRUDE/DIESEL PA EXCHANGER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000029 | 2018-04-30 | CLASS 2
CON-BMP-TRA-040022 | 019-E-DAT-00041-001 | 019-E-DAT-00041-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0029 HEAVY DIESEL ARI COOLER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000029 | 2018-04-30 | CLASS 2
CON-BMP-TRA-040022 | 019-E-DAT-00047-001 | 019-E-DAT-00047-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0025 DIESEL PRODUCT AIR COOLER | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000029 | 2018-04-30 | CLASS 2
CON-BMP-TRA-040023 | 010-C-DAT-00001-001 | 010-C-DAT-00001-001 | MECHANICAL DATA SHEET CRUDE OIL DESALTER 010U0001 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000019 | 2018-04-27 | CLASS 2
CON-BMP-TRA-040024 | 019-A-PFD-00001-001 | 019-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HIGH PRESSURE LOOP DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-002 | 019-A-PFD-00001-002 | PROCESS FLOW DIAGRAM LP SEPARATION AND PRODUCT STRIPPING DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-003 | 019-A-PFD-00001-003 | PROCESS FLOW DIAGRAM FRACTIONATION DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-004 | 019-A-PFD-00001-004 | PROCESS FLOW DIAGRAM NAPHTA PRODUCT SECTION DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-005 | 019-A-PFD-00001-005 | PROCESS FLOW DIAGRAM FEED AND PRODUCT RUNDOWN DESIGN CAE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-006 | 019-A-PFD-00001-006 | PROCESS FLOW DIAGRAM MAKE-UP HYDROGEN COMPRESSION SECTION DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-007 | 019-A-PFD-00001-007 | PROCESS FLOW DIAGRAM AMINE AND SOUR WATER SYSTEM DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-008 | 019-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-009 | 019-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-010 | 019-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-011 | 019-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-012 | 019-A-PFD-00001-012 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-013 | 019-A-PFD-00001-013 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-014 | 019-A-PFD-00001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-015 | 019-A-PFD-00001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-016 | 019-A-PFD-00001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-017 | 019-A-PFD-00001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-018 | 019-A-PFD-00001-018 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-019 | 019-A-PFD-00001-019 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-020 | 019-A-PFD-00001-020 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-021 | 019-A-PFD-00001-021 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-022 | 019-A-PFD-00001-022 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-023 | 019-A-PFD-00001-023 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-024 | 019-A-PFD-00001-024 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-025 | 019-A-PFD-00001-025 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-026 | 019-A-PFD-00001-026 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-027 | 019-A-PFD-00001-027 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-028 | 019-A-PFD-00001-028 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-029 | 019-A-PFD-00001-029 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-030 | 019-A-PFD-00001-030 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-031 | 019-A-PFD-00001-031 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-032 | 019-A-PFD-00001-032 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-033 | 019-A-PFD-00001-033 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE DESIGN CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-034 | 019-A-PFD-00001-034 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-035 | 019-A-PFD-00001-035 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-036 | 019-A-PFD-00001-036 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-037 | 019-A-PFD-00001-037 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-038 | 019-A-PFD-00001-038 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-039 | 019-A-PFD-00001-039 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-040 | 019-A-PFD-00001-040 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-041 | 019-A-PFD-00001-041 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-042 | 019-A-PFD-00001-042 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-043 | 019-A-PFD-00001-043 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-044 | 019-A-PFD-00001-044 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-045 | 019-A-PFD-00001-045 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-046 | 019-A-PFD-00001-046 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE SOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-047 | 019-A-PFD-00001-047 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-048 | 019-A-PFD-00001-048 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-049 | 019-A-PFD-00001-049 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-050 | 019-A-PFD-00001-050 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-051 | 019-A-PFD-00001-051 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-052 | 019-A-PFD-00001-052 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-053 | 019-A-PFD-00001-053 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-054 | 019-A-PFD-00001-054 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-055 | 019-A-PFD-00001-055 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-056 | 019-A-PFD-00001-056 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-057 | 019-A-PFD-00001-057 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-058 | 019-A-PFD-00001-058 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040024 | 019-A-PFD-00001-059 | 019-A-PFD-00001-059 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE OPERATING CASE EOR | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 1-APPROVED BMP-MPC-TRE-000015 | 2018-04-25 | CLASS 1
CON-BMP-TRA-040025 | 011-H-DAT-00001-001 | 011-H-DAT-00001-001 | MECHANICAL DATA SHEET VACUUM PACKAGE 011U0001 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 4-NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-040025 | 019-H-DAT-00001-001 | 019-H-DAT-00001-001 | MECHANICAL DATA SHEET VACUUM DRYER EJECTOR SYSTEM 019U0002 | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 4-NOT APPROVED | 2018-04-17 | CLASS 2
CON-BMP-TRA-040026 | 019-G-DAT-00009-001 | 019-G-DAT-00009-001 | MECHANICAL DATA SHEET HEAVY NAPHTHA PRODUCT PUMPS 019P0020A/B/C | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000023 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-G-DAT-00010-001 | 019-G-DAT-00010-001 | MECHANICAL DATA SHEET HEAVY DIESEL PUMP AROUND PUMP 019P0012A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000023 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-G-DAT-00028-001 | 019-G-DAT-00028-001 | MECHANICAL DATA SHEET LIGHT DIESEL PRODUCT PUMP 019P0011A/B | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000023 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-K-DAT-00001-001 | 019-K-DAT-00001-001 | MECHANICAL DATA SHEET RECYCLE GAS COMPRESSOR | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000023 CS REPLIED ON 10/05/2018 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040026 | 019-K-DAT-00003-001 | 019-K-DAT-00003-001 | MECHANICAL DATA SHEET RECYCLE GAS COMPRESSOR TURBINE | AP | 2018-04-16 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000023 CS REPLIED ON 10/05/2018 | 2018-04-29 | CLASS 2
CON-BMP-TRA-040027 | 076551C-000M-DL-1020-001 | 000-K-IDL-70001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000024 CS REPLIED ON 18/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-ITP-1020-001 | 000-K-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000024 CS REPLIED ON 18/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-MR-1020-001 | 000-K-MRQ-70001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000024 CS REPLIED ON 18/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-SP-1020-001 | 000-K-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000024 CS REPLIED ON 18/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040027 | 076551C-000M-SR-1020-001 | 000-K-SOW-70001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000024 CS REPLIED ON 18/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-DL-4141-001 | 000-S-IDL-70009-001 | DEVIATION LIST FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000025 CS REPLIED ON 14/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-ITP-4141-001 | 000-S-ITP-70009-001 | INSPECTION AND TEST PLAN FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000025 CS REPLIED ON 14/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-MR-4141-001 | 000-S-MRQ-70009-001 | MATERIAL REQUISITION FOR DESALTER PACKAGER | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000025 CS REPLIED ON 14/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-SP-4141-001 | 000-S-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000025 CS REPLIED ON 14/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040028 | 076551C-000M-SR-4141-001 | 000-S-SOW-70009-001 | SCOPE OF SUPPLY FOR DESALTER PACKAGE | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000025 CS REPLIED ON 14/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-DL-1011-001 | 000-K-IDL-70002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000026 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-ITP-1011-001 | 000-K-ITP-70002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000026 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-MR-1011-001 | 000-K-MRQ-70002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000026 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-SP-1011-001 | 000-K-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000026 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040029 | 076551C-000M-SR-1011-001 | 000-K-SOW-70002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000026 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-DL-0846-001 | 000-S-IDL-70003-001 | DEVIATION LIST FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000027 CS REPLIED ON 22/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-ITP-0846-001 | 000-S-ITP-70003-001 | INSPECTION AND TEST PLAN FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000027 CS REPLIED ON 22/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-MR-0846-001 | 000-S-MRQ-70003-001 | MATERIAL REQUISITION FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000027 CS REPLIED ON 22/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-SP-0846-001 | 000-S-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000027 CS REPLIED ON 22/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040030 | 076551C-000M-SR-0846-001 | 000-S-SOW-70003-001 | SCOPE OF SUPPLY FOR FEED FILTER | AP | 2018-04-17 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000027 CS REPLIED ON 22/05/2018 | 2018-04-29 | CLASS 1
CON-BMP-TRA-040031 | 019-G-DAT-00004-001 | 019-G-DAT-00004-001 | MECHANICAL DATA SHEET INJECTION WATER PUMPS 019P0022 AB | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000028 | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-DL-0910-005 | 000-G-IDL-70005-001 | DEVIATION LIST FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 1-APPROVED BMP-MOC-TRE-000028 | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-ITP-0910-005 | 000-G-ITP-70005-001 | INSPECTION AND TEST PLAN FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000028 | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-MR-0910-005 | 000-G-MRQ-70005-001 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000028 | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-SP-0910-005 | 000-G-GRD-70005-001 | PARTICULAR TECHNICAL SPECIFICATION FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000028 | 2018-04-30 | CLASS 1
CON-BMP-TRA-040031 | 076551C-000M-SR-0910-005 | 000-G-SOW-70005-001 | SCOPE OF SUPPLY FOR API 610 HIGH SPEED PUMPS | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-04 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000028 | 2018-04-30 | CLASS 1
CON-BMP-TRA-040032 | 019-G-DAT-00007-001 | 019-G-DAT-00007-001 | MECHANICAL DATA SHEET LIGHT DIESEL P/A PUMO 019P0010 A/B | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 019-G-DAT-00008-001 | 019-G-DAT-00008-001 | MECHANICAL DATA SHEET FRACTIONATOR NAPHTA PUMPS 019P0006 A/B | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 050-G-DAT-55001-001 | 050-G-DAT-55001-001 | MECHANICAL DATA SHEET 1RHCU FEED PUMPS 050P0037 A/B | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-DL-0910-003 | 000-G-IDL-70004-001 | DEVIATION LIST FOR BB1, BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-ITP-0910-003 | 000-G-ITP-70004-001 | INSPECTION AND TEST PLAN FOR BB1, BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-MR-0910-003 | 000-G-MRQ-70004-001 | MATERIAL REQUISITION FOR BB1, BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-SP-0910-003 | 000-G-GRD-70004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BB1, BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 076551C-000M-SR-0910-003 | 000-G-SOW-70004-001 | SCOPE OF SUPPLY FOR BB1, BB2 AND BB3 PUMPS | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 372-G-DAT-57001-001 | 372-G-DAT-57001-001 | MECHANICAL DATA SHEET FED WATER PUMPS 372P0030 A/B/C | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040032 | 372-G-DAT-57002-001 | 372-G-DAT-57002-001 | MECHANICAL DATA SHEET COOLING WATER MAKE-UP PUMPS 372P0031 A/B/C | AP | 2018-04-20 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000035 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00012-001 | 085-S-DAT-00012-001 | MECHANICAL DATA SHEET BMP MAIN CALCITE BEDS PACKAGE 085U0001 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000030 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00013-001 | 085-S-DAT-00013-001 | MECHANICAL DATA SHEET BMP SECONDARY CALCITE BEDS PACKAGE 085U0010 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000030 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00014-001 | 085-S-DAT-00014-001 | MECHANICAL DATA SHEET BMP MAIN CW SIDE STREAM FILTERS PACKAGE 085U0002 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000030 CS REPLIED ON 17/05/2018 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040033 | 085-S-DAT-00015-001 | 085-S-DAT-00015-001 | MECHANICAL DATA SHEET BMP SECONDARY CW SIDE STREAM FILTERS PACKAGE 085U0003 | AP | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000030 CS REPLIED ON 17/05/2018 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040034 | 019-E-DAT-00045-001 | 019-E-DAT-00045-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR NAPHTA SPLITTER OVERHEAD AIR COOLER 019E0038 | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000031 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040034 | 019-E-DAT-00046-001 | 019-E-DAT-00046-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR HEAVY NAPHTA PRODUCT AIR COOLER 019E0041 | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000031 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 019-F-DAT-00001-001 | 019-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F-0001 1ST STAGE REACTOR FEED FURNACE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 019-F-DAT-00002-001 | 019-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F-0002 2ND STAGE REACTOR FEED FURNACE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 019-F-DAT-00003-001 | 019-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 019F-0003 FRACTIONATOR FEED FURNACE | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-DL-0110-001 | 000-F-IDL-70001-001 | DEVIATION LIST FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-ITP-0110-001 | 000-F-ITP-70001-001 | INSPECTION AND TEST PLANT (ITP) FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-MR-0110-001 | 000-F-MRQ-70001-001 | MATERIAL REQUISITION HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-SP-0110-001 | 000-F-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040035 | 076551C-000M-SR-0110-001 | 000-F-SOW-70001-001 | SCOPE OF SUPPLY FOR HCU FIRED HEATERS | AP | 2018-04-19 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-08 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000032 | 2018-05-02 | CLASS 1
CON-BMP-TRA-040036 | 019-C-GAD-00004-001 | 019-C-GAD-00004-001 | GENERAL ARRANGEMENT 019V0004 1ST STAGE COLD HIGH PRESSURE SEPARATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 019-C-GAD-00006-001 | 019-C-GAD-00006-001 | GENERAL ARRANGEMENT 019V0006 RECYCLE GAS K.O. DRUM | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 019-C-GAD-00009-001 | 019-C-GAD-00009-001 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 019-C-GAD-10003-001 | 019-C-GAD-10003-001 | GENERAL ARRANGEMENT 019V0009 2ND STAGE COLD HIGH PRESSURE SEPARATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-DL-0811-002 | 000-C-IDL-70001-001 | DEVIATION LIST FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-ITP-0811-002 | 000-C-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-MR-0811-002 | 000-C-MRQ-70001-001 | MATERIAL REQUISITION FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-SP-0811-002 | 000-C-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040036 | 076551C-000M-SR-0811-002 | 000-C-SOW-70001-001 | SCOPE OF SUPPLY FOR H.P. VESSELS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000034 CS REPLIED ON 18/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-DL-0811-001 | 000-C-IDL-70003-001 | DEVIATION LIST FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000033 CS REPLIED ON 09/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-ITP-0811-001 | 000-C-ITP-70003-001 | INSPECTION AND TEST PLAN (ITP) FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000033 CS REPLIED ON 09/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-MR-0811-001 | 000-C-MRQ-70003-001 | MATERIAL REQUISITION FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000033 CS REPLIED ON 09/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-SP-0811-001 | 000-C-GRD-70003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000033 CS REPLIED ON 09/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040037 | 076551C-000M-SR-0811-001 | 000-C-SOW-70003-001 | SCOPE OF SUPPLY FOR STAINLESS STEEL & CLAD VESSELS | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000033 CS REPLIED ON 09/05/2018 | 2018-05-02 | CLASS 2
CON-BMP-TRA-040038 | 010-C-GAD-10001-001 | 010-C-GAD-10001-001 | GENERAL ARRANGEMENT 010C0001 ATMOSPHERIC COLUMN | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 010-C-GAD-10002-001 | 010-C-GAD-10002-001 | GENERAL ARRANGEMENT 010C0002 KERO STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 010-C-GAD-10003-001 | 010-C-GAD-10003-001 | GENERAL ARRANGEMENT 010C0003 DIESEL STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 011-C-GAD-10001-001 | 011-C-GAD-10001-001 | GENERAL ARRANGEMENT 011C0001 VACUUM COLUMN | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 011-C-GAD-10002-001 | 011-C-GAD-10002-001 | GENERAL ARRANGEMENT 011C0002 TAL GAS ABSORBER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10004-001 | 019-C-GAD-10004-001 | GENERAL ARRANGEMENT 019C0004 PRODUCT STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10005-001 | 019-C-GAD-10005-001 | GENERAL ARRANGEMENT 019C0005 PRODUCT FRACTIONATOR | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10007-001 | 019-C-GAD-10007-001 | GENERAL ARRANGEMENT 019C0007 LIGHT DIESEL STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10008-001 | 019-C-GAD-10008-001 | GENERAL ARRANGEMENT 019C0008 HEAVY DIESEL STRIPPER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 019-C-GAD-10009-001 | 019-C-GAD-10009-001 | GENERAL ARRANGEMENT 019C0009 NAPHTHA STABILIZER | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-DL-0511-002 | 000-C-IDL-70009-001 | DEVIATION LIST FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 1-APPROVED BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-ITP-0511-002 | 000-C-ITP-70009-001 | INSPECTION AND TEST PLAN (ITP) FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-MR-0511-002 | 000-C-MRQ-70009-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-SP-0511-002 | 000-C-GRD-70009-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040038 | 076551C-000M-SR-0511-002 | 000-C-SOW-70009-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS (LLI) | AP | 2018-04-20 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-09 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000042 | 2018-05-06 | CLASS 2
CON-BMP-TRA-040039 | 076551C-000M-DL-0310-001 | 000-E-IDL-70006-001 | DEVIATION LIST FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 1-APPROVED BMP-MOC-TRE-000038 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-ITP-0310-001 | 000-E-ITP-70006-001 | INSPECTION AND TEST PLAN FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000038 CS REPLIED ON 16/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-MR-0310-001 | 000-E-MRQ-70006-001 | MATERIAL REQUISITION FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000038 CS REPLIED ON 16/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-SP-0310-001 | 000-E-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000038 CS REPLIED ON 16/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040039 | 076551C-000M-SR-0310-001 | 000-E-SOW-70006-001 | SCOPE OF SUPPLY FOR INDUCED DRAFT COOLING TOWER | AP | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000038 CS REPLIED ON 16/05/2018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040040 | 076551C-000M-DL-0570-001 | 000-C-IDL-70010-001 | DEVIATION LIST FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 1-APPROVED BMP-MOC-TRE-000043 | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-ITP-0570-001 | 000-C-ITP-70010-001 | INSPECTION AND TEST PLAN (ITP) FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000043 | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-MR-0570-001 | 000-C-MRQ-70010-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000043 | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-SP-0570-001 | 000-C-GRD-70010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000043 | 2018-05-07 | CLASS 2
CON-BMP-TRA-040040 | 076551C-000M-SR-0570-001 | 000-C-SOW-70010-001 | SCOPE OF SUPPLY FOR TRAYS AND INTERNALS FOR COLUMNS (CS & CLADDED) | A | 2018-04-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000043 | 2018-05-07 | CLASS 2
CON-BMP-TRA-040041 | 076551C-000M-DL-0840-002 | 000-S-IDL-70001-001 | DEVIATION LIST FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 1-APPROVED BMP-MOC-TRE-000037 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-ITP-0840-002 | 000-S-ITP-70001-001 | INSPECTION AND TEST PLAN FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000037 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-MR-0840-002 | 000-S-MRQ-70001-001 | MATERIAL REQUISITION FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000037 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-SP-0840-002 | 000-S-GRD-70001-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000037 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040041 | 076551C-000M-SR-0840-002 | 000-S-SOW-70001-001 | SCOPE OF SUPPLY FOR SIDE STREAM FILTERS | A | 2018-04-23 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-10 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000037 | 2018-05-04 | CLASS 1
CON-BMP-TRA-040042 | 010-E-DAT-00031-001 | 010-E-DAT-00031-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0023 DIESEL AIR COOLER | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00040 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040042 | 010-E-DAT-00031-001 | 010-E-DAT-00031-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0023 DIESEL AIR COOLER | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00040 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040042 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00040 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040042 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-00040 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-DAT-00008-001 | 019-E-DAT-00008-001 | AIR COOLED HEX DATA SHEET FOR 1ST STAGE HHPS VAPOR 019E0008 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000039 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-DAT-00009-001 | 019-E-DAT-00009-001 | AIR COOLED HEX DATA SHEET FOR 2ND STAGE HHPS VAPOR AIR COOLER 019E0012 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000039 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-DAT-00010-001 | 019-E-DAT-00010-001 | AIR COOLED HEX DATA SHEET FOR HLPS VAPOR AIR COOLER 019E0013 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000039 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-GAD-00013-001 | 019-E-GAD-00013-001 | SETTING PLAN FOR MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER 019E0044 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000039 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-GAD-00014-001 | 019-E-GAD-00014-001 | SETTING PLAN FOR MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER 019E0047 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000039 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040043 | 019-E-GAD-00015-001 | 019-E-GAD-00015-001 | SETTING PLAN FOR MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER 019E0049 | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000039 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-DL-0710-001 | 000-E-IDL-70007-001 | DEVIATION LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-MOC-TRE-000041 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-ITP-0710-001 | 000-E-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000041 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-MR-0710-001 | 000-E-MRQ-70007-001 | MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000041 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-SP-0710-001 | 000-E-GRD-70007-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000041 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040044 | 076551C-000M-SR-0710-001 | 000-E-SOW-70007-001 | SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL AIR COOLERS | AP | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000041 CS REPLIED ON 22/05/2018 | 2018-05-06 | CLASS 1
CON-BMP-TRA-040045 | 076551C-000M-PP-102 | 000-A-PRO-70001-001 | COORDINATION PROCEDURE BETWEEN BAPCO IMPT AND MOC | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000044 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040046 | 019-A-BOD-00001-001 | 019-A-BOD-00001-001 | PROCESS BASIS OF DESIGN 2HCU (UNIT C019) HYDROCRACKER UNIT | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040047 | 076551C-000M-PP-100 | 000-A-ORG-70001-001 | MOC PROJECT ORGANIZATION CHART | A | 2018-04-26 | FOR BAPCO INFORMATION | BMP Project Director |  |  |  | CLASS 3
CON-BMP-TRA-040048 | 010-A-EQL-00001-001 | 010-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 CRUDE DISTILLATION UNIT (7CDU) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000046 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 011-A-EQL-00001-001 | 011-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 7 VACUUM DISTILLATION UNIT (7 VDU) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000046 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 012-A-EQL-00001-001 | 012-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 1 SATURATED GAS PLANT- 1SGP | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000046 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 017-A-EQL-00001-001 | 017-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - NO 2 SATURATED GAS PLANT - 2SGP | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000046 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 019-A-EQL-00001-001 | 019-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - HYDROCRACKER UNIT (2 HCU) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000046 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040048 | 085-A-EQL-00001-001 | 085-A-EQL-00001-001 | ITEM INDEX (EQUIPMENT LIST) - COOLING WATER TOWER - CWT | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000046 | 2018-05-10 | CLASS 1
CON-BMP-TRA-040049 | 050-A-EQL-55001-001 | 050-A-EQL-55001-001 | ITEM INDEX (EQUIPMENT LIST) - REFINERY TANK FARM (PLANT N F050) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000048 | 2018-05-15 | CLASS 1
CON-BMP-TRA-040049 | 372-A-EQL-57001-001 | 372-A-EQL-57001-001 | ITEM INDEX (EQUIPMENT LIST) - BOILER FEED WATER AND CONDENSATE DISTRIBUTION (PLANT N U372) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000048 | 2018-05-15 | CLASS 1
CON-BMP-TRA-040050 | 076551C-000M-PP-124 | 000-A-PRO-70002-001 | MOC ENGINEERING MANAGEMENT PLAN | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000047 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-001 | 019-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-002 | 019-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM LP SEPARATION AND PRODUCT STRIPPING | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-003 | 019-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM FRACTIONATION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-004 | 019-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-005 | 019-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM FEED AND RUNDOWN | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-006 | 019-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM HYDROGEN COMPRESSION SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-007 | 019-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM AMINE AND SOUR WATER SYSTEM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-008 | 019-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM HIGH PRESSURE LOOP | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-009 | 019-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM FRACTIONATION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-010 | 019-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-011 | 019-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM FEED AND RUNDOWN | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-012 | 019-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM NAPHTHA PRODUCT SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-013 | 019-A-MSD-00001-013 | MATERIAL SELECTION DIAGRAM FEED FILTER SECTION | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-014 | 019-A-MSD-00001-014 | MATERIAL SELECTION DIAGRAM STEAM GENERATION SYSTEM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-015 | 019-A-MSD-00001-015 | MATERIAL SELECTION DIAGRAM PHOSPHATE INJECTION PACKAGE | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-016 | 019-A-MSD-00001-016 | MATERIAL SELECTION DIAGRAM STEAM BLOWDOWN COLLECTION SYSTEM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-017 | 019-A-MSD-00001-017 | MATERIAL SELECTION DIAGRAM FUEL GAS KO DRUM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-018 | 019-A-MSD-00001-018 | MATERIAL SELECTION DIAGRAM FLARE KO DRUM | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040051 | 019-A-MSD-00001-019 | 019-A-MSD-00001-019 | MATERIAL SELECTION DIAGRAM SOUR WATER SLOPS AND AMINE | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-MOC-TRE-000049 | 2018-05-15 | CLASS 2
CON-BMP-TRA-040052 | 076551C-000M-DL-0848-002 | 000-S-IDL-70004-001 | DEVIATION LIST FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-ITP-0848-002 | 000-S-ITP-70004-001 | INSPECTION AND TEST PLAN FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-MR-0848-002 | 000-S-MRQ-70004-001 | MATERIAL REQUISITION FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-SP-0848-002 | 000-S-GRD-70004-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 076551C-000M-SR-0848-002 | 000-S-SOW-70004-001 | SCOPE OF SUPPLY FOR CALCITE BED PACKAGE | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 085-S-DAT-00012-001 | 085-S-DAT-00012-001 | MECHANICAL DATA SHEET BMP MAIN CALCITE BEDS PACKAGE 085U0001 | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040052 | 085-S-DAT-00013-001 | 085-S-DAT-00013-001 | MECHANICAL DATA SHEET BMP SECONDARY CALCITE BEDS PACKAGE 085U0010 | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000050 | 2018-05-20 | CLASS 1
CON-BMP-TRA-040053 | 019-P-STS-00001-001 | 019-P-STS-00001-001 | LOAD BALANCE N 2 HYDROCRAKING UNIT - 2HCU SUBSTATION SST019R01 | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000052 | 2018-05-23 | CLASS 2
CON-BMP-TRA-040054 | 019-P-SLD-00001-001 | 019-P-SLD-00001-001 | KEY SINGLE LINE DIAGRAM N 2 HYDROCRAKING UNIT - 2HCU SUBSTATION SST019R01 | A | 2018-05-08 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS BMP-MOC-TRE-000051 | 2018-05-23 | CLASS 1
CON-BMP-TRA-040055 | 010-A-MSD-00001-001 | 010-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-002 | 010-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-003 | 010-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-004 | 010-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - GAS COMPRESSION SECT DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-005 | 010-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - DEBUTANIZER/NAPHTA SPLITTER DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-006 | 010-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT EQUIPMENT MATERIAL TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-007 | 010-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE PREHEAT EQUIPMENT MATERIAL TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-008 | 010-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE DISTILLATION EQUIPMENT MATERIAL TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-009 | 010-A-MSD-00001-009 | MATERIAL SELECTION DIAGRAM 7CDU/VDU/ - CRUDE DISTILLATION DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-010 | 010-A-MSD-00001-010 | MATERIAL SELECTION DIAGRAM SOUR WATER AND SLOPS CLOSED DRAINS | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-011 | 010-A-MSD-00001-011 | MATERIAL SELECTION DIAGRAM FLARE KO DRUM | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 010-A-MSD-00001-012 | 010-A-MSD-00001-012 | MATERIAL SELECTION DIAGRAM FUEL GAS KO DRUM | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-001 | 011-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM VACUUM DISTILLAION DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-002 | 011-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM STEAM GENERATION AND PRODUCTS COOLING DESIGN CASE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-003 | 011-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM VACUUM DISTILLATION EQUIPMENT TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040055 | 011-A-MSD-00001-004 | 011-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM STEAM GENERATION AND PRODUCTS COOLING EQUIPMENT TABLE | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040056 | 019-C-DAT-10008-001 | 019-C-DAT-10008-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HEAVY DIESEL STRIPPER 019C0008 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040056 | 019-C-DAT-10009-001 | 019-C-DAT-10009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER 019C0009 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040057 | 010-C-DAT-10001-001 | 010-C-DAT-10001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR ATMOSPHERIC COLUMN 010C0001 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040057 | 010-C-DAT-10002-001 | 010-C-DAT-10002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR KERO STRIPPER 010C0002 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040057 | 010-C-DAT-10003-001 | 010-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR DIESEL STRIPPER 010C0003 | AP | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 |  |  | CLASS 2
CON-BMP-TRA-040058 | 010-E-DAT-00016-001 | 010-E-DAT-00016-001 | SHELL AND TUBE HEX DATA SHEET FOR COMPRESSOR INTERSTAGE COOLER 010E0018 A/B | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040058 | 010-E-DAT-00017-001 | 010-E-DAT-00017-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER FEED/NAPHTHA SPLITTER BOTTOM EXCHANGER 010E0024 A/B | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040058 | 010-E-DAT-00024-001 | 010-E-DAT-00024-001 | SHELL AND TUBE HEX DATA SHEET FOR STABILIZER CONDENSER 010E0027 A/B | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040058 | 010-E-GAD-00016-001 | 010-E-GAD-00016-001 | SETTING PLAN COMPRESSOR INTERSTAGE COOLER 010E0018 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040058 | 010-E-GAD-00017-001 | 010-E-GAD-00017-001 | SETTING PLAN FOR STABILIZER FEED/NAPHTHA SPLITTER BOTTOM EXCHANGER 010E0024 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040058 | 010-E-GAD-00024-001 | 010-E-GAD-00024-001 | SETTING PLAN FOR STABILIZER CONDENSER 010E0027 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040059 | 011-E-DAT-00002-001 | 011-E-DAT-00002-001 | SHELL AND TUBE HEX DATA SHEET FOR LEAN AMINE | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040059 | 011-E-GAD-00002-001 | 011-E-GAD-00002-001 | SETTING PLAN FOR LEAN AMINE COOLER 0110E0008 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00025-001 | 019-E-DAT-00025-001 | SHELL AND TUBE HEX DATA SHEET FOR NAPHTHA STABILIZER FEED - BOTTOMS EXCHANGER 019E0035 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00026-001 | 019-E-DAT-00026-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0043 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00027-001 | 019-E-DAT-00027-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0046 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-DAT-00028-001 | 019-E-DAT-00028-001 | SHELL AND TUBE HEX DATA SHEET FOR MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER 019E0048 | A | 2018-04-30 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00025-001 | 019-E-GAD-00025-001 | SETTING PLAN 019E0035 NAPHTHA STABILIZER FEED BOTTOMS EXCHANGER | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00026-001 | 019-E-GAD-00026-001 | SETTING PLAN 019E0043 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00027-001 | 019-E-GAD-00027-001 | SETTING PLAN 019E0046 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040060 | 019-E-GAD-00028-001 | 019-E-GAD-00028-001 | SETTING PLAN 019E0048 MAKE-UP HYDROGEN FIRST STAGE INTERCOOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040061 | 019-E-DAT-00032-001 | 019-E-DAT-00032-001 | SHELL AND TUBE HEX DATA SHEET FOR KEROSENE PRODUCT TRIM COOLER 019E0020 | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040061 | 019-E-DAT-00036-001 | 019-E-DAT-00036-001 | SHELL AND TUBE HEX DATA SHEET FOR DIESEL PRODUCT TRIM COOLER 019E0026 | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-31 |  |  | CLASS 2
CON-BMP-TRA-040062 | 019-C-DAT-00005-001 | 019-C-DAT-00005-001 | MECHANICAL DATA SHEET HIGH PRESSURE CENTRIFUGAL SEPARATOR 019V0005 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040063 | 019-E-GAD-00032-001 | 019-E-GAD-00032-001 | SETTING PLAN FOR KEROSENE PRODUCT TRIM COOLER 019E0020 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040063 | 019-E-GAD-00036-001 | 019-E-GAD-00036-001 | SETTING PLAN FOR KEROSENE PRODUCT TRIM COOLER 019E0026 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040064 | 010-E-GAD-00022-001 | 010-E-GAD-00022-001 | SETTING PLAN FOR DESALTED CRUDE/KERO EXCHANGER 010E0007 A/B | A | 2018-04-26 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040065 | 011-E-DAT-00006-001 | 011-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 011E0004 LVGO PA COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040065 | 011-E-DAT-00007-001 | 011-E-DAT-00007-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 011E0009 TEMPERED WATR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00038-001 | 019-E-DAT-00038-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0014 PRODUCT STRIPPER OVERHEAD AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00039-001 | 019-E-DAT-00039-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0017 FRACTIONATOR OVERHEAD AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00040-001 | 019-E-DAT-00040-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0019 KEROSENE PRODUCT AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00042-001 | 019-E-DAT-00042-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0034 FRACTIONATOR BOTTOMS STARTUP AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00043-001 | 019-E-DAT-00043-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0033 UCO PRODUCT BLEED COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00044-001 | 019-E-DAT-00044-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0036 NAPHTHA STABILIZER OVERHEAD AIR COOLER | A | 2018-04-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00048-001 | 019-E-DAT-00048-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0051 BACKWASH OIL AIR COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040066 | 019-E-DAT-00049-001 | 019-E-DAT-00049-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 019E0045 MAKE-UP HYDROGEN SPILLBACK COOLER | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040067 | 019-C-DAT-00034-001 | 019-C-DAT-00034-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FLARE KO DRUM 019V0034 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00010-001 | 010-G-DAT-00010-001 | DATA SHEET FOR DESALTER WATER RECYCLE PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00011-001 | 010-G-DAT-00011-001 | MECHANICAL DATA SHEET ATMOSPHERIC COLUMN OVHD SOUR WATER PUMPS 010P0024 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00012-001 | 010-G-DAT-00012-001 | MECHANICAL DATA SHEET STABILIZER REFLUX PUMPS 010P0025 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00013-001 | 010-G-DAT-00013-001 | MECHANICAL DATA SHEET NAPHTHA SPLITTER REFLUX PUMPS 010P0027 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00014-001 | 010-G-DAT-00014-001 | MECHANICAL DATA SHEET SR HEAVY NAPHTHA PUMPS 010P0028 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00016-001 | 010-G-DAT-00016-001 | MECHANICAL DATA SHEET ATM COLUMN REFLUX PUMPS 010P0005 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-G-DAT-00017-001 | 010-G-DAT-00017-001 | MECHANICAL DATA SHEET KEROSENE PUMPS 010P0008 A/B | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040068 | 010-K-DAT-00002-001 | 010-K-DAT-00002-001 | DATA SHEET FOR STEAM TURBINE FOR ATM COLUMN REFLUX PUMP 010P0004B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00003-001 | 011-G-DAT-00003-001 | MECHANICAL DATA SHEET BSGO PUMPS 011P0007 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00004-001 | 011-G-DAT-00004-001 | MECHANICAL DATA SHEET RICH AMINE PUMPS 011P0008 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00005-001 | 011-G-DAT-00005-001 | MECHANICAL DATA SHEET LVGO PUMPS 011P0001 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00006-001 | 011-G-DAT-00006-001 | MECHANICAL DATA SHEET MVGO PUMPS 011P0002 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00007-001 | 011-G-DAT-00007-001 | MECHANICAL DATA SHEET VACUUM COLUMN SOUR WATER PUMPS 011P0006 A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00008-001 | 011-G-DAT-00008-001 | DATA SHEET FOR TEMPERED WATER PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-G-DAT-00009-001 | 011-G-DAT-00009-001 | DATA SHEET FOR WGO PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-K-DAT-00001-001 | 011-K-DAT-00001-001 | DATA SHEET FOR STEAM TURBINE FOR LVGO PUMPS 011P0002B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040069 | 011-K-DAT-00002-001 | 011-K-DAT-00002-001 | DATA SHEET FOR STEAM TURBINE TEMPERED WATER PUMPS 011P0008B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00011-001 | 019-G-DAT-00011-001 | MECHANICAL DATA SHEET NAPHTHA SLITTER REFLUX PUMP 019P0009A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00012-001 | 019-G-DAT-00012-001 | MECHANICAL DATA SHEET FRACTIONATOR OVERHEAD WATER PUMP 019P0014A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00014-001 | 019-G-DAT-00014-001 | MECHANICAL DATA SHEET HEAVY DIESEL STRIPPER BOTTOMS PUMP 019P0024A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00015-001 | 019-G-DAT-00015-001 | MECHANICAL DATA SHEET BACKWASH OIL PUMP 019P0031A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00016-001 | 019-G-DAT-00016-001 | MECHANICAL DATA SHEET VACUUM DRYER SLOP OIL PUMP 019P0032A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00017-001 | 019-G-DAT-00017-001 | MECHANICAL DATA SHEET VACUUM DRYER OILY WATER PUMP 019P0033A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00018-001 | 019-G-DAT-00018-001 | MECHANICAL DATA SHEET KEROSENE EXTERNAL REFLUX PUMP 019P0035A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00020-001 | 019-G-DAT-00020-001 | DATA SHEET FOR BFW CIRCULATION PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00021-001 | 019-G-DAT-00021-001 | MECHANICAL DATA SHEET RAW FEED BOOSTER PUMP 019P0001A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00022-001 | 019-G-DAT-00022-001 | MECHANICAL DATA SHEET KEROSENE PRODUCT PUMP 019P0006A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00023-001 | 019-G-DAT-00023-001 | MECHANICAL DATA SHEET HEAVY DIESEL PRODUCT PUMP 019P0011A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-G-DAT-00024-001 | 019-G-DAT-00024-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER REFLUX PUMP 019P0012A/B | A | 2018-05-09 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040070 | 019-K-DAT-00004-001 | 019-K-DAT-00004-001 | DATA SHEET FOR STEAM TURBINE FOR PRODUCT STRIPPER PUMPS 019P0004B 019T0004B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040071 | 050-G-DAT-55002-001 | 050-G-DAT-55002-001 | DATA SHEET FOR 3HDU DIESEL FEED PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 1
CON-BMP-TRA-040071 | 050-G-DAT-55003-001 | 050-G-DAT-55003-001 | DATA SHEET FOR 2HCU HVGOFEED PUMPS | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 1
CON-BMP-TRA-040071 | 050-K-DAT-55005-001 | 050-K-DAT-55005-001 | DATA SHEET FOR STEAM TURBINE FOR 3HDU DIESEL FEED PUMPS 050P0035A/B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 1
CON-BMP-TRA-040071 | 050-K-DAT-55006-001 | 050-K-DAT-55006-001 | DATA SHEET FOR STEAM TURBINE FOR 2HCU HVGO FEED PUMPS 050P0036A/B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 1
CON-BMP-TRA-040072 | 372-G-DAT-57003-001 | 372-G-DAT-57003-001 | MECHANICAL DATA SHEET UTILITY WATER PUMPS 372P3732A/B | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040074 | 011-G-DAT-00002-001 | 011-G-DAT-00002-001 | MECHANICAL DATA SHEET VACUUM RESIDUE PUMPS 01P0006A/B | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040075 | 085-S-DAT-00014-001 | 085-S-DAT-00014-001 | MECHANICAL DATA SHEET BMP MAIN CW SIDE STREAM FILTERS PACKAGE 085U0002 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040075 | 085-S-DAT-00015-001 | 085-S-DAT-00015-001 | MECHANICAL DATA SHEET BMP SECONDARY CW SIDE STREAM FILTERS PACKAGE 085U0003 | A | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-040076 | 012-S-DAT-00001-001 | 012-S-DAT-00001-001 | MECHANICAL DATA SHEET LPG MERCAPTANS REMOVAL AND OLEFIN SATURATION PACKAGE 012U0001 / 017U0001 | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-001 | 085-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM CALCITE BEDS PACKAGE | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-002 | 085-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BMP MAIN COOLING WATER SYSTEM | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-003 | 085-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM BMP MAIN COOLING WATER SYSTEM | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-004 | 085-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM BMP SECONDARY COOLING WATER SYSTEM | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-005 | 085-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM SIDE STREAM FILTER PACKAGE | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-006 | 085-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM CW CHEMICAL TREATMENT | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-007 | 085-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM BMP MAIN COOLING WATER DISTRIBUTION | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040077 | 085-A-MSD-00001-008 | 085-A-MSD-00001-008 | MATERIAL SELECTION DIAGRAM BMP SECONDARY COOLING WATER DISTRIBUTION | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00018-001 | 010-E-GAD-00018-001 | SETTING PLAN 010E0001 A/B CRUDE/KERO EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00019-001 | 010-E-GAD-00019-001 | SETTING PLAN 010E0003 A/B CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00020-001 | 010-E-GAD-00020-001 | SETTING PLAN 010E0004 A/B/C/D CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00021-001 | 010-E-GAD-00021-001 | SETTING PLAN 010E0006 A/B DESALTED CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00023-001 | 010-E-GAD-00023-001 | SETTING PLAN 010E0008 A/B/C/D DESALTED CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00026-001 | 010-E-GAD-00026-001 | SETTING PLAN 010E0020 KERO/DESALTER WATER FEED PREHEAT EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00027-001 | 010-E-GAD-00027-001 | SETTING PLAN 010E0022 KERO TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00028-001 | 010-E-GAD-00028-001 | SETTING PLAN 010E0032 SR HEAVY NAPHTHA TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040078 | 010-E-GAD-00029-001 | 010-E-GAD-00029-001 | SETTING PLAN 010E0030 LIGHT NAPHTHA COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00018-001 | 010-E-DAT-00018-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0001 A/B CRUDE/KERO EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00019-001 | 010-E-DAT-00019-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0003 A/B CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00020-001 | 010-E-DAT-00020-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0004 A/B/C/D CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00021-001 | 010-E-DAT-00021-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0006 A/B DESALTED CRUDE/DIESEL EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00022-001 | 010-E-DAT-00022-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0007 A/B DESALTED CRUDE/KERO EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00023-001 | 010-E-DAT-00023-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0008 A/B/C/D DESALTED CRUDE/KERO PA EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00026-001 | 010-E-DAT-00026-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0020 KERO/DESALTER WATER FEED PREHEAT EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00027-001 | 010-E-DAT-00027-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0022 KERO TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00028-001 | 010-E-DAT-00028-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0032 SR HEAVY NAPHTHA TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040079 | 010-E-DAT-00029-001 | 010-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 010E0030 LIGHT NAPHTHA COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040080 | 011-E-DAT-00003-001 | 011-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0005 A/B MVGO/HVGO COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040080 | 011-E-DAT-00004-001 | 011-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0007 A/B/C/D VACUUM RESIDUE COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040080 | 011-E-DAT-00005-001 | 011-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 011E0010 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040081 | 011-E-GAD-00003-001 | 011-E-GAD-00003-001 | SETTING PLAN 011E0005 A/B MVGO/HVGO COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040081 | 011-E-GAD-00004-001 | 011-E-GAD-00004-001 | SETTING PLAN 011E0007 A/B/C/D VACUUM RESIDUE COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040081 | 011-E-GAD-00005-001 | 011-E-GAD-00005-001 | SETTING PLAN 011E0010 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00029-001 | 019-E-DAT-00029-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0001 KEROSENE PRODUCT/FRESH FEED EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00030-001 | 019-E-DAT-00030-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0018 KEROSENE STRIPPER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00031-001 | 019-E-DAT-00031-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0052 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00033-001 | 019-E-DAT-00033-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0040 NAPHTA SPLITTER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00034-001 | 019-E-DAT-00034-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0042 HEAVY NAPHTA PRODUCT TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00035-001 | 019-E-DAT-00035-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0024 LIGHT DIESEL / BFW EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040082 | 019-E-DAT-00037-001 | 019-E-DAT-00037-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 019E0021 LIGHT DIESEL P/A MP STEAM GENERATOR | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040083 | 010-G-DAT-00018-001 | 010-G-DAT-00018-001 | MECHANICAL DATA SHEET RECOVERED PROCESS SLOP OIL SUMP PUMP 010P0018 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040083 | 010-G-DAT-00019-001 | 010-G-DAT-00019-001 | MECHANICAL DATA SHEET SOUR WATER SUMP PUMP 010P0017 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00013-001 | 019-G-DAT-00013-001 | MECHANICAL DATA SHEET FOR NAPHTA STABILIZER REFLUX PUMP 019P0018 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00025-001 | 019-G-DAT-00025-001 | MECHANICAL DATA SHEET FOR RECOVERED PROCESS SLOP OIL SUMP PUMP 019P0026 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00026-001 | 019-G-DAT-00026-001 | MECHANICAL DATA SHEET FOR AMINE SUMP PUMP 019P0027 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040084 | 019-G-DAT-00027-001 | 019-G-DAT-00027-001 | MECHANICAL DATA SHEET FOR SOUR WATER SUMP PUMP 019P0028 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040085 | 050-G-DAT-55004-001 | 050-G-DAT-55004-001 | MECHANICAL DATA SHEET FOR 7CDU FEED BOOSTER PUMPS 010P0031 A/B | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00029-001 | 019-E-GAD-00029-001 | SETTING PLAN 019E0001 KEROSENE PRODUCT / FRESH FEED EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00030-001 | 019-E-GAD-00030-001 | SETTING PLAN 019E0018 KEROSENE STRIPPER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00031-001 | 019-E-GAD-00031-001 | SETTING PLAN 019E0052 STEAM BLOWDOWN COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00033-001 | 019-E-GAD-00033-001 | SETTING PLAN 019E0040 NAPHTA SPLITTER REBOILER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00034-001 | 019-E-GAD-00034-001 | SETTING PLAN 019E0042 HEAVY NAPHTA PRODUCT TRIM COOLER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00035-001 | 019-E-GAD-00035-001 | SETTING PLAN 019E0024 LIGHT DIESEL / BFW EXCHANGER | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040086 | 019-E-GAD-00037-001 | 019-E-GAD-00037-001 | SETTING PLAN 019E0021 LIGHT DIESEL P/A MP STEAM GENERATOR | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040088 | 011-K-DAT-00004-001 | 011-K-DAT-00004-001 | DATA SHEET FOR STEAM TURBINE FOR VACUUM RESIDUE PUMPS 011P0006 B | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-040089 | 085-G-DAT-00003-001 | 085-G-DAT-00003-001 | MECHANICAL DATA SHEET BACKWASH WATER PUMPS 085P0003A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040089 | 085-G-DAT-00004-001 | 085-G-DAT-00004-001 | MECHANICAL DATA SHEET BACKWASH WATER PUMPS 085P0004A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040090 | 019-C-DAT-00025-001 | 019-C-DAT-00025-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STEAM DRUM 019V0025 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040090 | 019-C-DAT-00031-001 | 019-C-DAT-00031-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR STEAM BLOWDOWN DRUM 019V0031 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040090 | 019-C-DAT-10011-001 | 019-C-DAT-10011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR VACUUM DRYER 019C0011 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00005-001 | 019-K-DAT-00005-001 | MECHANICAL DATA SHEET PRODUCT STRIPPER BOTTOM PUMPS 019P0005 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00006-001 | 019-K-DAT-00006-001 | MECHANICAL DATA SHEET FRACTIONATOR BOTTOM PUMPS 019P0017 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00007-001 | 019-K-DAT-00007-001 | MECHANICAL DATA SHEET LIGHT DIESEL PUMPAROUND PUMPS 019P0010 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00008-001 | 019-K-DAT-00008-001 | MECHANICAL DATA SHEET FRACTIONATOR NAPHTHA PUMPS 019P0006 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040091 | 019-K-DAT-00009-001 | 019-K-DAT-00009-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR HEAVY DIESEL PUMPAROUND PUMPS 019P0012B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040092 | 085-K-DAT-00001-001 | 085-K-DAT-00001-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR MAIN COOLING WATER CIRCULATING PUMPS 085P0001 A/B/C | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040092 | 085-K-DAT-00002-001 | 085-K-DAT-00002-001 | MECHANICAL DATA SHEET STEAM TURBINE FOR SECONDARY COOLING WATER CIRCULATING PUMPS 085P0002 A | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00006-001 | 011-C-DAT-00006-001 | MECHANICAL DATA SHEET LVGO COLD REFLUX FILTERS 011V0002 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00007-001 | 011-C-DAT-00007-001 | MECHANICAL DATA SHEET LVGO HOT REFLUX FILTERS 011V0003 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00008-001 | 011-C-DAT-00008-001 | MECHANICAL DATA SHEET HVGO HOT REFLUX FILTERS 011V0005 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040093 | 011-C-DAT-00009-001 | 011-C-DAT-00009-001 | MECHANICAL DATA SHEET LVGO HOT REFLUX FILTERS 011V0004 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040094 | 010-C-DAT-00012-001 | 010-C-DAT-00012-001 | MECHANICAL DATA SHEET CRUDE FEED FILTERS 010V0001 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040094 | 010-C-DAT-00016-001 | 010-C-DAT-00016-001 | MECHANICAL DATA SHEET DESALTED CRUDE FILTERS 010V0004 A/B | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00005-001 | 010-C-GAD-00005-001 | GENERAL ARRANGEMENT 010V0005 PRE FLASH DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00007-001 | 010-C-GAD-00007-001 | GENERAL ARRANGEMENT 010V0007 OVERHEAD PRODUCT ACCUMULATOR | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00008-001 | 010-C-GAD-00008-001 | MECHANICAL DRAWING FOR 010V0008 COMPRESSOR K.O. DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00009-001 | 010-C-GAD-00009-001 | MECHANICAL DRAWING FOR 010V0009 COMPRESSOR INTERSTAGE K.O. DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00010-001 | 010-C-GAD-00010-001 | GENERAL ARRANGEMENT 010V0010 STABILIZER REFLUX DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00011-001 | 010-C-GAD-00011-001 | MECHANICAL DRAWING FOR 010V0011 NAPHTHA SPLITTER REFLUX DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00012-001 | 010-C-GAD-00012-001 | MECHANICAL DRAWING FOR 010V0012 DESALTER WATER SURGE DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00013-001 | 010-C-GAD-00013-001 | MECHANICAL DRAWING FOR 010V0013 SOUR WATER SUMP | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00014-001 | 010-C-GAD-00014-001 | MECHANICAL DRAWING FOR 010V0014 RECOVERED PROCESS SLOP OIL SUMP | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040095 | 010-C-GAD-00016-001 | 010-C-GAD-00016-001 | MECHANICAL DRAWING FOR 010V0016 FUEL GAS KO DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00001-001 | 011-C-GAD-00001-001 | MECHANICAL DRAWING FOR VACUUM HOT WELL 011V0001 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00006-001 | 011-C-GAD-00006-001 | MECHANICAL DRAWING FOR HOTWELL VAPOR WATER SEAL DRUM 011V0006 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00007-001 | 011-C-GAD-00007-001 | MECHANICAL DRAWING FOR SWEET TAIL GAS KO DRUM 011V0007 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00008-001 | 011-C-GAD-00008-001 | MECHANICAL DRAWING FOR TEMPERED WATER DRUM 011V0008 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00009-001 | 011-C-GAD-00009-001 | MECHANICAL DRAWING FOR STEAM DRUM 011V0009 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040096 | 011-C-GAD-00010-001 | 011-C-GAD-00010-001 | MECHANICAL DRAWING FOR BLOWDOWN FLUSH DRUM 011V0010 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00001-001 | 019-C-GAD-00001-001 | GENERAL ARRANGEMENT 019V0001 RAW FEED SURGE DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00002-001 | 019-C-GAD-00002-001 | MECHANICAL DRAWING FOR 1ST STAGE FEED SURGE DRUM 019V0002 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00007-001 | 019-C-GAD-00007-001 | GENERAL ARRANGEMENT 019V0007 2ND STAGE FEED SURGE DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00012-001 | 019-C-GAD-00012-001 | GENERAL ARRANGEMENT 019V0012 PRODUCT SPLITTER REFLUX DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00013-001 | 019-C-GAD-00013-001 | MECHANICAL DRAWING FOR FRACTIONATOR REFLUX DRUM 019V0013 | A | 2018-05-03 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00015-001 | 019-C-GAD-00015-001 | MECHANICAL DRAWING FOR NAPHTA SPLITTER REFLUX DRUM 019V0015 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00016-001 | 019-C-GAD-00016-001 | MECHANICAL DRAWING FOR NAPHTA SPLITTER REBOILER CONDENSATE POT 019V0016 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00017-001 | 019-C-GAD-00017-001 | MECHANICAL DRAWING FOR VACUUM DRYER HOTWELL 019V0017 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00018-001 | 019-C-GAD-00018-001 | GENERAL ARRANGEMENT 019V0018 MAKE-UP HYDROGEN FIRST STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00019-001 | 019-C-GAD-00019-001 | GENERAL ARRANGEMENT 019V0019 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00020-001 | 019-C-GAD-00020-001 | GENERAL ARRANGEMENT 019V0020 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00021-001 | 019-C-GAD-00021-001 | GENERAL ARRANGEMENT 019V0021 MAKE-UP HYDROGEN SECOND STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00022-001 | 019-C-GAD-00022-001 | GENERAL ARRANGEMENT 019V0022 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00023-001 | 019-C-GAD-00023-001 | GENERAL ARRANGEMENT 019V0023 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00024-001 | 019-C-GAD-00024-001 | GENERAL ARRANGEMENT 019V0024 MAKE-UP HYDROGEN THIRD STAGE SUCTION DRUM | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00025-001 | 019-C-GAD-00025-001 | MECHANICAL DRAWING FOR STEAM DRUM 019V0025 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00026-001 | 019-C-GAD-00026-001 | MECHANICAL DRAWING FOR LEAN AMINE SURGE DRUM 019V0026 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00027-001 | 019-C-GAD-00027-001 | MECHANICAL DRAWING FOR INJECTION WATER DRUM 019V0027 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00030-001 | 019-C-GAD-00030-001 | MECHANICAL DRAWING FOR BACKWASH OIL SURGE DRUM 019V0030 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00031-001 | 019-C-GAD-00031-001 | MECHANICAL DRAWING FOR STEAM BLOWDOWN DRUM 019V0031 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00032-001 | 019-C-GAD-00032-001 | MECHANICAL DRAWING FOR FUEL GAS KO DRUM 019V0032 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00033-001 | 019-C-GAD-00033-001 | MECHANICAL DRAWING FOR PROCESS GAS KO DRUM 019V0033 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00036-001 | 019-C-GAD-00036-001 | MECHANICAL DRAWING FOR RECOVERED PROCESS SLOP OIL SUMP 019V0036 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00037-001 | 019-C-GAD-00037-001 | MECHANICAL DRAWING FOR AMINE SUMP 019V0037 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-00038-001 | 019-C-GAD-00038-001 | MECHANICAL DRAWING FOR SOUR WATER SUMP 019V0038 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040097 | 019-C-GAD-10011-001 | 019-C-GAD-10011-001 | MECHANICAL DRAWING FOR VACUUM DRYER 019C0011 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00011-001 | 019-C-DAT-00011-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR COLD LOW PRESSURE SEPARATOR 019V0011 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00014-001 | 019-C-DAT-00014-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR NAPHTHA STABILIZER REFLUX DRUM 019V0014 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00028-001 | 019-C-DAT-00028-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RICH AMINE FLASH DRUM 019V0028 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040098 | 019-C-DAT-00029-001 | 019-C-DAT-00029-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SOUR WATER FLASH DRUM 019V0029 | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-040099 | 011-S-DAT-00001-001 | 011-S-DAT-00001-001 | MECHANICAL DATA SHEET PHOPSPHATE INJECTION PACKAGE 011U0002 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00001-001 | 010-S-DAT-00001-001 | MECHANICAL DATA SHEET NEUTRALIZING AMINE INJECTION PACKAGE 010U0002 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00002-001 | 010-S-DAT-00002-001 | MECHANICAL DATA SHEET FILMING AMINE INJECTION PACKAGE 010U0003 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00003-001 | 010-S-DAT-00003-001 | MECHANICAL DATA SHEET ANTIFOAMING INJECTION PACKAGE 010U0005 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040100 | 010-S-DAT-00004-001 | 010-S-DAT-00004-001 | MECHANICAL DATA SHEET DEMULSIFIER INJECTION PACKAGE 010U0004 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-001 | 372-D-GAD-57079-001 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-002 | 372-D-GAD-57079-002 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-003 | 372-D-GAD-57079-003 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040101 | 372-D-GAD-57079-004 | 372-D-GAD-57079-004 | GENERAL ARRANGEMENT 372D0079 FEED STORAGE TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-001 | 050-D-GAD-55001-001 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-002 | 050-D-GAD-55001-002 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-003 | 050-D-GAD-55001-003 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55001-004 | 050-D-GAD-55001-004 | GENERAL ARRANGEMENT 050D00001 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-001 | 050-D-GAD-55002-001 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-04-25 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-002 | 050-D-GAD-55002-002 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-003 | 050-D-GAD-55002-003 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55002-004 | 050-D-GAD-55002-004 | GENERAL ARRANGEMENT 050D00002 A/B CRUDE OIL TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-001 | 050-D-GAD-55003-001 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-002 | 050-D-GAD-55003-002 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-003 | 050-D-GAD-55003-003 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55003-004 | 050-D-GAD-55003-004 | GENERAL ARRANGEMENT 050D00003 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-001 | 050-D-GAD-55004-001 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-002 | 050-D-GAD-55004-002 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-003 | 050-D-GAD-55004-003 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040102 | 050-D-GAD-55004-004 | 050-D-GAD-55004-004 | GENERAL ARRANGEMENT 050D00004 1 RHCU FEED TANK | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00001-001 | 085-S-DAT-00001-001 | MECHANICAL DATA SHEET OXIDIZING BIOCIDE DOSING PACKAGE 085U0004 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00002-001 | 085-S-DAT-00002-001 | MECHANICAL DATA SHEET ANTICALE DISPERSANT DOSING PACKAGE 085U0005 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00003-001 | 085-S-DAT-00003-001 | MECHANICAL DATA SHEET BIODISPERSANT DOSING PACKAGE 085U0006 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00004-001 | 085-S-DAT-00004-001 | MECHANICAL DATA SHEET CORROSION INHIBITOR DOSING PACKAGE 085U0007 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00005-001 | 085-S-DAT-00005-001 | MECHANICAL DATA SHEET SULPHURIC ACID DOSING PACKAGE 085U0007 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00006-001 | 085-S-DAT-00006-001 | MECHANICAL DATA SHEET SODIUM HYDROXIDE DOSING PACKAGE 085U0009 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00011-001 | 085-S-DAT-00011-001 | MECHANICAL DATA SHEET MAIN NON OXIDIZING BIOCIDE DOSING PACKAGE 085U0011 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040103 | 085-S-DAT-00016-001 | 085-S-DAT-00016-001 | MECHANICAL DATA SHEET SECONDARY NON OXIDIZING BIOCIDE DOSING PACKAGE 085U0012 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040104 | 010-G-DAT-00015-001 | 010-G-DAT-00015-001 | MECHANICAL DATA SHEET FLARE KO DRUM PUMPS 010P0019 A/B | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00001-001 | 019-S-DAT-00001-001 | MECHANICAL DATA SHEET ANTIFOAM INJECTION PACKAGE 019U0003 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00002-001 | 019-S-DAT-00002-001 | MECHANICAL DATA SHEET ANTISTATIC ADDITIVE PACKAGE 019U0005 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00003-001 | 019-S-DAT-00003-001 | MECHANICAL DATA SHEET PHOSPHATE INJECTION PACKAGE 019U0006 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040105 | 019-S-DAT-00004-001 | 019-S-DAT-00004-001 | MECHANICAL DATA SHEET ANTIOXIDANT ADDITIVE PACKAGE 019U0004 | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040106 | 085-C-DAT-00001-001 | 085-C-DAT-00001-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 085V0008 A/B | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040106 | 085-C-DAT-00002-001 | 085-C-DAT-00002-001 | MECHANICAL DATA SHEET INSTRUMENT AIR FILTER 085V0009 A/B | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-040107 | 010-P-STS-00001-001 | 010-P-STS-00001-001 | LOAD BALANCE N 7 CDU SUBSTATION SST010R01 | A | 2018-05-24 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-08 |  |  | CLASS 2
CON-BMP-TRA-070001 | 076551C-000S-DL-0113-001 | 000-F-IDL-80001-001 | DEVIATION LIST FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-ITP-0113-001 | 000-F-ITP-80001-001 | INSPECTION AND TEST PLAN FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-MR-0113-001 | 000-F-MRQ-80001-001 | MATERIAL REQUISITION FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-SP-0113-001 | 000-F-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | 076551C-000S-SR-0113-001 | 000-F-SOW-80001-001 | SCOPE OF SUPPLY FOR HYDROGEN PLANT STEAM REFORMER | AP | 2018-03-29 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800007-001 | 098-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 098F9800 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800008-001 | 098-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 098F9804 STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800009-001 | 098-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 098E9801 PROCESS GAS BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09800010-001 | 098-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 098F9801 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900007-001 | 099-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 099F9900 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900008-001 | 099-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 099F9904 STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900009-001 | 099-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 099E9901 PROCESS GAS BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070001 | SO6001-EJ1E-TDS-09900010-001 | 099-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 099F9901 REFORMING FURNACE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000004 CS REPLIED ON 13/04/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-DL-0119-004 | 000-F-IDL-80002-001 | DEVIATION LIST FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-ITP-0119-004 | 000-F-ITP-80002-001 | INSPECTION AND TEST PLAN FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-MR-0119-004 | 000-F-MRQ-80002-001 | MATERIAL REQUISITION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-SP-0119-004 | 000-F-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | 076551C-000S-SR-0119-004 | 000-F-SOW-80002-001 | SCOPE OF SUPPLY FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100007-001 | 041-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 041F4101 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100008-001 | 041-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 041V4103 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100009-001 | 041-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 041E4101 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04100010-001 | 041-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 041X4101 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200007-001 | 042-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 041F4201 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200008-001 | 042-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 042V4203 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200009-001 | 042-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 042E4201 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04200010-001 | 042-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 042X4201 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300007-001 | 043-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 043F4301 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300008-001 | 043-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 043V4303 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300009-001 | 043-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 043E4301 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070002 | SO6001-EJ1E-TDS-04300010-001 | 043-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 043X4301 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000001 | 2018-04-09 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-DL-0140-001 | 000-F-IDL-80003-001 | DEVIATION LIST FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-ITP-0140-001 | 000-F-ITP-80003-001 | INSPECTION AND TEST PLAN FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-MR-0140-001 | 000-F-MRQ-80003-001 | MATERIAL REQUISITION FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-SP-0140-001 | 000-F-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | 076551C-000S-SR-0140-001 | 000-F-SOW-80003-001 | SCOPE OF SUPPLY FOR INCINERATOR PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | SO6001-EJ1E-TDS-04400007-001 | 044-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 044U4401 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070003 | SO6001-EJ1E-TDS-04500007-001 | 045-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 045U4501 | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000002 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-DL-0150-001 | 000-F-IDL-80004-001 | DEVIATION LIST FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-ITP-0150-001 | 000-F-ITP-80004-001 | INSPECTION AND TEST PLAN FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-MR-0150-001 | 000-F-MRQ-80004-001 | MATERIAL REQUISITION FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-SP-0150-001 | 000-F-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | 076551C-000S-SR-0150-001 | 000-F-SOW-80004-001 | SCOPE OF SUPPLY FOR AUXILIARY STEAM BOILERS | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | SO6001-EJ1E-TDS-31000001-001 | 310-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 310F0001 AUXILIARY STEAM BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070004 | SO6001-EJ1E-TDS-31100001-001 | 311-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 311F0001 AUXILIARY STEAM BOILER | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000005 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-DL-0215-001 | 000-S-IDL-80002-001 | INSPECTION AND TEST PLAN FOR DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-ITP-0215-001 | 000-S-ITP-80002-001 | INSPECTION AND TEST PLAN FOR DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-MR-0215-001 | 000-S-MRQ-80002-001 | MATERIAL REQUISITION FOR MULTI EFFECT DESALINATION PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-SP-0215-001 | 000-S-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR MULTI EFFECT DESALINATION PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | 076551C-000S-SR-0215-001 | 000-S-SOW-80002-001 | SCOPE OF SUPPLY FOR MULTI EFFECT DESALINATION PACKAGE | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | SO6001-EJ2E-TDS-35600001-001 | 356-S-DAT-80002-001 | DUTY SPECIFICATION FOR 356U0001 NO6 DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | SO6001-EJ2E-TDS-35700001-001 | 357-S-DAT-80002-001 | DUTY SPECIFICATION FOR 356U0001 NO7 DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070005 | SO6001-EJ2E-TDS-35800001-001 | 358-S-DAT-80002-001 | DUTY SPECIFICATION FOR 356U0001 NO8 DESALINATION PLANT | AP | 2018-03-30 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-16 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000003 CS REPLIED ON 08/05/2018 | 2018-04-10 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-DL-4352-001 | 000-S-IDL-80010-001 | LIST OF DEVIATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000007 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-ITP-4352-001 | 000-S-ITP-80010-001 | INSPECTION AND TEST PLAN FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000007 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-MR-4352-001 | 000-S-MRQ-80010-001 | MATERIAL REQUISITION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000007 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-SP-4352-001 | 000-S-GRD-80010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000007 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | 076551C-000S-SR-4352-001 | 000-S-SOW-80010-001 | SCOPE OF SUPPLY FOR BMP SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000007 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070006 | SO6001-EJ2E-TDS-09400001-001 | 094-S-DAT-00001-001 | DUTY SPECIFICATION FOR SULPHUR SOLIDIFICATION PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000007 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-DL-4010-001 | 000-S-IDL-80003-001 | DEVIATION LIST FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000008 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-ITP-4010-001 | 000-S-ITP-80003-001 | INSPECTION AND TEST PLAN FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000008 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-MR-4010-001 | 000-S-MRQ-80003-001 | MATERIAL REQUISITION FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000008 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-SP-4010-001 | 000-S-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000008 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | 076551C-000S-SR-4010-001 | 000-S-SOW-80003-001 | SCOPE OF SUPPLY FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000008 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070007 | SO6001-EJ2E-TDS-09400002-001 | 094-S-DAT-00002-001 | DUTY SPECIFICATION FOR BMP SOLID SULPHUR HANDLING PACKAGE | AP | 2018-04-06 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-23 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000008 | 2018-04-17 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-DL-0710-002 | 000-E-IDL-80007-001 | DEVIATION LIST FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-ITP-0710-002 | 000-E-ITP-80007-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-MR-0710-002 | 000-E-MRQ-80007-001 | MATERIAL REQUISITION FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-SP-0710-002 | 000-E-GRD-80007-001 | PARTICULAR TECHNICAL SPEIFICATION FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | 076551C-000S-SR-0710-002 | 000-E-SOW-80007-001 | SCOPE OF SUPPLY FOR AIR COOLERS | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03600001-001 | 036-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 036E3611 REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03600002-001 | 036-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 036E3612 AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03700001-001 | 037-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 037E3711 REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-03700002-001 | 037-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 037E3712 AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04100001-001 | 041-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 041E4111 STEAM CONDENSER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04200001-001 | 042-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 042E4211 STEAM CONDENSER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04300001-001 | 043-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 043E4311 STEAM CONDENSER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400001-001 | 044-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4410 CONDENSATE AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400002-001 | 044-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4411 QUENCH WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400003-001 | 044-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET 044E4412 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400004-001 | 044-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4413 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400005-001 | 044-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4414 60# STEAM BLOWDOWN DRUM CONDENSER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04400006-001 | 044-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4415 STEAM CONDENSER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04500001-001 | 045-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4511 QUENCH WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04500002-001 | 045-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4512 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04500003-001 | 045-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4513 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04600001-001 | 046-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 046E4611 STRIPPER PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04600002-001 | 046-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 046E4612 STRIPPED WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04700001-001 | 047-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 047E4711 STRIPPER PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04700002-001 | 047-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 047E4712 STRIPPED WATER COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800001-001 | 048-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4811 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800002-001 | 048-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4812 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800003-001 | 048-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4813 ARU STEAM CONDENSER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04800004-001 | 048-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4814 ARU CONDENSATE AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04900001-001 | 049-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 049E4911 AMINE REGENERATOR PUMP AROUND COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-04900002-001 | 049-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 049E4912 LEAN AMINE COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-08800001-001 | 088-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 088E1931 KERO PRODUCT AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-09800001-001 | 098-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 098E9805 PROCESS GAS COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-09900001-001 | 099-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 099E9905 PROCESS GAS COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070008 | SO6001-EJ1E-TDS-37155001-001 | 371-E-DAT-55001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 371E0002 60 PSIG EXCESS STEAM CONDENSATE AIR COOLER | AP | 2018-04-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000011 | 2018-04-24 | CLASS 1
CON-BMP-TRA-070009 | SO6001-ES0B-PHL-35600001-001 | 356-A-BOD-00001-001 | BASIS OF DESIGN 6,7,8 DESAL (UNIT 356/357/358) N¿ 6,7,8 DESALINATION PLANTS | A | 2018-04-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000010 | 2018-04-23 | CLASS 1
CON-BMP-TRA-070010 | SO6001-ES0B-PHL-09400001-001 | 094-A-BOD-00001-001 | BASIS OF DESIGN 2SHF (UNIT 094) SULPHUR HANDLING FACILITY | A | 2018-04-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-04-25 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000009_CS REPLIED ON 18/05/2018 | 2018-04-23 | CLASS 1
CON-BMP-TRA-070011 | 076551C-000S-DL-0411-001 | 000-C-IDL-80004-001 | DEVIATION LIST FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-ITP-0411-001 | 000-C-ITP-80004-001 | INSPECTION AND TEST PLAN FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-MR-0411-001 | 000-C-MRQ-80004-001 | MATERIAL REQUISITION FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-SP-0411-001 | 000-C-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | 076551C-000S-SR-0411-001 | 000-C-SOW-80004-001 | SCOPE OF SUPPLY FOR REACTORS | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-01600001-001 | 016-C-GAD-00001-001 | 016C1640 MEROX REACTOR TRAIN C MISC-P1052-B2-LH | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04100002-001 | 041-C-GAD-00001-001 | 041C4101 NO.1 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04100003-001 | 041-C-GAD-00002-001 | 041C4102 NO.2 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04200002-001 | 042-C-GAD-00001-001 | 042C4201 NO.1 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04200003-001 | 042-C-GAD-00002-001 | 042C4202 NO.2 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04300002-001 | 043-C-GAD-00001-001 | 043C4301 NO.1 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04300003-001 | 043-C-GAD-00002-001 | 043C4302 NO.2 CONVERTER | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04400008-001 | 044-C-GAD-00001-001 | 044C4401 TAIL GAS REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-04500008-001 | 045-C-GAD-00001-001 | 045C4501 TAIL GAS REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09800002-001 | 098-C-GAD-00001-001 | 098C9801 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09800003-001 | 098-C-GAD-00002-001 | 098C9802 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09800004-001 | 098-C-GAD-00003-001 | 098C9803 HIGH TEMPERATURE SHIFT REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09900002-001 | 099-C-GAD-00001-001 | 099C9901 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09900003-001 | 099-C-GAD-00002-001 | 099C9902 ZINC OXIDE DRUM | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070011 | SO6001-EJ1E-TDS-09900004-001 | 099-C-GAD-00003-001 | 099C9903 HIGH TEMPERATURE SHIFT REACTOR | AP | 2018-04-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-04-30 | 4-NOT APPROVED BMP-SOC-TRE-000006 | 2018-04-17 | CLASS 2
CON-BMP-TRA-070012 | 076551C-000S-DL-4112-001 | 000-S-IDL-80008-001 | DEVIATION LIST FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-ITP-4112-001 | 000-S-ITP-80008-001 | INSPECTION AND TEST PLAN FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-MR-4112-001 | 000-S-MRQ-80008-001 | MATERIAL REQUISITION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-SP-4112-001 | 000-S-GRD-80008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | 076551C-000S-SR-4112-001 | 000-S-SOW-80008-001 | SCOPE OF SUPPLY FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-070012 | SO6001-EJ2E-TDS-08300001-001 | 083-S-DAT-00001-001 | DUTY SPECIFICATION FOR 083U0001 NITROGEN PLANT | AP | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-02 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000012 | 2018-04-25 | CLASS 1
CON-BMP-TRA-070013 | SO6001-ES0B-PHL-00500001-001 | 005-A-BOD-00001-001 | BASIS OF DESIGN RLPG (UNIT 005) LPG C3-C4 STORAGE FACILITY AT REFINERY | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000014 | 2018-04-27 | CLASS 1
CON-BMP-TRA-070014 | SO6001-ES0B-PHL-09800001-001 | 098-A-BOD-00001-001 | BASIS OF DESIGN 3H2,4H2 PLANT (UNIT 098,099) NO.3 NO.4 HYDROGEN PLANT | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00013 - CS REPLIED ON 03/05/18 | 2018-04-26 | CLASS 1
CON-BMP-TRA-070015 | SO6001-ES0B-PHL-34100001-001 | 341-A-BOD-00001-001 | BASIS OF DESIGN 2IAS (UNIT 341) AIR VOMPRESSOR AND DRYERS | A | 2018-04-16 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-03 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000015 | 2018-04-27 | CLASS 1
CON-BMP-TRA-070016 | SO6001-ES0B-PHL-37155001-001 | 371-A-BOD-55001-001 | BASIS OF DESIGN STM G AND D (UNIT 371) STEAM GENERATION AND DISTRIBUTION | A | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS - BMP-TRA-070016 | 2018-04-30 | CLASS 1
CON-BMP-TRA-070017 | SO6001-ES0B-PHL-37254001-001 | 372-A-BOD-54001-001 | BASIS OF DESIGN 2 BFW AND COND(UNIT 372) BOILER FEED WATER ANDCONDENSATE DISTRIBUTION | A | 2018-04-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-07 | 3-REVIEWED WITH COMMENTS - BMP-TRA-070017 | 2018-04-30 | CLASS 1
CON-BMP-TRA-070018 | SO6001-ES0D-PFD-01600001-001 | 016-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TRAIN A AND B - (KERO MEROX OFFPLOT FACILITIES) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000032 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070018 | SO6001-ES0D-PFD-01600001-002 | 016-A-PFD-00001-002 | PROCESS FLOW DIAGRAM TRAIN C (KERO MEROX OFFPLOT FACILITIES) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000032 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070019 | SO6001-ES0D-MSD-00500001-001 | 005-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM C3 STORAGE BULLETS AND PUMPS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENTS - BMP-SOC-TRE-000041 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070019 | SO6001-ES0D-MSD-00500001-002 | 005-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM C4 STORAGE BULLETS AND PUMPS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENTS - BMP-SOC-TRE-000041 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070019 | SO6001-ES0D-MSD-00500001-003 | 005-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM OFF SPEC AND SPARE LPG BULLETS AND OFF SPEC LPG PUMPS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENTS - BMP-SOC-TRE-000041 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070020 | SO6001-ES0D-MSD-01600001-001 | 016-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MEROX PROCESS UNIT - TRAIN A AND B (KERO MEROX OFFPLOT FACILITIES) | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000040 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070020 | SO6001-ES0D-MSD-01600001-002 | 016-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM MEROX PROCESS UNIT TRAIN C | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000040 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070020 | SO6001-ES0D-MSD-01600001-003 | 016-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM MEROX PROCESS UNIT | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000040 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-001 | 041-A-PFD-00001-001 | PROCESS FLOW DIAGRAM ACID/ SWS OFF GAS KO DRUM & PUMP SECTION (#5SRU, #6SRU, #7SU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000020 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-002 | 041-A-PFD-00001-002 | PROCESS FLOW DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000020 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-003 | 041-A-PFD-00001-003 | PROCESS FLOW DIAGRAM SULPHUR DEGASSING AND STORAGE (#5SRU, #6SRU, #7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000020 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-004 | 041-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000020 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-005 | 041-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000020 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070021 | SO6001-ES0D-PFD-04100001-006 | 041-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#5SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000020 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-001 | 042-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000021 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-002 | 042-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000021 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-003 | 042-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000021 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070022 | SO6001-ES0D-PFD-04200001-004 | 042-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#6SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000021 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-001 | 043-A-PFD-00001-001 | PROCESS FLOW DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000022 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-002 | 043-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000022 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-003 | 043-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000022 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070023 | SO6001-ES0D-PFD-04300001-004 | 043-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#7SRU) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000022 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070024 | SO6001-ES0D-MSD-31000001-001 | 310-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HP STEAM BOILER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENTS - BMP-SOC-TRE-000044 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070024 | SO6001-ES0D-MSD-31000001-002 | 310-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BLOWDOWN | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENTS - BMP-SOC-TRE-000044 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070024 | SO6001-ES0D-MSD-31000001-003 | 310-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM PHOSPHATE INJECTION PACKAGE | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENTS - BMP-SOC-TRE-000044 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070025 | SO6001-ES0D-MSD-31100001-001 | 311-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM HP STEAM BOILER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENT - BMP-SOC-TRE-000043 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070025 | SO6001-ES0D-MSD-31100001-002 | 311-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BLOWDOWN | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVEIWED WITH MINOR COMMENT - BMP-SOC-TRE-000043 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070026 | SO6001-ES0D-PFD-04600001-001 | 046-A-PFD-00001-001 | PROCESS FLOW DIAGRAM NON PHENOLIC SOUR WATER UNIT (#5SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070026 | SO6001-ES0D-PFD-04600001-002 | 046-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE WATER UNIT (#5SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070026 | SO6001-ES0D-PFD-04600001-003 | 046-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE WATER UNIT (#5SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070027 | SO6001-ES0D-PFD-04700001-001 | 047-A-PFD-00001-001 | PROCESS FLOW DIAGRAM PHENOLIC SOUR STRIPPER UNIT (#6SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000019 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070027 | SO6001-ES0D-PFD-04700001-002 | 047-A-PFD-00001-002 | PROCESS FLOW DIAGRAM PHENOLIC SOUR STRIPPER UNIT (#6SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000019 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070027 | SO6001-ES0D-PFD-04700001-003 | 047-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT(#6SWS) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000019 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070028 | SO6001-ES0D-MSD-38200001-001 | 382-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM OILY WATER BASIN, CONTAMINED STORM WATER SURGE BASIN AND CLEAN SEWER BASIN | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000042 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070028 | SO6001-ES0D-MSD-38200001-002 | 382-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM SANITARY BASINS | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000042 | 2018-05-10 | CLASS 2
CON-BMP-TRA-070029 | SO6001-EJ1E-TDS-04100004-001 | 041-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E4102 NO.1 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00035 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070029 | SO6001-EJ1E-TDS-04100005-001 | 041-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E4103 NO.2 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00035 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070029 | SO6001-EJ1E-TDS-04100006-001 | 041-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 041E4104 NO.3 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00035 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070030 | SO6001-ES0D-PFD-08300001-001 | 083-A-PFD-00001-001 | PROCESS FLOW DIAGRAM NITROGEN SYSTEM BLOCK FLOW DIAGRAM | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000024 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070031 | SO6001-ES0D-PFD-08700001-001 | 087-A-PFD-00001-001 | PROCESS FLOW DIAGRAM LSFO COOLING TOWER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000031 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070031 | SO6001-ES0D-PFD-08700001-002 | 087-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000031 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070031 | SO6001-ES0D-PFD-08700001-003 | 087-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000031 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070032 | SO6001-ES0D-PFD-08800001-001 | 088-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KERO RERUN UNIT (EX BRB-229600 SH 01) | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000025 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070032 | SO6001-ES0D-PFD-08800001-002 | 088-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000025 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070033 | SO6001-EJ1E-TDS-04200004-001 | 042-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E4202 NO.1 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00034 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070033 | SO6001-EJ1E-TDS-04200005-001 | 042-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E4203NO.2 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00034 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070033 | SO6001-EJ1E-TDS-04200006-001 | 042-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E4204 NO.3 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00034 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070034 | SO6001-EJ1E-TDS-04300004-001 | 043-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E4302 NO.1 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00036 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070034 | SO6001-EJ1E-TDS-04300005-001 | 043-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E4303 NO.2 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00036 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070034 | SO6001-EJ1E-TDS-04300006-001 | 043-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 043E4304 NO.3 SULPHUR CONDENSER | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00036 CS REPLIED ON 21/05/2018 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070035 | SO6001-EJ2E-TDS-34100001-001 | 341-S-DAT-00001-001 | DATASHHET FOR AIR DRYERS PACKAGE 341U0140A/B PLANT NO.: 341 MATERIAL CLASSIFICATION LETTER:S | A | 2018-04-27 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-16 | 4-NOT APPROVED - BMP-SOC-TRE-00038 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-001 | 094-A-PFD-00001-001 | PROCESS FLOW DIAGRAM 2SHF SULPHUR HANDLING FACILITIES STORAGE TANK/ PRECONDITIONER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-002 | 094-A-PFD-00001-002 | PROCESS FLOW DIAGRAM 2SHF SULPHUR HANDLING FACILITIES PELLETIZER/ COOLING/ LOADING | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-003 | 094-A-PFD-00001-003 | PROCESS FLOW DIAGRAM EXISTING SULPHUR HANDLING FACILITIES STORAGE TANK/ PRECONDITIONER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-004 | 094-A-PFD-00001-004 | PROCESS FLOW DIAGRAM PROPOSAL FOR SULPHUR STORAGE TANK OPTION WHEN SHF TANK D9600 IS OUT OF SERVICE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-005 | 094-A-PFD-00001-005 | PROCESS FLOW DIAGRAM EXISTING SULPHUR HANDLING FACILITIES PELLETIZER/ COOLING/ LOADING | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-006 | 094-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070036 | SO6001-ES0D-PFD-09400001-007 | 094-A-PFD-00001-007 | PROCESS FLOW DIAGRAM 2SHF NEUTRALIZATION FACILITY | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000023 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-001 | 098-A-PFD-00001-001 | PROCESS FLOW DIAGRAM FEED DESULPHURISATION AND REFORMING | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-002 | 098-A-PFD-00001-002 | PROCESS FLOW DIAGRAM PROCESS GAS BOILER AND HTS REACTOR | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-003 | 098-A-PFD-00001-003 | PROCESS FLOW DIAGRAM PROCESS GAS BOILER AND HTS REACTOR | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-004 | 098-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-005 | 098-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-006 | 098-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-007 | 098-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE TURNDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-008 | 098-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE TURNDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-009 | 098-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE TURNDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-010 | 098-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE MIXED FUEL | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070037 | SO6001-ES0D-PFD-09800001-011 | 098-A-PFD-00001-011 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE MIXED FUEL | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 1-APPROVED BMP-SOC-TRE-000018 | 2018-05-04 | CLASS 1
CON-BMP-TRA-070038 | SO6001-ES0B-PHL-03600001-001 | 036-A-BOD-00001-001 | BASIS OF DESIGN (UNIT 036,037,041,042,043,044,045,046,047,048,049) NO.3 SULPHUR PLANT | A | 2018-04-27 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000046 | 2018-05-11 | CLASS 1
CON-BMP-TRA-070039 | SO6001-EJ2E-TDS-34100002-001 | 341-K-DAT-00001-001 | DATASHEET FOR INTEGRALLY GEARED CENTRIFUGAL COMPRESSORS FOR 341K 3415 A-B-C-D AIR COMPRESSORS | A | 2018-05-02 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-17 | 4-NOT APPROVED - BMP-SOC-TRE-00033 | 2018-05-09 | CLASS 2
CON-BMP-TRA-070040 | SO6001-ES0D-PFD-38200001-001 | 382-A-PFD-00001-001 | PROCESS FLOW DIAGRAM OILY WATER BASIN, CONTAMINED STORM WATER SURGE BASIN AND CLEAN WATER BASIN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000028 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070040 | SO6001-ES0D-PFD-38200001-002 | 382-A-PFD-00001-002 | PROCESS FLOW DIAGRAM SANITARY BASINS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000028 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070040 | SO6001-ES0D-PFD-38200001-003 | 382-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000028 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-001 | 005-A-PFD-00001-001 | PROCESS FLOW DIAGRAM C3 STORAGE BULLETS AND PUMPS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000027 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-002 | 005-A-PFD-00001-002 | PROCESS FLOW DIAGRAM C4 STORAGE BULLETS AND PUMPS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000027 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-003 | 005-A-PFD-00001-003 | PROCESS FLOW DIAGRAM OFF SPEC AND SPARE LPG BULLETS AND OFF SPEC LPG PUMPS | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000027 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070041 | SO6001-ES0D-PFD-00500001-004 | 005-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000027 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-001 | 310-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HP STEAM BOILER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-002 | 310-A-PFD-00001-002 | PROCESS FLOW DIAGRAM BLOWDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-003 | 310-A-PFD-00001-003 | PROCESS FLOW DIAGRAM PHOSPHATE INJECTION PACKAGE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070042 | SO6001-ES0D-PFD-31000001-004 | 310-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 |  |  | CLASS 1
CON-BMP-TRA-070043 | SO6001-ES0D-PFD-31100001-001 | 311-A-PFD-00001-001 | PROCESS FLOW DIAGRAM HP STEAM BOILER | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000029 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070043 | SO6001-ES0D-PFD-31100001-002 | 311-A-PFD-00001-002 | PROCESS FLOW DIAGRAM BLOWDOWN | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000029 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070043 | SO6001-ES0D-PFD-31100001-003 | 311-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-11 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000029 | 2018-05-08 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-001 | 341-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000037 | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-002 | 341-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000037 | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-003 | 341-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000037 | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-004 | 341-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000037 | 2018-05-09 | CLASS 1
CON-BMP-TRA-070044 | SO6001-ES0D-PFD-34100001-005 | 341-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-16 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000037 | 2018-05-09 | CLASS 1
CON-BMP-TRA-070045 | SO6001-ES0D-PFD-37800001-001 | 378-A-PFD-00001-001 | PROCESS FLOW DIAGRAM SALT WATER SYSTEM | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-30 |  |  | CLASS 1
CON-BMP-TRA-070045 | SO6001-ES0D-PFD-37800001-002 | 378-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-04-24 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-30 |  |  | CLASS 1
CON-BMP-TRA-070046 | SO6001-ES0B-PHL-08300001-001 | 083-A-BOD-00001-001 | BASIS OF DESIGN FOR NITROGEN PLANT (UNIT 083) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-14 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000026 | 2018-05-06 | CLASS 1
CON-BMP-TRA-070047 | SO6001-ES0B-PHL-38200001-001 | 382-A-BOD-00001-001 | BASIS OF DESIGN FOR SEWER SYSTEMS (UNIT 382) | A | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-14 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00039 | 2018-05-09 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-DL-1020-001 | 000-K-IDL-80001-001 | LIST OF DEVIATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-ITP-1020-001 | 000-K-ITP-80001-001 | INSPECTION AND TESTS PLAN FOR RECIPROCATING COMPRESSORS | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-MR-1020-001 | 000-K-MRQ-80001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSORS | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-SP-1020-001 | 000-K-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | 076551C-000S-SR-1020-001 | 000-K-SOW-80001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSORS | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | SO6001-EJ2E-TDS-09800001-001 | 098-K-DAT-00001-001 | DATASHEET FOR RECIPROCATING COMPRESSOR FOR 098K9810 CIRCULATION NITROGEN COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070048 | SO6001-EJ2E-TDS-09900001-001 | 099-K-DAT-00001-001 | DATASHEET FOR RECIPROCATING COMPRESSOR FOR 099K9910 CIRCULATION NITROGEN COMPRESSOR | AP | 2018-04-26 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-15 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000045 | 2018-05-10 | CLASS 1
CON-BMP-TRA-070049 | SO6001-ES0B-PHL-09800001-001 | 098-A-BOD-00001-001 | PROCESS DESIGN BASIS NO.3 NO.4 HYDROGEN PLANT (UNIT 098-099) | B | 2018-05-03 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-17 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000047 | 2018-05-11 | CLASS 1
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-001 | 041-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT SECTION (#5SRU, #6SRU, #7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000050 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-002 | 041-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#5SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000050 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-003 | 041-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM SULPHUR DEGASSING AND STORAGE (#5SRU,#6SRU,#7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000050 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070050 | SO6001-ES0D-MSD-04100001-004 | 041-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#5SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000050 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070051 | SO6001-ES0D-MSD-04200001-001 | 042-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#6SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000048 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070051 | SO6001-ES0D-MSD-04200001-002 | 042-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#6SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000048 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070052 | SO6001-ES0D-MSD-04300001-001 | 043-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000049 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070052 | SO6001-ES0D-MSD-04300001-002 | 043-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM REACTION FURNACE & WASTE HEAT BOILER (#7SRU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000049 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-001 | 045-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM TAIL GAS REACTOR AND DCC (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00054 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-002 | 045-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00054 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-003 | 045-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM INCINERATOR (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00054 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070053 | SO6001-ES0D-MSD-04500001-004 | 045-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM UNIT (#4TGTU) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00054 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070054 | SO6001-ES0D-MSD-04600001-001 | 046-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM NON PHENOLIC SOUR WATER UNIT (#5SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000052 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070054 | SO6001-ES0D-MSD-04600001-002 | 046-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM NON PHENOLIC SOUR WATER UNIT (#5SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000052 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070055 | SO6001-ES0D-MSD-04700001-001 | 047-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM PHENOLIC SOUR WATER UNIT (#6SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000051 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070055 | SO6001-ES0D-MSD-04700001-002 | 047-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM NON PHENOLIC SOUR WATER UNIT (#6SWS) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000051 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070056 | SO6001-ES0D-MSD-08800001-001 | 088-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KERO RETURN UNIT (EX BRB-229600 SH 01) | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-00055 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-001 | 094-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM BMP SULPHUR HANDLING FACILITIES STORAGE TANK / PRECONDITIONER | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000057 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-002 | 094-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM BMP SULPHUR HANDLING FACILITIES PELLETIZER / COOLING / LOADING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000057 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-003 | 094-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM EXISTING SULPHUR HANDLING FACILITIES STORAGE TANK / PRECONDITIONER | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000057 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-004 | 094-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM EXISTING SULPHUR HANDLING FACILITIES STORAGE TANK | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000057 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-005 | 094-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM EXISTING SULPHUR HANDLING FACILITIES PELLETIZER / COOLING / LOADING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000057 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070057 | SO6001-ES0D-MSD-09400001-006 | 094-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM 2SHF NEUTRALIZATION FACILITY | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000057 | 2018-05-17 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-001 | 098-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM FEED DESULPHURISATION AND REFORMING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000053 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-002 | 098-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM PROCESS GAS BOILER AND HTS REACTOR | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000053 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-003 | 098-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM PROCESS GAS COOLING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000053 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-004 | 098-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM DESULPHURISATION AND REFORMING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000053 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070058 | SO6001-ES0D-MSD-09800001-005 | 098-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM PROCESS GAS COOLING | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000053 | 2018-05-16 | CLASS 2
CON-BMP-TRA-070059 | SO6001-ES0D-MSD-34100001-001 | 341-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000063 | 2018-05-18 | CLASS 2
CON-BMP-TRA-070059 | SO6001-ES0D-MSD-34100001-002 | 341-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AIR COMPRESSORS DRYERS & DISTRIBUTION | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000063 | 2018-05-18 | CLASS 2
CON-BMP-TRA-070060 | SO6001-ES0D-MSD-37800001-001 | 378-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM SALT WATER SYSTEM | A | 2018-05-08 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-23 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000064 | 2018-05-18 | CLASS 2
CON-BMP-TRA-070061 | SO6001-ES0D-PFD-35600001-001 | 356-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MED DESALINATION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000061 | 2018-05-21 | CLASS 1
CON-BMP-TRA-070061 | SO6001-ES0D-PFD-35600001-002 | 356-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000061 | 2018-05-21 | CLASS 1
CON-BMP-TRA-070062 | SO6001-ES0D-PFD-35700001-001 | 357-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MED DESALINATION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000068 | 2018-05-20 | CLASS 1
CON-BMP-TRA-070063 | SO6001-ES0D-PFD-35800001-001 | 358-A-PFD-00001-001 | PROCESS FLOW DIAGRAM MED DESALINATION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000069 | 2018-05-20 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-001 | 372-A-PFD-54001-001 | PROCESS FLOW DIAGRAM FED STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-002 | 372-A-PFD-54001-002 | PROCESS FLOW DIAGRAM FED TREATMENT MIXED BED | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-003 | 372-A-PFD-54001-003 | PROCESS FLOW DIAGRAM OIL SEPARATOR TANKS | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-004 | 372-A-PFD-54001-004 | PROCESS FLOW DIAGRAM HOTWELLS | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-005 | 372-A-PFD-54001-005 | PROCESS FLOW DIAGRAM CONDENSATE RECOVERY VESSEL | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-006 | 372-A-PFD-54001-006 | PROCESS FLOW DIAGRAM RECOVERED CONDENSATE STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-007 | 372-A-PFD-54001-007 | PROCESS FLOW DIAGRAM CONDENSATE TRETMENT ACTIVATED CARBON FILTERS | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-008 | 372-A-PFD-54001-008 | PROCESS FLOW DIAGRAM TREATED CONDENSATE STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-009 | 372-A-PFD-54001-009 | PROCESS FLOW DIAGRAM CONDENSATE TREATMENT MIXED BED | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-010 | 372-A-PFD-54001-010 | PROCESS FLOW DIAGRAM DEMINERALIZED WATER STORAGE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-011 | 372-A-PFD-54001-011 | PROCESS FLOW DIAGRAM DEAREATION AND BFW DISTRIBUTION | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-012 | 372-A-PFD-54001-012 | PROCESS FLOW DIAGRAM BFW CHEMICALS DOSING | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-013 | 372-A-PFD-54001-013 | PROCESS FLOW DIAGRAM NETURALIZATION FACILITIES | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-014 | 372-A-PFD-54001-014 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-015 | 372-A-PFD-54001-015 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-016 | 372-A-PFD-54001-016 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254001-017 | 372-A-PFD-54001-017 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254002-001 | 372-A-PFD-54002-001 | PROCESS FLOW DIAGRAM UTILITY WATER HEADER | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254002-002 | 372-A-PFD-54002-002 | PROCESS FLOW DIAGRAM DEMIN WATER HEADER | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070064 | SO6001-ES0D-PFD-37254002-003 | 372-A-PFD-54002-003 | PROCESS FLOW DIAGRAM BFW HEADER | A | 2018-05-10 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-25 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000077 | 2018-05-23 | CLASS 1
CON-BMP-TRA-070065 | SO6001-ES0D-MSD-35600001-001 | 356-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MED DESALINATION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000065 | 2018-05-18 | CLASS 2
CON-BMP-TRA-070066 | SO6001-ES0D-MSD-35700001-001 | 357-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MED DESALINATION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000066 | 2018-05-18 | CLASS 2
CON-BMP-TRA-070067 | SO6001-ES0D-MSD-35800001-001 | 358-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM MED DESALINATION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 |  |  | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-001 | 372-A-MSD-54001-001 | MATERIAL SELECTION DIAGRAM FED STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-002 | 372-A-MSD-54001-002 | MATERIAL SELECTION DIAGRAM FED TREATMENT MIXED BED | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-003 | 372-A-MSD-54001-003 | MATERIAL SELECTION DIAGRAM OIL SEPARATOR TANKS | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-004 | 372-A-MSD-54001-004 | MATERIAL SELECTION DIAGRAM HOTWELLS | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-005 | 372-A-MSD-54001-005 | MATERIAL SELECTION DIAGRAM CONDENSATE RECOVERY VESSEL | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-006 | 372-A-MSD-54001-006 | MATERIAL SELECTION DIAGRAM RECOVERED CONDENSATE STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-007 | 372-A-MSD-54001-007 | MATERIAL SELECTION DIAGRAM CONDENSATE TREATMENT ACTIVATED CARBON FILTERS | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-008 | 372-A-MSD-54001-008 | MATERIAL SELECTION DIAGRAM TREATED CONDENSATE STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-009 | 372-A-MSD-54001-009 | MATERIAL SELECTION DIAGRAM CONDENSATE TREATMENT MIX BED | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-010 | 372-A-MSD-54001-010 | MATERIAL SELECTION DIAGRAM DEMI WATER STORAGE | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-011 | 372-A-MSD-54001-011 | MATERIAL SELECTION DIAGRAM DEAERATION & BFW DISTRIBUTION | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-012 | 372-A-MSD-54001-012 | MATERIAL SELECTION DIAGRAM BFW CHEMICALS DOSING | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254001-013 | 372-A-MSD-54001-013 | MATERIAL SELECTION DIAGRAM NEUTRALIZATION FACILITIES | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254002-001 | 372-A-MSD-54002-001 | MATERIAL SELECTION DIAGRAM UTILITY WATER HEADER | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254002-002 | 372-A-MSD-54002-002 | MATERIAL SELECTION DIAGRAM DEMIN WATER HEADER | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070068 | SO6001-ES0D-MSD-37254002-003 | 372-A-MSD-54002-003 | MATERIAL SELECTION DIAGRAM BFW HEADER | A | 2018-05-11 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-SOC-TRE-000076 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070069 | SO6001-ES0D-PFD-03600001-001 | 036-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KHUFF GAS TREATMENT UNIT (#2BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000061 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070069 | SO6001-ES0D-PFD-03600001-002 | 036-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#2BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000061 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070069 | SO6001-ES0D-PFD-03600001-003 | 036-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#2BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000061 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070070 | SO6001-ES0D-PFD-03700001-001 | 037-A-PFD-00001-001 | PROCESS FLOW DIAGRAM KHUFF GAS TREATMENT UNIT (#3BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 |  |  | CLASS 1
CON-BMP-TRA-070070 | SO6001-ES0D-PFD-03700001-002 | 037-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#3BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 |  |  | CLASS 1
CON-BMP-TRA-070070 | SO6001-ES0D-PFD-03700001-003 | 037-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE UNIT (#3BAGRU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 |  |  | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-001 | 044-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TAIL GAS REACTOR QUENCH COLUMN (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-002 | 044-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-003 | 044-A-PFD-00001-003 | PROCESS FLOW DIAGRAM INCINERATOR (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-004 | 044-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HP STEAM AND CONDENSATE SECTION (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-005 | 044-A-PFD-00001-005 | PROCESS FLOW DIAGRAM LP STEAM AND BLOWDOWN SECTION (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-006 | 044-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-007 | 044-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-008 | 044-A-PFD-00001-008 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-009 | 044-A-PFD-00001-009 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070071 | SO6001-ES0D-PFD-04400001-010 | 044-A-PFD-00001-010 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00060 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-001 | 045-A-PFD-00001-001 | PROCESS FLOW DIAGRAM TAIL GAS REACTOR AND QUENCH COLUMN (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-002 | 045-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE ABSORBER, REGENERATOR AND STORAGE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-003 | 045-A-PFD-00001-003 | PROCESS FLOW DIAGRAM INCINERATOR (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-004 | 045-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-005 | 045-A-PFD-00001-005 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-006 | 045-A-PFD-00001-006 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070072 | SO6001-ES0D-PFD-04500001-007 | 045-A-PFD-00001-007 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#4TGTU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00058 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-001 | 048-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00059 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-002 | 048-A-PFD-00001-002 | PROCESS FLOW DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00059 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-003 | 048-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00059 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070073 | SO6001-ES0D-PFD-04800001-004 | 048-A-PFD-00001-004 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#2ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00059 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070074 | SO6001-ES0D-PFD-04900001-001 | 049-A-PFD-00001-001 | PROCESS FLOW DIAGRAM AMINE REGENERATION (#3ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00056 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070074 | SO6001-ES0D-PFD-04900001-002 | 049-A-PFD-00001-002 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00056 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070074 | SO6001-ES0D-PFD-04900001-003 | 049-A-PFD-00001-003 | PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE (#3ARU) | A | 2018-05-11 | FOR BAPCO APPROVAL | BMP Project Director | 2018-05-28 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00056 | 2018-05-17 | CLASS 1
CON-BMP-TRA-070075 | SO6001-EJ2E-TDS-09800004-001 | 098-S-DAT-00004-001 | DATASHEET FOR HYDROGEN PSA UNIT (098U0001) | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2-reviewed with minor comments - bmp-soc-tre-000078 | 2018-05-23 | CLASS 2
CON-BMP-TRA-070076 | SO6001-EJ2E-TDS-09900004-001 | 099-S-DAT-00004-001 | DATASHEET FOR HYDROGEN PSA UNIT (099U0001) | A | 2018-05-14 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-29 | 2-REVIEWED WITH MINOR COMMENTS - BMP-SOC-TRE-000079 | 2018-05-23 | CLASS 2
CON-BMP-TRA-070077 | SO6001-ES0D-MSD-03600001-001 | 036-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#2BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000071 | 2018-05-20 | CLASS 2
CON-BMP-TRA-070077 | SO6001-ES0D-MSD-03600001-002 | 036-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#2BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000071 | 2018-05-20 | CLASS 2
CON-BMP-TRA-070078 | SO6001-ES0D-MSD-03700001-001 | 037-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#3BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000070 | 2018-05-20 | CLASS 2
CON-BMP-TRA-070078 | SO6001-ES0D-MSD-03700001-002 | 037-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM KHUFF GAS TREATMENT UNIT (#3BAGRU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-000070 | 2018-05-20 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-001 | 044-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM TAIL GAS REACTOR AND DCC (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-002 | 044-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE ABSORBER REGENERATOR AND STORAGE (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-003 | 044-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM INCINERATOR (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-004 | 044-A-MSD-00001-004 | MATERIAL SELECTION DIAGRAM STEAM CONDENSATE AND BLOWDOWN SECTION (#3TGTU & #4TGTU ) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-005 | 044-A-MSD-00001-005 | MATERIAL SELECTION DIAGRAM UNIT (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-006 | 044-A-MSD-00001-006 | MATERIAL SELECTION DIAGRAM UNIT (#3TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070079 | SO6001-ES0D-MSD-04400001-007 | 044-A-MSD-00001-007 | MATERIAL SELECTION DIAGRAM UNIT (#3TGTU & #4TGTU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000074 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070080 | SO6001-ES0D-MSD-04800001-001 | 048-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00072 | 2018-05-20 | CLASS 2
CON-BMP-TRA-070080 | SO6001-ES0D-MSD-04800001-002 | 048-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 | 3-REVIEWED WITH COMMENTS - BMP-SOC-TRE-00072 | 2018-05-20 | CLASS 2
CON-BMP-TRA-070081 | SO6001-ES0D-MSD-04900001-001 | 049-A-MSD-00001-001 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#3ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000073 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070081 | SO6001-ES0D-MSD-04900001-002 | 049-A-MSD-00001-002 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#3ARU) | A | 2018-05-15 | FOR BAPCO REVIEW | BMP Project Director | 2018-05-30 | 3-REVIEWED WITH COMMENTS BMP-SOC-TRE-000073 | 2018-05-21 | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-DL-0511-002 | 000-C-IDL-80007-001 | LIST OF DEVIATION FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-ITP-0511-002 | 000-C-ITP-80007-001 | INSPECTION AND TEST PLAN FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-MR-0511-002 | 000-C-MRQ-80007-001 | MATERIAL REQUISITION FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-SP-0511-002 | 000-C-GRD-80007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | 076551C-000S-SR-0511-002 | 000-C-SOW-80007-001 | SCOPE OF SUPPLY FOR CLADDED COLUMNS | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-001 | 036-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-002-001 | 036-C-GAD-00002-001 | 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-002-002 | 036-C-GAD-00002-002 | 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03600004-002-003 | 036-C-GAD-00002-003 | 036C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-001 | 037-C-DAT-00002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-002-001 | 037-C-GAD-00002-001 | 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-002-002 | 037-C-GAD-00002-002 | 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-03700004-002-003 | 037-C-GAD-00002-003 | 037C0002 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-001 | 044-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-002-001 | 044-C-GAD-00004-001 | 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-002-002 | 044-C-GAD-00004-002 | 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04400011-002-003 | 044-C-GAD-00004-003 | 044C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-001 | 045-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-002-001 | 045-C-GAD-00004-001 | 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-002-002 | 045-C-GAD-00004-002 | 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04500006-002-003 | 045-C-GAD-00004-003 | 045C0004 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-001 | 046-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 046C0001 REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-002-001 | 046-C-GAD-00001-001 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-002-002 | 046-C-GAD-00001-002 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04600003-002-003 | 046-C-GAD-00001-003 | 046C0001 NON-PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-001 | 047-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-002-001 | 047-C-GAD-00001-001 | 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-002-002 | 047-C-GAD-00001-002 | 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04700003-002-003 | 047-C-GAD-00001-003 | 047C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-001 | 048-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 048C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-002-001 | 048-C-GAD-00001-001 | 048C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-002-002 | 048-C-GAD-00001-002 | 048C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04800005-002-003 | 048-C-GAD-00001-003 | 048C0001 PHENOLIC SOUR WATER STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-001 | 049-C-DAT-00001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-002-001 | 049-C-GAD-00001-001 | 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-002-002 | 049-C-GAD-00001-002 | 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-04900003-002-003 | 049-C-GAD-00001-003 | 049C0001 AMINE REGENERATOR | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-001 | 098-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-002-001 | 098-C-GAD-00004-001 | 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-002-002 | 098-C-GAD-00004-002 | 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09800005-002-003 | 098-C-GAD-00004-003 | 098C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-001 | 099-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-002-001 | 099-C-GAD-00004-001 | 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-002-002 | 099-C-GAD-00004-002 | 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070082 | SO6001-EJ1E-TDS-09900005-002-003 | 099-C-GAD-00004-003 | 099C0004 HIGH PRESSURE STRIPPER | AP | 2018-05-17 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-01 |  |  | CLASS 2
CON-BMP-TRA-070083 | SO6001-ES0B-PHL-09400001-001 | 094-A-BOD-00001-001 | BASIS OF DESIGN 2SHF (UNIT 094) SULPHUR HANDLING FACILITY | B | 2018-05-18 | FOR BAPCO APPROVAL | BMP Project Director | 2018-06-04 |  |  | CLASS 1
CON-BMP-TRA-070084 | SO6001-EJ2E-TDS-01610003-001 | 016-G-DAT-00003-001 | DATA SHEET FOR CAUSTIC INJECTION PUMP TRAIN C | A | 2018-05-18 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-04 |  |  | CLASS 2
CON-BMP-TRA-070085 | SO6001-EJ1E-TDS-04100004-001 | 041-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0002 NO.1 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070085 | SO6001-EJ1E-TDS-04100005-001 | 041-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0003 NO.2 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070085 | SO6001-EJ1E-TDS-04100006-001 | 041-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 041E0004 NO.3 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070086 | SO6001-EJ1E-TDS-04200004-001 | 042-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 042E0002 NO.1 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070086 | SO6001-EJ1E-TDS-04200005-001 | 042-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGE DATA SHEET FOR 042E0003 NO.2 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070086 | SO6001-EJ1E-TDS-04200006-001 | 042-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 042E0004 NO.3 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070087 | SO6001-EJ1E-TDS-04300004-001 | 043-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0002 NO.1 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070087 | SO6001-EJ1E-TDS-04300005-001 | 043-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0003 NO.2 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070087 | SO6001-EJ1E-TDS-04300006-001 | 043-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 043E0004 NO.3 SULPHUR CONDENSER | B | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070088 | SO6001-EJ1E-TDS-04400012-001 | 044-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 044E0002 WASTE HEAT BOILER | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070089 | SO6001-EJ1E-TDS-04500009-001 | 045-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 045E0002 WASTE HEAT BOILER | A | 2018-05-21 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-05 |  |  | CLASS 2
CON-BMP-TRA-070090 | SO6001-ES0D-MSD-04800001-003 | 048-A-MSD-00001-003 | MATERIAL SELECTION DIAGRAM AMINE REGENERATION (#2ARU) | A | 2018-05-23 | FOR BAPCO REVIEW | BMP Project Director | 2018-06-07 |  |  | CLASS 2
JVD-OCS-TRA-000001 | 076551C-000D-PP-103 |  | COORDINATION PROCEDURE BETWEEN TTSJV AND OCS | 0 | 2018-03-16 | FOR OCS INFORMATION | MOC-ROC-SOC
JVD-OCS-TRA-000002 | 076551C-000D-PP-262 |  | P&ID & PFD DRAFTING PROCEDURE | 0 | 2018-03-27 | FOR OCS INFORMATION | MOC-ROC-SOC
JVD-OCS-TRA-000003 | 076551C-000D-PP-263 |  | COORDINATION PROCEDURE FOR SMARTPLANT ELECTRICAL | A | 2018-04-13 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-04-24
JVD-OCS-TRA-000004 | 076551C-000S-DL-0215-001 | 000-S-IDL-80002-001 | DEVIATION LIST FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | 076551C-000S-ITP-0215-001 | 000-S-ITP-80002-001 | INSPECTION AND TEST PLAN FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | 076551C-000S-MR-0215-001 | 000-S-MRQ-80002-001 | MATERIAL REQUISITION FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | 076551C-000S-SP-0215-001 | 000-S-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | 076551C-000S-SR-0215-001 | 000-S-SOW-80002-001 | SCOPE OF SUPPLY FOR NO. 6-7 AND 8 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | SO6001-EJ2E-TDS-35600001-001 | 356-S-DAT-00001-001 | DUTY SPECIFICATION FOR 356U0001 NO6 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | SO6001-EJ2E-TDS-35700001-001 | 357-S-DAT-00001-001 | DUTY SPECIFICATION FOR 356U0001 NO7 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000004 | SO6001-EJ2E-TDS-35800001-001 | 358-S-DAT-00001-001 | DUTY SPECIFICATION FOR 356U0001 NO8 DESALINATION PLANT | A | 2018-04-12 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | 076551C-000S-DL-0119-004 | 000-F-IDL-80002-001 | DEVIATION LIST FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | 076551C-000S-ITP-0119-004 | 000-F-ITP-80002-001 | INSPECTION AND TEST PLAN FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | 076551C-000S-MR-0119-004 | 000-F-MRQ-80002-001 | MATERIAL REQUISITION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | 076551C-000S-SP-0119-004 | 000-F-GRD-80002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | 076551C-000S-SR-0119-004 | 000-F-SOW-80002-001 | SCOPE OF SUPPLY FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04100007-001 | 041-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 041F4101 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04100008-001 | 041-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 041V4103 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04100009-001 | 041-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 041E4101 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04100010-001 | 041-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 041X4101 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04200007-001 | 042-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 041F4201 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04200008-001 | 042-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 042V4203 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04200009-001 | 042-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 042E4201 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04200010-001 | 042-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 042X4201 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04300007-001 | 043-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE 043F4301 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04300008-001 | 043-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR HP STEAM DRUM 043V4303 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04300009-001 | 043-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR WASTE HEAT BOILER 043E4301 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000005 | SO6001-EJ1E-TDS-04300010-001 | 043-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR REACTION FURNACE BURNER 043X4301 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | 076551C-000S-DL-0113-001 | 000-F-IDL-80001-001 | DEVIATION LIST FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | 076551C-000S-ITP-0113-001 | 000-F-ITP-80001-001 | INSPECTION AND TEST PLAN FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | 076551C-000S-MR-0113-001 | 000-F-MRQ-80001-001 | MATERIAL REQUISITION FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | 076551C-000S-SP-0113-001 | 000-F-GRD-80001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | 076551C-000S-SR-0113-001 | 000-F-SOW-80001-001 | SCOPE OF SUPPLY FOR HYDROGEN PLANT STEAM REFORMER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09800007-001 | 098-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09800008-001 | 098-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 098V0004 STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09800009-001 | 098-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 098E0001 PROCESS GAS BOILER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09800010-001 | 098-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 098F0001 REFORMING FURNACE BURNERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09900007-001 | 099-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 099F0001 REFORMING FURNACE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09900008-001 | 099-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR 099V0004 STEAM DRUM | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09900009-001 | 099-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR 099E0001 PROCESS GAS BOILER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000006 | SO6001-EJ1E-TDS-09900010-001 | 099-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR 099F00011 REFORMING FURNACE BURNERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | 076551C-000S-DL-0140-001 | 000-F-IDL-80003-001 | DEVIATION LIST FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | 076551C-000S-ITP-0140-001 | 000-F-ITP-80003-001 | INSPECTION AND TEST PLAN FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | 076551C-000S-MR-0140-001 | 000-F-MRQ-80003-001 | MATERIAL REQUISITION FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | 076551C-000S-SP-0140-001 | 000-F-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | 076551C-000S-SR-0140-001 | 000-F-SOW-80003-001 | SCOPE OF SUPPLY FOR INCINERATOR PACKAGE | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | SO6001-EJ1E-TDS-04400007-001 | 044-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 044U4401 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000007 | SO6001-EJ1E-TDS-04500007-001 | 045-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR INCINERATOR PACKAGE 045U4501 | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | 076551C-000S-DL-0150-001 | 000-F-IDL-80004-001 | DEVIATION LIST FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | 076551C-000S-ITP-0150-001 | 000-F-ITP-80004-001 | INSPECTION AND TEST PLAN FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | 076551C-000S-MR-0150-001 | 000-F-MRQ-80004-001 | MATERIAL REQUISITION FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | 076551C-000S-SP-0150-001 | 000-F-GRD-80004-001 | PARTICULAR TECHNICAL SPECIFICATION FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | 076551C-000S-SR-0150-001 | 000-F-SOW-80004-001 | SCOPE OF SUPPLY FOR AUXILIARY STEAM BOILERS | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | SO6001-EJ1E-TDS-31000001-001 | 310-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 310F0001 AUXILIARY STEAM BOILER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000008 | SO6001-EJ1E-TDS-31100001-001 | 311-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR 311F0001 AUXILIARY STEAM BOILER | A | 2018-04-13 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000009 | BMPS-A14 |  | ENVIRONMENTAL PHILOSOPHY | 0 | 2016-05-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A17 |  | PREPARATION OF SAFETY INSTRUCTION SHEETS | 0 | 2015-12-23 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A19 |  | DESIGN OF FLARE EQUIPMENT | 0 | 2016-03-03 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A2 |  | SPECIFICATIONS, CODES AND STANDARDS | 1 | 2016-07-14 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A21 |  | NOISE LIMITATIONS FOR EQUIPMENT | 0 | 2016-01-02 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A23 |  | SELECTION OF METALLIC MATERIALS | 0 | 2015-09-11 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A25 |  | THICK WALL PRESSURE VESSELS AND HEAT EXCHANGERS | 0 | 2015-12-14 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A26 |  | CARBON STEEL PRESSURE VESSELS AND HEAT EXCHANGERS IN SOUR SERVICE | 1 | 2018-04-13 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A27 |  | CLAD CARBON STEEL AND LOW ALLOY PRESSURE VESSELS AND HEAT EXCHANGERS | 0 | 2015-12-14 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A3 |  | DESIGN PHILOSOPHY | 0 | 2016-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A4 |  | REFINERY LAYOUT AND SPACING | 0 | 2016-05-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A5 |  | SAFETY IN DESIGN INCORPORATING HUMAN FACTORS ENGINEERING | 0 | 2016-04-26 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A6 |  | MATERIAL CLASSIFICATIONS | 0 | 2015-12-23 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-A7 |  | PROJECT INFORMATION MANAGEMENT AND HANDOVER (PIMH) | 1 | 2016-06-21 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-B1 |  | GENERAL WELDING REQUIREMENTS | 1 | 2018-04-06 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-B3 |  | PIPING FABRICATION, INSTALLATION AND TESTING | 0 | 2015-07-02 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-B5 |  | COATING OF EXTERNAL SURFACES AND COLOUR CODING | 0 | 2015-11-18 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-B9 |  | POSITIVE ALLOY MATERIAL IDENTIFICATION | 1 | 2018-03-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C11 |  | BUBBLE CAP AND SIEVE TRAYS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C12 |  | ALUMINIZING OF STAINLESS STEEL FASTENERS | 0 | 2016-02-26 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C2 |  | CARBON STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C3 |  | 1 1/4 CR - 1/2 MO STEEL PRESSURE VESSELS OPERATING BELOW 825°F (440°C) | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C4 |  | HYDROPROCESSING REACTORS AND HIGH PRESSURE VESSELS MANUFACTURED FROM 1 1/4 CR - 1/2 MO ALLOY STEEL | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C5 |  | CONVENTIONAL 2 1/4 CR-1MO STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C6 |  | HYDROPROCESSING REACTORS AND HIGH PRESSURE VESSELS MANUFACTURED FROM 2.25CR-1MO AND 2.25CR-1MO-0.25V LOW ALLOY STEELS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C7 |  | AUSTENITIC STAINLESS STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C8 |  | DUPLEX STAINLESS STEEL PRESSURE VESSELS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-C9 |  | FIELD ERECTED CARBON STEEL STORAGE SPHERES | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-E7 |  | AIR COOLED HEAT EXCHANGERS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F1 |  | FIRED HEATERS | 0 | 2016-01-22 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F10 |  | AUXIARY STEAM BOILERS | 0 | 2015-11-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F2 |  | MATERIAL SPECIFICATION FOR FIRED HEATERS / BOILERS TUBES AND FITTINGS | 0 | 2016-04-12 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F3 |  | CENTRIFUGALLY CAST FURNACE TUBE ASSEMBLIES OF 25% CR ¿ 35% NI HP-MICRO ALLOY AND 25% CR ¿ 35% NI HP-MODIFIED ALLOY | 0 | 2015-11-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F4 |  | PROCESS HEATER BURNER TESTING | 0 | 2015-11-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F6 |  | REFRACTORY LININGS FOR SULPHUR RECOVERY UNIT MAIN REACTION FURNACES | 0 | 2015-11-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F7 |  | MONOLITHIC REFRACTORY MATERIAL REQUIRED PROPERTIES AND RECOMMENDED BRANDS | 0 | 2015-11-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F8 |  | PURCHASING SPECIFICATION - MONOLITHIC REFRACTORIES | 0 | 2015-11-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-F9 |  | INSTALLATION OF MONOLITHIC REFRACTORY LINING | 0 | 2016-02-26 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J1 |  | CONTROL SYSTEM DESIGN BASIS | 1 | 2018-04-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J19 |  | FIRE ALARM SYSTEM (FAS) | 1 | 2018-04-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J2 |  | GENERAL INSTRUMENT SPECIFICATION | 1 | 2018-04-16 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J33 |  | DESIGN PHILOSOPHY FOR FIRED HEATERS BURNER MANAGEMENT SYSTEM (BMS) | 0 | 2015-05-25 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J6 |  | INSTRUMENTATION FOR PACKAGE UNITS | 1 | 2018-04-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J7 |  | FOUNDATION FIELDBUS HIGH POWER TRUNK - FIELDBUS BARRIER MODEL | 1 | 2018-04-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-J8 |  | CONTROL VALVES | 1 | 2018-04-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-K8 |  | GENERAL PURPOSE PRESSURE LUBRICATION SYSTEMS | 1 | 2018-03-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-K9 |  | LUBRICATION, SHAFT SEALING AND CONTROL OIL SYSTEMS FOR SPECIAL PURPOSE APPLICATIONS | 1 | 2018-03-01 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-L2 |  | PIPING LINE CLASSES | 0 | 2016-05-23 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-L3 |  | PIPING LAYOUT AND PIPING DESIGN | 1 | 2016-06-17 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-L4 |  | PIPING SYSTEMS - NOISE LIMITATIONS | 0 | 2016-01-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-L5 |  | STEAM TRACING | 0 | 2015-11-16 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-L6 |  | CEMENT LINED PIPING | 0 | 2015-05-02 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-L9 |  | PIPING FLEXIBILITY AND STRESS ANALYSIS | 0 | 2015-12-22 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-M1 |  | BASIC CIVIL AND STRUCTURAL DESIGN DATA | 1 | 2016-06-09 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-M3 |  | STEEL STRUCTURES | 1 | 2016-06-09 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-M6 |  | FIREPROOFING | 0 | 2016-01-20 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-N1 |  | INSULATION | 0 | 2015-11-18 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P1 |  | GENERAL DESIGN RULES FOR ELECTRICAL SYSTEM | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P12 |  | POWER FACTOR CORRECTION SYSTEM | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P14 |  | LV OUTDOOR SWITCHRACKS AND DISTRIBUTION BOARDS | 0 | 2015-10-19 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P18 |  | HV INDUCTION MOTORS | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P19 |  | LV INDUCTION MOTORS | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P2 |  | CLASSIFICATION OF LOCATIONS FOR SELECTION OF ELECTRICAL EQUIPMENT | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P3 |  | ELECTRICAL REQUIREMENTS FOR PACKAGE UNITS | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P5 |  | POWER, CONTROL AND GROUNDING CABLES | 0 | 2015-10-19 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P6 |  | HV GAS INSULATED SWITCHGEAR (GIS) | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P7 |  | HV AIR INSULATED SWITCHGEARS | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P8 |  | LOW VOLTAGE SWITCHGEARS | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-P9 |  | POWER TRANSFORMERS | 1 | 2018-03-30 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-Q1 |  | CONCRETE FOUNDATIONS | 0 | 2016-02-26 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-Q2 |  | GROUTING | 0 | 2018-04-13 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R1 |  | BUILDING GENERAL SPECIFICATIONS; DESIGN PHILOSOPHY, MATERIALS, FINISHES AND FIXTURES (ARCHITECTURAL AND STRUCTURAL) | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R10 |  | HVAC PHILOSOPHY AND EQUIPMENT | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R2 |  | SATELLITE RACK ROOMS | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R3 |  | ELECTRICAL SUBSTATION BUILDING | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R4 |  | OPERATOR WORKSTATIONS | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R7 |  | REFINERY CONTROL BUILDING | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-R9 |  | PROFILED METAL CLADDING SUPPLY AND INSTALLATION | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S1 |  | DRAINAGE SEWER SYSTEMS AND EFFLUENT TREATING | 0 | 2018-04-11 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S10 |  | CHEMICAL INJECTION PACKAGES | 0 | 2018-01-26 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S11 |  | PACKAGE UNIT FOR INSTRUMENT AIR COMPRESSION SYSTEM AND DRYERS | 0 | 2015-12-21 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S12 |  | GUIDELINES FOR PREPARATION OF SPARE PARTS AND INTERCHANGEABILITY LISTS (SPILS) | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S13 |  | GUIDELINES FOR PREPARATION OF LUBRICATION SCHEDULE FOR MACHINERY | 0 | 2015-05-04 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S2 |  | SITE PREPARATION, CLEARING AND EARTHWORKS | 0 | 2018-04-11 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S6 |  | FACILITIES FOR PRESSURIZED MOUNDED STORAGE AND LOADING OF LPG | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S7 |  | FACILITIES FOR STORAGE AND LOADING OF PROPANE (C3) AND BUTANES (C4S) | 0 | 2016-04-28 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S8 |  | DESALINATION PLANT | 0 | 2015-08-05 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000009 | BMPS-S9 |  | BOILER FEED WATER TEATING PLANT | 0 | 2015-08-05 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000010 | 010-F-DAT-00001-001 | 010-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 010F0001 ATMOSPHERIC COLUMN HEATER | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000010 | 011-F-DAT-00001-001 | 011-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS - 011F0001 VACUUM COLUMN HEATER | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000010 | 076551C-000M-DL-0110-002 | 000-F-IDL-70002-001 | DEVIATION LIST FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000010 | 076551C-000M-ITP-0110-002 | 000-F-ITP-70002-001 | INSPECTION AND TEST PLAN FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000010 | 076551C-000M-MR-0110-002 | 000-F-MRQ-70002-001 | MATERIAL REQUISITION FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000010 | 076551C-000M-SP-0110-002 | 000-F-GRD-70002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000010 | 076551C-000M-SR-0110-002 | 000-F-SOW-70002-001 | SCOPE OF SUPPLY FOR CDU/VCU FIRED HEATERS | A | 2018-04-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00001-001 | 019-E-DAT-00001-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0006 A/B 1ST STAGE REACTOR EFFLUENT / FRESH FEED EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00002-001 | 019-E-DAT-00002-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0004 A/B 1ST STAGE REACTOR EFFLUENT / EFFLUENT EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00003-001 | 019-E-DAT-00003-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0005 A/B 1ST STAGE REACTOR EFFLUENT / FRACTIONATOR FEED EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00004-001 | 019-E-DAT-00004-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0007 A/B 1ST STAGE HHPS VAPOR / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00005-001 | 019-E-DAT-00005-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0011 A/B 2ND STAGE HHPS VAPOR /CLPS LIQUID EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00006-001 | 019-E-DAT-00006-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0009 A/B 2ND STAGE REACTOR FEED /EFFLUENT EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00007-001 | 019-E-DAT-00007-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0010 2ND STAGE REACTOR EFFLUENT / RECYCLE GAS EXCHANGER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00013-001 | 019-E-DAT-00013-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0044 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00014-001 | 019-E-DAT-00014-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0047 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 019-E-DAT-00015-001 | 019-E-DAT-00015-001 | SHELL AND TUBE HEAT EXCHANGER DATA SHEET FOR 19E0074 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 076551C-000M-DL-0610-001 | 000-E-IDL-70001-001 | DEVIATION LIST FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 076551C-000M-ITP-0610-001 | 000-E-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 076551C-000M-MR-0610-001 | 000-E-MRQ-70001-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 076551C-000M-SP-0610-001 | 000-E-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000011 | 076551C-000M-SR-0610-001 | 000-E-SOW-70001-001 | SCOPE OF SUPPLY FOR HP SHELL AND TUBE HEAT EXCHANGES | A | 2018-04-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000012 | 010-C-GAD-10004-001 | 010-C-GAD-10004-001 | STABILIZER - ITEM 010C0004 EX 010C0005/010-C-GAD-10005-001 AS PER CLIENT COMMENTS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 010-C-GAD-10005-001 | 010-C-GAD-10005-001 | NAPHTHA SPLITTER - ITEM 010C0005 EX 010C0005/010-C-GAD-10006-001 AS PER CLIENT COMMENTS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 019-C-GAD-10006-001 | 019-C-GAD-10006-001 | KEROSENE STRIPPER - ITEM 019C0006 | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 019-C-GAD-10010-001 | 019-C-GAD-10010-001 | NAPHTHA SPLITTER - ITEM 019C0010 | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 076551C-000M-DL-0511-001 | 000-C-IDL-70008-001 | DEVIATION LIST FOR CS COLUMNS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 076551C-000M-ITP-0511-001 | 000-C-ITP-70008-001 | INSPECTION AND TEST PLAN FOR CS COLUMNS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 076551C-000M-MR-0511-001 | 000-C-MRQ-70008-001 | MATERIAL REQUISITION FOR CS COLUMNS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 076551C-000M-SP-0511-001 | 000-C-GRD-70008-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CS COLUMNS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000012 | 076551C-000M-SR-0511-001 | 000-C-SOW-70008-001 | SCOPE OF SUPPLY FOR CS COLUMNS | A | 2018-04-20 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000013 | BMPS-A8 |  | DRAFTING AND DOCUMENTATION REQUIREMENTS | 1 | 2018-04-20 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000014 | 076551C-000S-DL-4352-001 | 000-S-IDL-80010-001 | LIST OF DEVIATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-03 |  |  | CLASS 1
JVD-OCS-TRA-000014 | 076551C-000S-ITP-4352-001 | 000-S-ITP-80010-001 | INSPECTION AND TESTS PLAN FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-03 |  |  | CLASS 1
JVD-OCS-TRA-000014 | 076551C-000S-MR-4352-001 | 000-S-MRQ-80010-001 | MATERIAL REQUISITION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-03 |  |  | CLASS 1
JVD-OCS-TRA-000014 | 076551C-000S-SP-4352-001 | 000-S-GRD-80010-001 | PARTICULAR TECHNICAL SPECIFICATION FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-03 |  |  | CLASS 1
JVD-OCS-TRA-000014 | 076551C-000S-SR-4352-001 | 000-S-SOW-80010-001 | SCOPE OF SUPPLY FOR BMP SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-03 |  |  | CLASS 1
JVD-OCS-TRA-000014 | SO6001-EJ2E-TDS-09400001-001 | 094-S-DAT-00001-001 | DUTY SPECIFICATION FOR 094U9401 SULPHUR SOLIDIFICATION PACKAGE | A | 2018-04-20 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-03 |  |  | CLASS 1
JVD-OCS-TRA-000015 | BMPS-D3 |  | STORAGE TANKS TO API 620 | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000015 | BMPS-J23 |  | ONLINE ANALYSER SYSTEMS | 1 | 2018-03-29 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000016 | 076551C-000R-DL-0110-001 | 000-F-IDL-60001-001 | DEVIATION LIST 1 RHCU FIRED HEATERS | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-000R-ITP-0110-001 | 000-F-ITP-60001-001 | INSPECTION AND TEST PLAN (ITP) 1 RHCU FIRED HEATERS | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-000R-MR-0110-001 | 000-F-MRQ-60001-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-000R-SP-0110-001 | 000-F-GRD-60001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 1 RHCU FIRED HEATERS 18F1001/18-F1002/18F2001/18F2002/18F0001/18F0002 | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-018-SP-0110-001 | 018-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1001 /F 018F2001 TRAIN 1&2 - REACTOR FEED FURNACE | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-018-SP-0110-002 | 018-F-DAT-00002-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0001 ATM COLUMN FEED FURNACE | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-018-SP-0110-003 | 018-F-DAT-00003-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F0002 VACUUM COLUMN FEED FURNACE | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000016 | 076551C-018-SP-0110-004 | 018-F-DAT-00004-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 018F1002 / 018F2002 TRAIN 1&2 - RECYCLE HYDROGEN FURNACE | A | 2018-04-24 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000017 | BMPS-J14 |  | EMERGENCY SHUT DOWN (ESD) SYSTEM | 1 | 2018-04-03 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000017 | BMPS-J39 |  | CCTV, RADIO, TELECOMMUNICATIONS AND SECURITY SYSTEMS | 1 | 2018-04-03 | FOR OCS IMPLENTATION | MOC-ROC-SOC
JVD-OCS-TRA-000018 | 076551C-000S-DL-0710-002 | 000-E-IDL-80007-001 | DEVIATION LIST FOR AIR COOLERS | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | 076551C-000S-ITP-0710-002 | 000-E-ITP-80007-001 | INSPECTION AND TEST PLAN FOR AIR COOLERS | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | 076551C-000S-MR-0710-002 | 000-E-MRQ-80007-001 | MATERIAL REQUISITION FOR AIR COOLERS | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | 076551C-000S-SP-0710-002 | 000-E-GRD-80007-001 | PARTICULAR TECHNICAL SPEIFICATION FOR AIR COOLERS | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | 076551C-000S-SR-0710-002 | 000-E-SOW-80007-001 | SCOPE OF SUPPLY FOR AIR COOLERS | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-03600001-001 | 036-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 036E3611 REGENERATOR PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-03600002-001 | 036-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 036E3612 AMINE COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-03700001-001 | 037-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 037E3711 REGENERATOR PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-03700002-001 | 037-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 037E3712 AMINE COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04100001-001 | 041-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 041E4111 STEAM CONDENSER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04200001-001 | 042-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 042E4211 STEAM CONDENSER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04300001-001 | 043-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 043E4311 STEAM CONDENSER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04400001-001 | 044-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4410 CONDENSATE AIR COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04400002-001 | 044-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4411 QUENCH WATER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04400003-001 | 044-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET 044E4412 AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04400004-001 | 044-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4413 LEAN AMINE COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04400005-001 | 044-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4414 60# STEAM BLOWDOWN DRUM CONDENSER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04400006-001 | 044-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 044E4415 STEAM CONDENSER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04500001-001 | 045-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4511 QUENCH WATER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04500002-001 | 045-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4512 AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04500003-001 | 045-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 045E4513 LEAN AMINE COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04600001-001 | 046-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 046E4611 STRIPPER PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04600002-001 | 046-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 046E4612 STRIPPED WATER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04700001-001 | 047-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 047E4711 STRIPPER PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04700002-001 | 047-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 047E4712 STRIPPED WATER COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04800001-001 | 048-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4811 AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04800002-001 | 048-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4812 LEAN AMINE COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04800003-001 | 048-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4813 ARU STEAM CONDENSER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04800004-001 | 048-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 048E4814 ARU CONDENSATE AIR COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04900001-001 | 049-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 049E4911 AMINE REGENERATOR PUMP AROUND COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-04900002-001 | 049-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 049E4912 LEAN AMINE COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-08800001-001 | 088-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 088E1931 KERO PRODUCT AIR COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-09800001-001 | 098-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 098E9805 PROCESS GAS COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-09900001-001 | 099-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 099E9905 PROCESS GAS COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000018 | SO6001-EJ1E-TDS-37155001-001 | 371-E-DAT-55001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 371E0002 60 PSIG EXCESS STEAM CONDENSATE AIR COOLER | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000019 | 076551C-000S-DL-4010-001 | 000-S-IDL-80003-001 | DEVIATION LIST FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000019 | 076551C-000S-ITP-4010-001 | 000-S-ITP-80003-001 | INSPECTION AND TEST PLAN FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000019 | 076551C-000S-MR-4010-001 | 000-S-MRQ-80003-001 | MATERIAL REQUISITION FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000019 | 076551C-000S-SP-4010-001 | 000-S-GRD-80003-001 | PARTICULAR TECHNICAL SPECIFICATION FOR FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000019 | 076551C-000S-SR-4010-001 | 000-S-SOW-80003-001 | SCOPE OF SUPPLY FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000019 | SO6001-EJ2E-TDS-09400002-001 | 094-S-DAT-00002-001 | DUTY SPECIFICATION FOR BMP SOLID SULPHUR HANDLING PACKAGE | A | 2018-04-27 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-10 |  |  | CLASS 1
JVD-OCS-TRA-000022 | 019-C-DAT-30001-001 | 019-C-DAT-30001-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE REACTOR 019C0001R | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 019-C-DAT-30002-001 | 019-C-DAT-30002-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAGE REACTOR 019C0002R | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 019-C-GAD-30001-001 | 019-C-GAD-30001-001 | GENERAL ARRANGEMENT 019C0001R 1ST STAGE REACTOR | A | 2018-04-27 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 019-C-GAD-30002-001 | 019-C-GAD-30002-001 | GENERAL ARRANGEMENT 019C0002R 2ND STAGE REACTOR | A | 2018-04-27 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 076551C-000M-DL-0470-001 | 000-C-IDL-70007-001 | DEVIATION LIST FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 076551C-000M-ITP-0470-001 | 000-C-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 076551C-000M-MR-0470-001 | 000-C-MRQ-70007-001 | MATERIAL REQUISITION FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 076551C-000M-SP-0470-001 | 000-C-GRD-70007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000022 | 076551C-000M-SR-0470-001 | 000-C-SOW-70007-001 | SCOPE OF SUPPLY FOR HCU REACTORS INTERNALS (CLG PROPRIETARY ITEM) | A | 2018-04-24 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000023 | 076551C-000R-DL-0960-001 | 000-G-IDL-60002-001 | DEVIATION LIST FOR EBULLATING PUMPS | A | 2018-04-26 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000023 | 076551C-000R-ITP-0960-001 | 000-G-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR EBULLATING PUMPS | A | 2018-04-26 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000023 | 076551C-000R-MR-0960-001 | 000-G-MRQ-60002-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | A | 2018-04-26 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000023 | 076551C-000R-SP-0960-001 | 000-G-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR EBULLATING PUMPS | A | 2018-04-26 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000023 | 076551C-000R-SR-0960-001 | 000-G-SOW-60002-001 | SCOPE OF SUPPLY FOR EBULLATING PUMPS | A | 2018-04-26 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000023 | 076551C-018-SP-0960-001 | 018-G-DAT-00001-001 | 1ST 2ND REACTOR RECYCLE PUMPS PACKAGE | A | 2018-04-26 | FOR INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000025 | 076551C-000D-NM-0002-001 |  | FLUID LIST | A | 2018-05-16 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-30
JVD-OCS-TRA-000040 | 076551C-000D-PP-265 |  | SPLIT OF ELECRICAL ENGINEERING WORKS | A | 2018-05-15 | FOR OCS REVIEW | MOC-ROC-SOC | 2018-05-29
JVD-OCS-TRA-000043 | 076551C-000M-DL-0310-001 | 000-E-IDL-70006-001 | DEVIATION LIST FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000043 | 076551C-000M-ITP-0310-001 | 000-E-ITP-70006-001 | INSPECTION AND TEST PLAN FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000043 | 076551C-000M-MR-0310-001 | 000-E-MRQ-70006-001 | MATERIAL REQUISITION FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000043 | 076551C-000M-SP-0310-001 | 000-E-GRD-70006-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000043 | 076551C-000M-SR-0310-001 | 000-E-SOW-70006-001 | SCOPE OF SUPPLY FOR INDUCED DRAFT COOLING TOWER | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000043 | 085-E-DAT-00001-001 | 085-E-DAT-00001-001 | MECHANICAL DATA SHEET BMP MAIN COOLING TOWER 085CWT0001 | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000043 | 085-E-DAT-00002-001 | 085-E-DAT-00002-001 | MECHANICAL DATA SHEET BMP SECONDARY COOLING TOWER 085CWT0002 | A | 2018-05-15 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 010-K-DAT-00001-001 | 010-K-DAT-00001-001 | MECHANICAL DATA SHEET CDU OVERHEAD VAPOR COMPRESSOR 010K0001 A/B | A | 2018-05-09 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 019-K-DAT-00002-001 | 019-K-DAT-00002-001 | MECHANICAL DATA SHEET MAKE-UP HYDROGEN COMPRESSORS 19K0002 19K0003 19K0004 | A | 2018-05-09 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 076551C-000M-DL-1020-001 | 000-K-IDL-70001-001 | DEVIATION LIST FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 076551C-000M-ITP-1020-001 | 000-K-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 076551C-000M-MR-1020-001 | 000-K-MRQ-70001-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 076551C-000M-SP-1020-001 | 000-K-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000045 | 076551C-000M-SR-1020-001 | 000-K-SOW-70001-001 | SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSOR | A | 2018-05-17 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000049 | 019-C-DAT-00004-001 | 019-C-DAT-00004-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR FIRST STAGE COLD HIGH PRESSURE SEPARATOR 019V0004 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-DAT-00006-001 | 019-C-DAT-00006-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR RECYCLE GAS KO DRUM 019V0006 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-DAT-00009-001 | 019-C-DAT-00009-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR SECOND STAEG COLD HIGH PRESSURE SEPARATOR 019V0009 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-DAT-10003-001 | 019-C-DAT-10003-001 | UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION SHEET FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-GAD-00004-001 | 019-C-GAD-00004-001 | MECHANICAL DRAWING FOR 1ST STAGE COLD HIGH PRESSURE SEPARATOR DRRUM 019V0004 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-GAD-00006-001 | 019-C-GAD-00006-001 | MECHANICAL DRAWING FOR RECYCLE GAS K.O. DRUM 019V0006 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-GAD-00009-001 | 019-C-GAD-00009-001 | MECHANICAL DRAWING FOR 2ND STAGE COLD HIGH PRESSURE SEPARATOR DRUM 019V0009 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 019-C-GAD-10003-001 | 019-C-GAD-10003-001 | MECHANICAL DRAWING FOR HP H2S ABSORBER 019C0003 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 076551C-000M-DL-0811-002 | 000-C-IDL-70001-001 | DEVIATION LIST FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 076551C-000M-ITP-0811-002 | 000-C-ITP-70001-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 076551C-000M-MR-0811-002 | 000-C-MRQ-70001-001 | MATERIAL REQUISITION FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 076551C-000M-SP-0811-002 | 000-C-GRD-70001-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000049 | 076551C-000M-SR-0811-002 | 000-C-SOW-70001-001 | SCOPE OF SUPPLY FOR H.P. VESSELS (LLI) | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 2
JVD-OCS-TRA-000050 | 076551C-000R-DL-0710-001 | 000-E-IDL-60007-001 | DEVIATION LIST FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-000R-ITP-0710-001 | 000-E-ITP-60007-001 | INSPECTION AND TEST PLAN (ITP) FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-000R-MR-0710-001 | 000-E-MRQ-60007-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-000R-SP-0710-001 | 000-E-GRD-60007-001 | PARTICULAR TECHNICAL SPECIFICATION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-000R-SR-0710-001 | 000-E-SOW-60007-001 | SCOPE OF SUPPLY FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-018-SP-0710-001 | 018-E-DAT-00005-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E1005 TRAIN 1 - HP/MT FLASH GAS COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-018-SP-0710-002 | 018-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0006 - MP/MT VAPOR COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-018-SP-0710-003 | 018-E-DAT-00003-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0010 - ATM COLUMN REFLUX AIR COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-018-SP-0710-007 | 018-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0007 - QUENCH OIL COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-018-SP-0710-008 | 018-E-DAT-00006-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E2005 - TRAIN 2 - HP/MT FLASH GAS COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-018-SP-0710-011 | 018-E-DAT-00004-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 018E0030 - CIRCULATION OIL AIR COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-021-SP-0710-001 | 021-E-DAT-00001-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0010 HHPS VAPOR AIR COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000050 | 076551C-021-SP-0710-002 | 021-E-DAT-00002-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 021E0011 HLPS VAPOR AIR COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 010-E-DAT-00034-001 | 010-E-DAT-00034-001 | AIR COOLED HEAT EXCHANGERS DATA SHEET FOR 010E0034 BRINE AIR COOLER | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 019-E-DAT-00008-001 | 019-E-DAT-00008-001 | AIR COOLED HEX DATA SHEET FOR 1ST STAGE HHPS VAPOR 019E0008 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 019-E-DAT-00009-001 | 019-E-DAT-00009-001 | AIR COOLED HEX DATA SHEET FOR 2ND STAGE HHPS VAPOR AIR COOLER 019E0012 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 019-E-DAT-00010-001 | 019-E-DAT-00010-001 | AIR COOLED HEX DATA SHEET FOR HLPS VAPOR AIR COOLER 019E0013 | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 076551C-000M-DL-0710-001 | 000-E-IDL-70007-001 | DEVIATION LIST FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 076551C-000M-ITP-0710-001 | 000-E-ITP-70007-001 | INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 076551C-000M-MR-0710-001 | 000-E-MRQ-70007-001 | MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 076551C-000M-SP-0710-001 | 000-E-GRD-70007-001 | PARTICULAR AND TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000051 | 076551C-000M-SR-0710-001 | 000-E-SOW-70007-001 | SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL AIR COOLERS | A | 2018-05-18 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-000R-DL-1011-001 | 000-K-IDL-60002-001 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-000R-ITP-1011-001 | 000-K-ITP-60002-001 | INSPECTION AND TEST PLAN (ITP) FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-000R-MR-1011-001 | 000-K-MRQ-60002-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-000R-SP-1011-001 | 000-K-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-000R-SR-1011-001 | 000-K-SOW-60002-001 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSOR | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-018-SP-1011-001 | 018-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 018K0002 A/B SOUR GAS COMPRESSORS | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-021-SP-1011-001 | 021-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 021K0001 RECYCLE GAS COMPRESSOR | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-021-SP-1012-001 | 021-K-DAT-00002-001 | DATA SHEET FOR SPECIAL PURPOSE STEAM TURBINES FOR 021T0001 RECYCLE GAS COMPRESSOR TURBINE | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-023-SP-1011-001 | 023-K-DAT-00002-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHHET FOR 023K0002 A/B PURGE GAS COMPRESSORS | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
JVD-OCS-TRA-000058 | 076551C-051-SP-1011-001 | 051-K-DAT-00001-001 | CENTRIFUGAL AND AXIAL COMPRESSOR DATA SHEET FOR 051K0001 A/B PROPANE COMPRESSORS | A | 2018-05-23 | FOR OCS INFORMATION | MOC-ROC-SOC |  |  |  | CLASS 1
ROC-ID-000052 | 076551C-000D-RR-1003 | 000-A-RPT-50003-001 | WEEKLY PROGRESS REPORT N.03 AS OF MARCH 30TH, 2018 (WEEK 005) | 0 | 2018-04-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 3
ROC-ID-000053 | 076551C-000D-PP-121 | 000-A-PRO-50015-001 | DEVIATION WAIVER AND TECHNICAL QUERY REQUEST PROCEDURE | A | 2018-04-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 2
ROC-ID-000067 | 076551C-000D-SL-0411-001 | 000-A-INX-50020-001 | BIDDERS LIST FOR 2.25CR-1MO-V REACTORS AND INTERNALS | 0 | 2018-04-09 | FOR INFORMATION | Involved People |  |  |  | CLASS 3
ROC-ID-000067 | 076551C-000D-SL-0610-001 | 000-A-INX-50018-001 | BIDDERS LIST FOR HP S&T HEAT EXCHANGERS | 0 | 2018-04-09 | FOR INFORMATION | Involved People |  |  |  | CLASS 3
ROC-ID-000067 | 076551C-000D-SL-0710-002 | 000-A-INX-50011-001 | BIDDERS LIST FOR AIR COOLERS | 0A | 2018-04-09 | FOR INFORMATION | Involved People |  |  |  | CLASS 3
ROC-ID-000067 | 076551C-000D-SL-1013-001 | 000-A-INX-50019-001 | BIDDERS LIST FOR INTEGRALLY GEARED AIR COMPRESSOR | 0 | 2018-04-09 | FOR INFORMATION | Involved People |  |  |  | CLASS 3
ROC-ID-000163 | 076551C-000D-PP-109 | 000-A-PRO-50007-001 | COMMENT MANAGEMENT PROCEDURE | A | 2018-05-02 | FOR INFORMATION | Involved People |  |  |  | CLASS 2
ROC-ID-000177 | 076551C-000R-DL-0110-003 | 000-F-IDL-60002-001 | DEVIATION LIST 3HDU FIRED HEATER | A | 2018-05-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 1
ROC-ID-000177 | 076551C-000R-ITP-0110-003 | 000-F-ITP-60002-001 | INSPECTION AND TEST PLAN 3HDU FIRED HEATER | A | 2018-05-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 1
ROC-ID-000177 | 076551C-000R-MR-0110-003 | 000-F-MRQ-60002-001 | MATERIAL REQUISITION 3HDU FIRED HEATER | A | 2018-05-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 1
ROC-ID-000177 | 076551C-000R-SP-0110-003 | 000-F-GRD-60002-001 | PARTICULAR TECHNICAL SPECIFICATION FOR 3HDU FIRED HEATER 021F0001 COMBINED FEED HEATER | A | 2018-05-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 1
ROC-ID-000177 | 076551C-000R-SR-0110-003 | 000-F-SOW-60002-001 | SCOPE OF SUPPLY 3HDU FIRED HEATER | A | 2018-05-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 1
ROC-ID-000177 | 076551C-021-SP-0110-001 | 021-F-DAT-00001-001 | EQUIPMENT DATA SHEET FOR FIRED HEATERS FOR 021F0001 COMBINED FEED HEATER | A | 2018-05-04 | FOR INFORMATION | Involved People |  |  |  | CLASS 1
ROC-ID-000218 | 076551C-000D-PP-265 |  | SPLIT OF ELECRICAL ENGINEERING WORKS | A | 2018-05-15 | FOR BAPCO INFORMATION | Involved People