## 000-A-PRI-50002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | always add document title in the header | N.A. | N.A.
2 | Call-out | Page 2 | Ali Abbas | the original ITB list | N.A. | N.A.
3 | Call-out | Page 2 | Ali Abbas | The additional vendor para is not applicable and acceptable for critical systems such as DCS, ESD, MCM, etc. that remains unchanged during the revised additional vendor list. | N.A. | N.A.
4 | Call-out | Page 3 | Raj | This type of auto-approval is not acceptable in any conditions. TTSJV is not supposed to add any new vendors to the list provided in the Contract. If any new addition is required for a very good reason, TTSJV to discuss with Owner and if an pre-agreement is reached, then only Pre-Qualification documentation shall be issued for formal approval. | N.A. | N.A.
5 | Note | Page 3 | peter.gilzean | Adequate HSSE record. | Yes | Y