## 011-F-DAT-00001-001-RAP
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
| Stamp |  | Raj
1 | Call-out |  | 986131 | Clearly specify if the data provided is for Clean or Fouled Pressure Drop (DP). Both clean and fouled DP to be provided. | As per Note 7 data provided it is for fouled condition. Vendor to inform heater pressure drops for clean condition. This comment doesn´t apply for this data. Updated | Y
2 | Text Box |  | 986131 | (Note 56) | Refer to answer to comment 26 | N
3 | Call-out |  | 986131 | Max. Allow./Calc. Inside film Temp. to be specified (inline with API 560). For Vacuum heat suggest considering Maximum 950°F | Max allow/calc inside film temperature shall be defined by Vendor according their knowhow. Please note that no max allowable film temperature is specified for this heater – refer to heater DS. Only max average radiant flux limit shall be respected by heater. | N
4 | Call-out |  | 986131 | Additional note added on page 10/16 | Refer to answer to comment 26 | N
5 | Call-out |  | 986131 | Vendor to also provide the Radiant/Convection duties split. | Note 1 has been updated as follows: 1) The absorbed duty specified is the radiant heat energy absorbed by the process fluid in the radiant section and convection section, plus the heat absorbed in the convection section for LP steam superheating. VENDOR to split Radiant/Convection duties. | Y
6 | Call-out |  | 986131 | Provide the Design Crude blend considered. | note inlcuded | Y
7 | Call-out |  | 986131 | Cover through notes is the inlet pressure refers to clean or fouled condition | Inlet pressure is independent from fouling in heater tubes. This comment doesn´t apply for this data. | N
8 | Call-out |  | 986131 | Add note 57 to row 23 | Refer to answer to comment 26 | N
9 | Call-out |  | 986131 | The term "TR10" to be defined in this data sheet. | Noted and updated | Y
10 | Text Box |  | 986131 | Comments mentioned in page 2/16 are also applicable for this page. | Noted and updated accordign above answers | -
| Cloud |  | 986131
11 | Call-out |  | 986131 | Data to be provided by TR | Refer to note 51, when available data shall be provided | N
| Cloud |  | 986131
12 | Call-out |  | 986131 | Data to be provided by TR | Refer to note 51, when available data shall be provided | N
13 | Call-out |  | Ahmed Bucheeri | ATMOS Residue | Noted and updated | Y
| Line |  | Ahmed Bucheeri
| Arrow |  | Ahmed Bucheeri
14 | Call-out |  | Ahmed Bucheeri | Please specify the temperatuers | Temperatures shall be provided by vendor of Heater | N
15 | Call-out |  | 986131 | Tube Design Pressure to be rechecked based on detail hydraulic calculation and it must be ensured that the number provided is acceptable. | MOC agree with comment. Design Pressure value will be updated, if applicable, based on detail hydraulic calculation. Detailed information will be updated in the context of Note 11 in the next revision. | N
16 | Call-out |  | 986131 | Add note 56 in Row 23 | Refer to answer to comment 26 | N
18 | Text Box |  | Ahmed Bucheeri | Beveled U-Bends | Noted and updated | Y
19 | Call-out |  | Ahmed Bucheeri | What is the basis of selecting this thickness | This are Feed data, what ever this data shall be confirmed/defined by VENDOR according specifications, codes etc. | N
| Arrow |  | Ahmed Bucheeri
| Text Box |  | Ahmed Bucheeri
20 | Call-out |  | Hasan Al Noaimi | R.spools for DDT. Descaling/decocking technology. | Mechanical Decocking is defined as per contract. Type to be defined later DDT is a comercial type of decocking | N
21 | Callout |  | Yousif Ahmedi | Should be 011F0001 | Noted and updated | Y
22 | Callout |  | Yousif Ahmedi | Should be 010F0001 | Noted and updated | Y
23 | Call-out |  | 986131 | Refer note 6: TR to check and confirm | Operating Pressure value will be updated based on detail hydraulic calculation as per Note 6. | N
24 | Call-out |  | 986131 | Ensure the API, ID and FD operate within the operating range of the equipment when 7VDU is shutdown and 7CDU is in turn-down condition. | Note 20 updated as follows: 20) One APH and one Steam APH common with 010F0001 to be provided with one ID fan for flue gas extration and two FD fan (each one for 100% combined CDU/VDU capacity). ID fans and FD fan shall be design also for the special operation case: 7VDU is shutdown with 7CDU operating in turndown case For more detail refer to Document 010-F-DAT-00001-001 | Y
25 | Call-out |  | 986131 | For note 7 - Note that BMPS F1 - item 3.86 - JV to confirm if this requirement supersedes that requirement. Or based on the vendor provided information provided the final coke buildup would be decided. To be clarify in the data sheet. | As per BMPS-F1 para 3,86 data sheet requirement prevails. Final coke buildup shall be provided by VENDOR accordingly. | N
26 | Text Box |  | 986131 | 56) The arrangement of the radiant section coils must ensure that the inside film temperature is kept below the maximum allowable for every single tube. The best practice is to place the outlet tubes close to the top of the radiant section for bottom-fired heaters and avoid stacking the passes i.e do not have one complete pass located above another pass. 57) The cold oil velocity entering the radiant section must be equal or greater than 10 ft/sec. | Please note that no max allowable film temperature is specified for this heater – refer to heater DS. Only max average radiant flux limit shall be respected by heater. ( Based on that Vendor will calculate and inform max film temperature calculated that will correspond to the hottest tube (i.e. outlet tubes) and will be respected on each tube along the entire coil (where anyway the temperature is normally lower compared to the outlet). Moreover please note that note 17 of heater DS require vendor design to ensure “Passes shall be thermally balanced on the flue gas side. Passes shall be hydraulically balanced by symmetrical piping”. This means Vendor shall arrange passes in each firebox to match this requirement. This is normally achieved by heat distribution analysis by vendor and does not imply necessarily to avoid stacked passed or to have the outlets on the top of radiant box on bottom fired heaters. Very important is also to guarantee a self-draining capability of heater coil considering the connecting line up to the vacuum column. No pocket shall be present along the route to the column from the heater outlet. Note 26 on DS already indicate that “ Velocity steam injection point to be foreseen (on crossover/radiant coil). Heater Vendor to confirm steam flow and inform pressure required at the injection point. “ | N
27 | Call-out |  | 986131 | Notes 56 and 57 added. | refer to comment 26 | N
28 | Call-out |  | 986131 | note 50)TR to confirm. | Note 50 updated, pending answer, data shall be provided to vendor when available | Y
29 | Call-out |  | 986131 | note 51)TR to include the vaporization curve in the data sheet. | Note 50 updated, pending answer, data shall be provided to vendor when available | Y
30 | Text Box |  | 986131 | HEATING CURVES TO CASE: DESIGN CRUDE BLEND (Note TR10) | Noted and updated | Y
31 | Call-out |  | 986131 | Add this note to all the relevant pages. | Noted and updated | Y
32 | Text Box |  | 986131 | Add the Isobaric heating curves for the 100% Arab Light case. | Pending data from TPIT. It shall be provideed to Vendor when available | N