## 019-C-GAD-00003-001-RAP-CS REP
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | A.Jabbar Mahmood | CLG's detailed mechanical drawing with the "Fabrication notes" in RD-140630 shall be included when the vendor is selected, | Agreed.
2 | Text Box | 1 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated. | Y
3 | Text Box | 1 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
4 | Text Box | 1 | MAK | Use the latest drawing borders as in BMPS-A-50009 Rev. 1 dated 09-04-2018. | Agreed.
5 | Call-out | 1 | MAK | 019 - NO. 2 HYDROCRACKING UNIT | Agreed, included and updated. | Y
6 | Cloud+ | 1 | A.Jabbar Mahmood | According to the P&IDs and FEED D/S, the rating is 1500#. Check and confirm | But according to calculations the rating is 2500# instead of 1500#.
7 | Cloud+ | 1 | Jawad Alawi | Confirm material type. Swap shell and heads spec | Confirmed material type. | Y
8 | Call-out | 1 | Sameer Foujdar | Pleases include note 25 in the notes. | Agreed, included and updated. | Y
9 | Cloud+ | 1 | bapco-user | Materials Spec. are missing for Ladder & Platform Support/ Piping support | This equipment will not have neither platforms nor ladders because will be assisted by a metallic structure.
10 | Cloud+ | 1 | bapco-user | CA is not as per Note 18 in Page 2 of 3 and FEED Drwg | The CA is indicated in that table for shell and head, internally (WOL) and externally (1,5 mm). The Note 18 indicates the CA for fixed and removable internals.
11 | Callout | 1 | bapco-user | What about Nozzle Flange (Size <=6) | Agreed, this has been corrected and included. | Y
12 | Callout | 1 | bapco-user | Correct: SA 194 GR 8CA | Agreed, corrected and updated. | Y
13 | Text Box | 1 | A.Jabbar Mahmood | This drawing shall be reviewed and approved by the Licensor | Agreed. | Y
14 | Text Box | 2 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated. | Y
15 | Text Box | 2 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
16 | Callout | 2 | Mohamed Ayyash | Allign | Agreed, aligned and updated. | Y
17 | Call-out | 2 | Sameer Foujdar | It is separator not reactor | Agreed, corrected and updated. | Y
18 | Text Box | 3 | Mahdi Ali | Use latest border that includes a different disclaimer note. | Agreed.
19 | Text Box | 3 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated. | Y
20 | Text Box | 3 | Mahdi Ali | This shall be sheet 1 of 3 | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
21 | Text Box | 3 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
22 | Text Box | 3 | Mahdi Ali | 1. Always put the general arrangement as sheet 1. 2. Indicate the equipment number inside the equipment. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.