## 000-A-PPN-60000-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out |  | MAK | Correct drawing numbering format shall be used as per BMPS-A8.
2 | Text Box |  | MAK | -1
3 | Call-out |  | MAK | This field shall indicate the total sheet number of the current drawing. In any case, If the total is one sheet, then it shall be 001
4 | Text Box |  | Ebrahim | General comments : EPC Contractor shall update the existing Refinery Master Plan drawing (BRA-12768) to reflect modifications associated to BMP
5 | Call-out |  | Ebrahim | DRAWING NO. 000-A-PPN-60001-001 Typical
6 | Callout |  | Robert.Kawitzki | Matchline font as per BMPS-A8
7 | Cloud |  | Ebrahim
8 | Callout |  | Robert.Kawitzki | Matchline Drawing Number Missing
9 | Call-out |  | Ebrahim | Avoid writing on the line as possible
10 | Callout |  | Robert.Kawitzki | Text height as per BMPS-A8 6.3.15 Typical comment all drawings If text is too large then drawing shall be split and shown at larger scale
11 | Callout |  | Robert.Kawitzki | Prepared, Checked and Approved to be completed
12 | Text Box |  | Ebrahim | T/X
13 | Text Box |  | Ebrahim | PK
14 | Callout |  | Robert.Kawitzki | Carpark - Typ comment
15 | Cloud |  | Ebrahim
16 | Callout |  | Robert.Kawitzki | Main Roads show northing and easting
17 | Callout |  | Robert.Kawitzki | Arrow to be shown correctly pointing at the sulphur handling
18 | Callout |  | Robert.Kawitzki | Is this a unit limit?
19 | Callout |  | Robert.Kawitzki | Is this a unit limit?
20 | Cloud |  | Mahdi Ali
21 | Arrow |  | Mahdi Ali
22 | Text Box |  | Mahdi Ali | This is a split of Bapco existing drawing. TTSJV shall justify the rational behind this as as existing drawing is already available as indicated by one of comments. This leads to modifying two drawings in the future unless the original master plan is superseded by 'two' drawings. 3. All drawing numbers indicated within the drawing shall be changed to the new Bapco numbering system, i.e. BRA-26131. TTSJV shall request the new number from Bapco. 4. The addition to this drawings is not clear. suggest to cloud the additions or change the line thicknesses for clarity.
23 | Arrow |  | Ebrahim
24 | Text Box |  | Ebrahim | Be consistence
25 | Cloud |  | Ebrahim
26 | Arrow |  | Ebrahim
27 | Arrow |  | Ebrahim
28 | Ellipse |  | Ebrahim
29 | Ellipse |  | Ebrahim
30 | Cloud |  | Edgardo
31 | Call-out |  | Edgardo | Please highlight the areas included in the BMP scope
32 | Cloud |  | Edgardo
33 | Call-out |  | Edgardo | Please highlight the areas covered in the BMP scope
34 | Cloud |  | Edgardo
35 | Arrow |  | Edgardo
36 | Microsoft Word - Code 3 With Comments |  | Adel
37 | Call-out |  | Adel | EPC Contractor to discuss the comment mentioned about update of existing Refinery Master Plan with Bapco prior to any work.