## 000-A-PPN-60001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out |  | MAK | Move the text inside the border
2 | Call-out |  | Ebrahim | This will go in the future, suggestion to be moved as number 7.
3 | Cloud |  | Mahdi Ali
4 | Text Box |  | Mahdi Ali | Sheet number to be added as part of the drawing number.
5 | Callout |  | Robert.Kawitzki | Show correct matchline font
6 | Callout |  | Robert.Kawitzki | Text height as per BMPS-A8 6.3.15 Typical comment all drawings If text is too large then drawing shall be split and shown at larger scale
7 | Callout |  | Robert.Kawitzki | Title block to be fully filled out
8 | Strikethrough |  | Mahdi Ali
9 | Text Box |  | Mahdi Ali | Avoid the word 'NEW'
10 | Arrow |  | Mahdi Ali
11 | Text Box |  | Mahdi Ali | General comments apply from first sheet.
12 | Call-out |  | Ali Hasan | Avoid the word 'NEW'. This comment is also applicable to 000-A-PPN-60003 and other sheets.
13 | Call-out |  | Ali Hasan | Avoid the word 'NEW'. This comment is also applicable to 000-A-PPN-60003 and other sheets
14 | Call-out |  | Ali Hasan | Change to 'Refinery South Flare'. This comment is also applicable to 000-A-PPN-60003 and other sheets
15 | Call-out |  | Nalini Mohan | Modify unit number for N2 plant
16 | Call-out |  | Nalini Mohan | Mark N/E co-ordinates for road centrelines. Typ
17 | Call-out |  | Nalini Mohan | Include SS numbers
18 | Call-out |  | Nalini Mohan | There should be distinction between existing and BMP facilities
19 | Call-out |  | Nalini Mohan | should be OW
20 | Call-out |  | Nalini Mohan | should be RR
21 | Text Box |  | Edgardo | Please highlight the areas that are included in the BMP scope. Note that not all areas shown in this Plot Plan are included in the BMP scope
22 | Call-out |  | Edgardo | Please indicate the drawing number of the plot plan of the respective unit. This is a typical comment for all the units, wherein individual plot plan drawings are also provided
23 | Arrow |  | Edgardo
24 | Cloud |  | Edgardo
25 | Call-out |  | Edgardo | Please modify the format of the unit name / number similar to those of existing units. As an example, rewrite 2HCU as follows: 2HCU Plant No. 019 BRA-229567 This comment is typical for all units
26 | Cloud |  | Edgardo
27 | Call-out |  | Edgardo | Please confirm if this fence will remain as a temporary fence or will be changed to permanent at the completion of the BMP. If the latter is confirmed, the word 'temporary" should be deleted when the as built revision of this drawing is prepared.
28 | Cloud |  | Edgardo
29 | Call-out |  | Edgardo | There are buildings which are labeled R but R is not included in the legend. Only RR, which stands for Rackroom, is included in the legends. This is typical comment, as there are several buildings which are labeled R only.
30 | Call-out |  | Edgardo | Please indicate the coordinates / centerlines of the roads. This comment applies for all roads where the coordinates / centerlines are not yet shown.
31 | Arrow |  | Edgardo
32 | Arrow |  | Edgardo
33 | Arrow |  | Edgardo
34 | Call-out |  | Ali Abbas | State 2HCU SRR and associated number. This is a general comments to all SRR.
35 | Call-out |  | Ali Abbas | Note: The Satellite Rack Room SRR has a name and plant No. to be reflected.
36 | Callout |  | Raj | Current plot space for 7CDU-VDU and 2HCU is potentially inadequate in terms of locating the equipment operating near auto-ignition around access points/roads. During EPC, evaluate and confirm the plot space requirement for well laid out plant from plant safety perspective.
37 | Line |  | Mohamed Ayyash
38 | Typewritten Text |  | Mohamed Ayyash | Slop rerun was demolished many years ago it does not exist. Pls delete
39 | Arrow |  | Mohamed Ayyash
40 | Typewritten Text |  | Mohamed Ayyash | has been converted to platformer office building and work station
41 | Arrow |  | Mohamed Ayyash
42 | Typewritten Text |  | Mohamed Ayyash | Will be removed
43 | Arrow |  | Mohamed Ayyash
44 | Callout |  | Mohamed Ayyash | what is this ?
45 | Callout |  | Mohamed Ayyash | Area for a new control room
46 | Callout |  | Mohamed Ayyash | Name s/s
47 | Arrow |  | Mohamed Ayyash
48 | Arrow |  | Mohamed Ayyash
49 | Arrow |  | Mohamed Ayyash
50 | Arrow |  | Mohamed Ayyash
51 | Microsoft Word - Code 3 With Comments |  | Adel