## 000-A-PRO-50015-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Document Title shall be placed in the header | It will be Reflected | Y
2 | Text Box | Page 1 | Ravi Kumar | The TQ workflow procedure shall be extended further to include which documents will be impacted by the change approval and a tracking procedure to know the referenced documents are updated | Tracking procedure for impacted referenced document is not covered by TQ workflow procedure. | N
3 | Text Box | Page 1 | Stephen.Jackson | Reference also needs to be made to Annex 1, Project Instructions, in particular Para. 5 which provides obligations on the Contractor to provide details on a CTN for any impacts associated with cost, quality or schedule related to Deviations, Waivers, TQ's and Concessions. | For those Deviations, Waivers, and Technical Queries that have cost, quality and/or schedule impact, the Contractor shall proceed in accordance with the Trend Procedure and the Contract provisions for Variations. | Y
4 | Text Box | Page 3 | Jeung.Kim | Please add "Company" in the Section 2 as it may cause confusion. | Company is changed to Owner as described in the section 2. | Y
5 | Text Box | Page 3 | Stephen.Jackson | General, in the event of any conflict between this document and the Contract, the Contract will prevail. | Noted, we will follow Contract requirement. | N
6 | Text Box | Page 4 | Jeung.Kim | Please make a clear identification between JV, Contractor and OC as it is difficult to exactly understand who is the Contractor. | Contractor will be changed to JV | Y
7 | Text Box | Page 4 | Jeung.Kim | Is there no deviation or waiver request other than BMPS? | It will be added other project specifications. | Y
8 | Text Box | Page 4 | Jeung.Kim | Suggested to delete this as no meaning of it | It will be deleted | Y
9 | Text Box | Page 4 | Jeung.Kim | Why does the Contractor include this Owner internal procedure in his procedure?a | It will be deleted | Y
10 | Text Box | Page 4 | Jeung.Kim | what kind of number of it? | It will be deleted | Y
11 | Text Box | Page 5 | Jeung.Kim | Strongly suggest to separate at least for each discipline. | Confirmed to change paragraph as follows: Each waiver request contain each discipline deviation. | Y
12 | Text Box | Page 5 | Jeung.Kim | this cannot be a justification as the Contract signed without such deviation | It will be deleted | Y
13 | Text Box | Page 6 | Jeung.Kim | may not shall | It will be deleted | Y
14 | Text Box | Page 6 | Jeung.Kim | Contractor own evaluation and justification of proposed deviation by vendor has to be included in the request | It will be added. | Y
15 | Callout | Page 6 | Nalini Mohan | Exceptions/deviations on particular items that have been highlighted by multiple vendors only should be formally evaluated and forwarded to Company. Individual exceptions will not be reviewed. | TTSJV will minimize exception/deviations on particular items as much as possible. However, it may propose individual exceptions due to vendor proprietary design. | N
16 | Text Box | Page 7 | Jeung.Kim | Please add procedure for the TQ- who prepare, review and approve for which kind of clarification and query will be issued or other details | As per the appendix 2 Work Flow for Contractor’s Deviation / Waiver / TQ Request, TQ will be prepared by Operating Center Discipline Lead Engineer. OC Engineering manager will evaluate whether TQ will be issued to JVD or not. Also JVD Technical Project Manager and Engineering Manager will make decision whether TQ will be issued to Owner or not. Please be informed that procedure for the TQ is the sama as deviation/waiver. | Y
17 | Text Box | Page 13 | Mahdi Ali | Bapco document number shall be placed in the footer for all other pages | Noted | Y
18 | Text Box | Page 13 | Jeung.Kim | Please add any cost variation(save or addition) due to waiver or deviation | This template is from Attachment 1 of BMPS-A2. | N
19 | Callout | Page 13 | Nalini Mohan | Spell check "Discipline" | Confirmed. | Y
20 | Callout | Page 14 | Nalini Mohan | Conflict resolution form should be different. This form should highlight OWNER's final position only. There is no question of approve or reject | This template is from Attachment 1 of BMPS-A2. | N
21 | Text Box | Page 17 | Mahdi Ali | Bapco document number shall be placed in the footer for all other pages | Confirmed. | Y
22 | Callout | Page 17 | Nalini Mohan | Query form should be different. There is no need for APPROVE/REJECT and also It need not be approved by OWNER Project Director | Query form was discussed and agreed with Bapco. | N