## 000-A-PRO-50039-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  | Harshad.K.Patel
2 | Arrow |  | Mohamed Ayyash
3 | Arrow |  | Mohamed Ayyash
4 | Arrow |  | Mohamed Ayyash
5 | Arrow |  | Mohamed Ayyash
6 | Typewritten Text |  | Mohamed Ayyash | Remove dots from all sub numbers
7 | Text Box |  | Mahdi Ali | Inconsistent naming in other procedures. TTSJV has been used.
8 | Strikethrough |  | Mahdi Ali
9 | Strikethrough |  | Mahdi Ali
10 | Text Box |  | Mahdi Ali | To be consistent, OWNER shall be used
11 | Arrow |  | Jeung.Kim
12 | Text Box |  | Jeung.Kim | Instructed what? Please modify the these statements to fit the purpose.
13 | Rectangle |  | Jeung.Kim
14 | Call-out |  | Jawad Alawi | live
15 | Arrow |  | Jeung.Kim
16 | Text Box |  | Jeung.Kim | Please add this in the reference list in below paragraph 1.6.
17 | Arrow |  | Jeung.Kim
18 | Arrow |  | Jeung.Kim
19 | Text Box |  | Jeung.Kim | Are the Procurement and Construction teams located for each JV Contractor?
20 | Callout |  | Harshad.K.Patel | Overall OC organization chart provided by TTSJV do not show PQM position for each OC.
21 | Highlight |  | Mahdi Ali
22 | Highlight |  | Mahdi Ali
23 | Highlight |  | Mahdi Ali
24 | Text Box |  | Mahdi Ali | TTSJV to be consistent in naming
25 | Typewritten Text |  | Mohamed Ayyash | add space
26 | Arrow |  | Mohamed Ayyash
27 | Cloud |  | Mahdi Ali
28 | Callout |  | Nalini Mohan | Irrespective of scope of work, subcontractors documents should be reviewed by JV before incorporating in the work.
29 | Arrow |  | Mahdi Ali
30 | Callout |  | Raj | Owner need to be part of the Quality Audit team as described in the Bidder's Bid Proposal.
31 | Callout |  | Raj | This Lessons Learnt para needs to be more specific and elaborate. Provide more specifics on the creation of a LL register from previous projects from 3 EPC partners and how they will be implemented on BMP.
32 | Call-out |  | Ali Abbas | Specific lessons learn for multi EPC Contractors project to be discussed and considered to ensure it is covered in this document.
33 | Arrow |  | Jeung.Kim
34 | Arrow |  | Jeung.Kim
35 | Text Box |  | Jeung.Kim | Please provide these refereneces.
36 | Callout |  | Nalini Mohan | How does "project direction" ensure org interfaces? Not clear. Elaborate this imp. apsect
37 | Arrow |  | Mahdi Ali
38 | Text Box |  | Mahdi Ali | How?
39 | Text Box |  | Mahdi Ali | Which software?
40 | Highlight |  | Mahdi Ali
41 | Text Box |  | Mahdi Ali | TTSJV to ensure that cross referencing made to those documents are tracked and removed.
42 | Text Box |  | Mahdi Ali | Suggest to add the AFR template in the appendix for reference.
43 | Callout |  | Raj | Add wordings that any new vendor (not in AVL) can only be added with agreement from Owner.
44 | Call-out |  | Ali Abbas | Need to address K.O meeting with vendor on critical equipment and Owner involvement.
45 | Call-out |  | Jawad Alawi | Typo: BMPS
46 | Callout |  | Nalini Mohan | OWNER shall be consulted regarding disposition of NCRs
47 | Callout |  | Nalini Mohan | Intent is not clear. Please elaborate