## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | always add document title in the header | TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables. | N
2 | Text Box | 1 | Mahdi Ali | what is the equipment number | Due to the Requisition Package is formed by the documents MRQ, SOW, GRD, ITP, and IDL, the equipment included into the scope of this requisition are indicated in MRQ.
3 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all pages | Agreed, this typo has already been corrected and updated. | Y
4 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3. | Noted.
5 | Text Box | 4 | Antony.Bentley | Seismic not applicable | Agreed, this was deleted and updated in the document. | Y
6 | Call-out | 4 | Ahmed Marhoon | Add a note to the suppliers on possibility of modifications in the instrument nozzles details that may occur as a result of Hazop/SIL recommendation and/or EPC design development. | Any possibility of modifications in the nozzles that may occur as a result of Hazop/SIL recommendation and/or EPC design development, it is included into the scope of separate optional quotations; Unitary Price (USD/nozzle) of addition/delete of installed nozzles for the applicable ratings and materials.
7 | Text Box | 5 | Mahdi Ali | remove revision from the document number. add revision 'A' instead. | Agreed, revision has been removed from the document number. | Y
8 | Cloud+ | 5 | bapco-user | 019V0003 and 019V0010 and also correct the other numbers in this page | Agreed, corrected and updated. | Y
9 | Callout | 6 | Mohamed Ayyash | Two (Tyop) | Agreed, corrected and updated. | Y
10 | Call-out | 7 | Ali Abbas | Note: The Nozzles and Connections location for instrumentations shall be confirmed once level measurement type, range and installations are finalized. | This information will be receipt and sent to Vendor, once being defined by the sections of Instruments and Piping.
11 | Callout | 7 | Adnan Alothman | Typo - 4 | Agreed, corrected and updated. | Y
12 | Text Box | 9 | Mahdi Ali | remove revision from the document number. add revision 'A' and revision 'B' instead. | Agreed, revision has been removed from the document number. | Y
13 | Text Box | 10 | Mahdi Ali | remove revision from the document number. add revision 'A' instead. | Agreed, revision has been removed from the document number. | Y
14 | Callout | 13 | Mohamed Ayyash | Should read Commissioning and Start-up (not vise versa) | Agreed, corrected and updated. | Y
15 | Callout | 13 | Mohamed Ayyash | Add "Commissioning" | Agreed, included and updated. | Y
16 | Text Box | 13 | Hasan Asad | Spare parts shall include first run and T&I list of spares. SPIL sheet as per BMPS S-12 shall be provided. | This comment has been included partially, Could you indicate us what do you means with "first run and T&I list of spares"?
17 | Callout | 14 | Mohamed Ayyash | Space | Agreed, corrected and updated. | Y
18 | Callout | 14 | Mohamed Ayyash | Is the commissioning phase included ? | Agreed, included and updated. | Y