## 000-C-GRD-70008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | Page 1 | Ahmed Marhoon | Different addresses are being quoted on different documents issued by MOC. MOC to confirm.
2 | Text Box | Page 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
3 | Stamp | Page 1 | Raj
4 | Cloud+ | Page 3 | Ahmed Marhoon | TTSJV to ensure consistency between all documents in describing the JV structure. Should it read TechnipFMC instead of U.S.A and Italy?. TTSJV to confirm.
5 | Callout | Page 4 | Adnan Alothman | Change BMPS-C3 to BMPS-C2
6 | Callout | Page 4 | Adnan Alothman | Change BMPS-C3 to BMPS-C2
7 | Call-out | Page 5 | 986131 | The level of the tray support rings must be fabricated with the tolerance specified by the internal vendor. This comment is applicable for all the columns in this document.
8 | Callout | Page 6 | Adnan Alothman | Correct document no. to GF-C13950
9 | Callout | Page 6 | Adnan Alothman | Correct document no. to GF-C13950
10 | Call-out | Page 13 | bapco-user | Change SR to SOW
11 | Callout | Page 15 | Mohamed Ayyash | Add the word "commissioning" to this sentence.
12 | Arrow | Page 16 | Mohamed Ayyash
13 | Arrow | Page 16 | Mohamed Ayyash
14 | Callout | Page 16 | Mohamed Ayyash | Add the word "start up" to those sentences.
15 | Pen | Page 16 | Mohamed Ayyash | .