## 000-C-MRQ-70003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets. | Noted. It will be updated in revision A | Y
2 | Cloud+ | 1 | Adnan Alothman | All vessels listed in this MR are CS vessels. TR to check and modify the title | This title is preffered in case a SS vessels need to be quoted in a future
3 | Callout | 2 | Mohamed Ayyash | Correct spacing and underline for better appearance | Noted. It will be updated in revision A | Y
4 | Callout | 2 | Mohamed Ayyash | Align | Noted. It will be updated in revision A | Y
5 | Cloud+ | 2 | A.Jabbar Mahmood | These documents have not been provided to the Owner for review.
6 | Callout | 3 | Mohamed Ayyash | Align | Noted. It will be updated in revision A | Y
7 | Callout | 3 | Mohamed Ayyash | Why dark font (correct inline with others) | Noted. It will be updated in revision A | Y
8 | Text Box | 5 | A.Jabbar Mahmood | Ensure that all applicable licensor specifications and standard drawings are included. E.g licensor drawings RC-940132 and GA-C15105 are missing from the list | Noted. It will be updated in revision A | Y