## 000-E-GRD-80007-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | always add document title in the header | Will be incorporated into PO Material Requisition, after revising the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all Ocs. | N
2 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs | All have been implemented, but will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | Y
3 | Text Box | Page 3 | Dowon Pyun | Company General Comments; 1. Contractor to finalize the width of piperack at the earliest. This will not only help the downstream work progress of the Contractor, but will also eliminate the time loss in the bid evaluation through the fairness of quotation from air cooler Suppliers. 2. The Contractor is required to receive the thermal calculation results throughout Vendors quotation to complete early verification works for the thermal ratings. 3. Considering inland transportation, erection, future maintenance and Vendor's equality opportunity for their bidding, bay/bundle size and weight shall be restricted. Contractor to confirm this. 4. Direct loads transferring from piping manifold to bundle header boxes shall be minimized within the ranges permitted in API 661 and Contractor shall confirm the maximum load conditions to cover external loads under the conditions of Vendor's himself design. | 1. Agreed. Contractor will finalize the width of piperack as soon as possible during the inquiry stage. 2. Agreed. The thermal calculation result will be reflected at the vendor's datasheet, which includes at the quotation. 3. Though the base of transportation is knock-down as per requisition, all the limitations and O&M philosophy will be checked during early stage of project. 4. Agreed. The requirements of lateral movement and nozzle load will be clarified and finalized at the inquiry stage with each vendor and piping. | Y
4 | Callout | Page 5 | Dowon Pyun | Contractor to show document no. | Will be incorporated into PO Material Requisition, after the document format officially issue. | N
5 | Text Box | Page 5 | Dowon Pyun | There are many document numbers specified as PTC-XXX in the scope of supply or particular technical specification, but they are actually not shown in the document list of requisition. This is typical comment to other requisitions. | Will be incorporated into PO Material Requisition. | N
6 | Callout | Page 6 | Salman Jaffer | Please refer to Bid Query T1383 for the requirement for automatic louver | Implemented. The automatic louvers were reflected at the datasheet of air coolers in Sulphur Block, which comply the Bid Query T1383. | Y
7 | Cloud+ | Page 6 | Julio.Aguilar | Supplier | Comment incorporated. | Y
8 | Cloud+ | Page 6 | Sameer.Ahmed | Remove V belts | Comment incorporated. | Y
9 | Callout | Page 6 | Dowon Pyun | Usually flooring grating is handled by Civil. Contractor needs to confirm internally the scope of responsibility and Company recommends the installation of flooring grating in the entire area where air coolers are installed. Compared to cross type walkway, it is excellent in Contractor's constructability and will be helpful for future maintenance by Company | This requirement of flooring (Grating plate) is not for maintenance platform which placed underneath of air cooler, but for header platform. The maintenance platform will be supplied by Civil, and already reflected at the para 3.2 Exclusions as "Motor service platform". And the basis of maintenance platform is the cross type walkway, as per BMPS-E7, para 7.3.5.2. | Y
10 | Call-out | Page 6 | Ali Abbas | Louvers shall be fitted with FF type smart positioner with full diagnostic as per BMPS J specification/standard drawings/AVL to meet project design with position indication in the DCS. I/P not to be used. Need to attached applicable BMPSs and also reference Inst Air pressure for the actuator design. | This will reflect during vendor clarification and PO. | N
11 | Callout | Page 7 | Salman Jaffer | Please add (Free draining whenever applicable per the data sheet or PIDs | This is the part of supply materials. It will clarify with vendor during inquiry, not reflect at requisition. | N
12 | Call-out | Page 7 | Ali Abbas | Refer to spec for SS type | Pneumatic actuators for variable blade pitch has been deleted, there is only adjustable fan blade pitch as per datasheet. However, the tubing material for automatic louver was changed to 316SS. | Y
13 | Callout | Page 7 | Syed Ahmed | Local start/stop switch box at platform, stop switch box at grade level and stop DCS switch. | This will reflect during vendor clarification and PO. | N
14 | Callout | Page 7 | Syed Ahmed | The nameplate shall be made of stainless steel and be fixed to a non-removal part of the frame.in addition, motor with VFD shall be provided with additional nameplate information showing related data. as per BMPS -P19 | Motor nameplate is reflected, and the detail information of nameplate will be clarified at the vendor print stage. | Y
15 | Callout | Page 7 | Dowon Pyun | When transition beams are installed, the maintenance floor shall NOT be stepped. | Transition beams and maintenance floor will be supplied by Civil. The comment will be noted. | Y
16 | Text Box | Page 7 | Hasan Asad | Add: Spare interchangeable belts | There is no capital spare requirement for belts at BMPS specification, and this part is contrator's spare parts during construction, pre-commissioning commissioning and start up. If spare interchangeable belts is needed for operation, it shall be included at 2 years spare part. | N
17 | Callout | Page 9 | Dowon Pyun | requisition | Comment incorporated. | Y
18 | Callout | Page 9 | Dowon Pyun | Contractor to add project specification 2520-Z000-MS6740-52, Material Preservation during Construction, Pre-commissioning and Commissioining. Accordingly this statement shall be corrected and Company considers that the start period is based on the completion of on-site delivery. | This will reflect during vendor clarification and PO. | N
19 | Callout | Page 10 | BD Mori | Based on the highest temperature expected at inlet to the cooler at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario specified in the air coolers data sheets, if required the vendor shall perform FEA analysis. | To be reviewed with FEED/Licensor, if required. | N
20 | Callout | Page 10 | Dowon Pyun | Delete this paragraph since noise requirement is covered by next para. 5.6 | Comment incorporated. | Y
21 | Text Box | Page 11 | Antony.Bentley | Earthquake loads need not be considered BMPS-M1 - 7.15 | Comment incorporated. | Y
22 | Arrow | Page 11 | Antony.Bentley
23 | Cloud+ | Page 11 | Julio.Aguilar | Replace by "Supplier" throughout all document | Comment incorporated. | Y
24 | Callout | Page 11 | Sameer.Ahmed | Addition (as applicable) loads described in BMPS-A1 Section 10.7 to be considered | These loads are remarked at GA drawings, because main load for each supporting columns. Other loads (Nozzle load and etc.) which described in BMPS-A1 will be verified at another document, such as calculation sheet. | N
25 | Text Box | Page 11 | Hasan Asad | Add: Fan and Motor bearings lubrication points shall be extended to the platform level for on-line greasing. | This will reflect during vendor clarification and PO. | N
26 | Callout | Page 11 | Dowon Pyun | Insert "In addition to documents and drawings supply required in 000-E-SOW-80007-001-RAP," | Comment incorporated. | Y
27 | Text Box | Page 12 | Hasan Asad | Portable heavy lifter shall be provided for ease of rigging of motor, fan, etc. | This shall be separately discussed with respect to operation and maintenance. | N
28 | Text Box | Page 14 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
29 | Cloud | Page 15 | Mahdi Ali
30 | Callout | Page 15 | Sameer.Ahmed | Why cooler 371E0001 is not included in this list? TTSJV to advise if this cooler will be purchased under another MR | 371E0001 is scope of ROC. So it will be included at the requisition of ROC. | Y
31 | Text Box | Page 16 | Hasan Asad | SAT for entire bank rotating units and structure to verify structure and equipment vibration levels. | This SAT will perform by contactor, not by vendor. So it will not be included at this requisition, but the preparation will be done by vendor. | N
32 | Text Box | Page 18 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
33 | Text Box | Page 20 | Hasan Asad | Applicable to all data sheets comments: 1. Lubrication points shall be extended to platform level for ease of lubrication without shutting down the equipment. 2. Vibration pick-up points shall be accessible for routine condition monitoring. 3. SAT shall be performed including machinery vibration, bearing temperature, alignment verification, belt tightness test, etc. | 1. Agreed. It will be reflected during vendor clarification and PO. 2. Vibration cut-off switch will be installed at the accessible position, as per BMPS-E7 and datasheet. 3. These SATs will perform by contactor, not by vendor. So it will not be included at this requisition, but the preparation will be done by vendor. | N