## 000-E-ITP-80007-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | Page 1 | Dowon Pyun | Criticality rating is directly affected the inspection level thus this work shall be done in advance to the decision of inspection level | All air coolers are Criticality Rating "C" as per 2520-z000-PP-611 and matched Inspection Level is 3. | Y
2 | Text Box | Page 2 | Sankara | Variable | Document has been revised from 'various' to 'variable' | Y
3 | Callout | Page 2 | Saeed Taher | Add C for contractor all pages | 1. C has been added in all pages. 2. General note has been added in the cover sheet of ITP as follows ; Supplier’s Fabrication and Quality Control Plan shall include a column for Owner with same attendance level as the one reserved to Contractor. | Y
4 | Callout | Page 2 | Saeed Taher | Add O for owner all pages | 1. O has been added in all pages. 2. General note has been added in the cover sheet of ITP as follows ; Supplier’s Fabrication and Quality Control Plan shall include a column for Owner with same attendance level as the one reserved to Contractor. | Y
5 | Callout | Page 2 | Saeed Taher | Owner inspection requirements to be finalized during the ITP finalization with the vendor | General note has been added in the cover sheet of ITP as follows ; Supplier’s Fabrication and Quality Control Plan shall include a column for Owner with same attendance level as the one reserved to Contractor. Owner inspection involvement will be finalized during Supplier's Quality Control Plan(or ITP) approval stage. | Y
6 | Callout | Page 2 | Saeed Taher | Add WPS & PQR for all welded equipment - BMPS-B1 | Activity "WPS & PQR" has been added as review. 'Review as per applicable specification' shall be stated instead of "BMPS-B1" since there are additional requirements regarding WPS & PQR on other BMPS specifications. (Such as BMPS-B7) | Y
7 | Text Box | Page 2 | Hasan Asad | SAT for entire back machinery for equipment and structure vibration level. | SAT(Site Acceptance Test) is not included in the ITP since it is not the scope of Vendor. During shop run-in test, vibration for the equipment and structure shall be checked as per specified in the requisition. | N
8 | Callout | Page 4 | Saeed Taher | Instruments | Component Type has been revised to "Instruments" | Y
9 | Callout | Page 4 | Dowon Pyun | Contractor to recheck all components of type in this ITP | Component Type has been re-checked and revised accordingly. | Y
10 | Callout | Page 5 | Saeed Taher | Electric Motors and Various Speed | Component Type has been revised to "ELECTRIC MOTORS AND VARIABLE SPEED DRIVERS" | Y
11 | Callout | Page 6 | Dowon Pyun | Activities are not applicable to bundle & headers | Component Type has been revised to "ELECTRIC MOTORS AND VARIABLE SPEED DRIVERS" | Y