## 000-E-MRQ-80007-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
2 | Callout | Page 1 | Jong.Ahn | Pls add equipment number with P&ID. | Will be clarified with vendor during inquiry stage and incorporated into PO Material Requisition, after P&ID official issue. | N
3 | Text Box | Page 1 | Jeung.Kim | Typical comment for the Data Sheets: All data sheets have to be updated according to detail design development of all related disciplines and any updating has to be implemented in the equipment purchase order. | Will be incorporated into PO Material Requisition. | N
4 | Text Box | Page 1 | Dowon Pyun | Add following std. specifications; BMPS-SF-A-700 | It was included at 5 page. | Y
5 | Text Box | Page 2 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
6 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
7 | Callout | Page 3 | Dowon Pyun | Not applicable for Vendor's scope of supply | Comment incorporated. Deleted. | Y
8 | Callout | Page 3 | Dowon Pyun | Add BMPS-E1, Heat Exchangers - General Requirements | JV made decided not to attached BMPS-C1 and E1 at the requisitions, because these are general specfication for FEED and need not to vendor. | N
9 | Text Box | Page 3 | Dowon Pyun | P&IDs should be in requisition showing the type of vibration detection and the temperature control such by fan pitch, driver, louver or air recirculation system. | Will be clarified with vendor during inquiry stage and incorporated into PO Material Requisition, after P&ID official issue. | N
10 | Call-out | Page 4 | Ebrahim | Add BMPS-P1 | Comment incorporated. | Y
11 | Callout | Page 4 | Dowon Pyun | Add BMPS-S-50814, Utility Consumption Summary Add BMPS-S-50815, Utility Electrical Consumer List | Comment incorporated. | Y
12 | Callout | Page 4 | Dowon Pyun | Add BMPS-M6, Fireproofing | Comment incorporated. | Y
13 | Text Box | Page 4 | Dowon Pyun | Add job specification 2520-Z000-MS-6740-52 for Material Preservation During Construction, Pre-Commissioning and Commissioning | Will be incorporated into PO Material Requisition. | N